## Project_Info
Project Name | Client | Consultant | Contractor | Start Date | Finish Date | Contract Duration (Days) | Contract Value
MASEEL MIXED-USE DEVELOPMENT | Oroub investment | Saudi Diyar Consultants | Alenshaiah Contracting Co | 2025-10-01 | 2027-03-31 | 18 Months | 672483500

## Overall_Progress
Report Date | Planned % | Actual % | Variance % | SPI | BL Start Date | BL Finish Date | Forecast Finish Date | Variance Finish Date | Project Duration | Time Elapsed | Remaining Time | Time Elapsed %
2026-06-21 | 9.911% | 9.837% | -0.07407% | 0.99253 | 2025-10-01 | 2027-03-31 | 2027-03-31 | 0 | 547 | 263 | 284 | 48.08%

## Phase_Progress
Phase | Planned % | Actual % | Variance | SPI
Phase-1 | 14.99% | 14.21% | -0.7846% | 0.94767
Phase-2 | 1.604% | 1.694% | 0.09059% | 1.0565
Phase-3 | 10.26% | 10.3% | 0.03947% | 1.0038
Phase-4 | 0.7122% | 0.7151% | 0.002907% | 1.0041
Phase-5 | 5.501% | 6.342% | 0.8409% | 1.1529

## Activities
Activity ID | Activity Name | Original Duration | Activity Status | 02- Con.Phase | BL Project Start | BL Project Finish | Start | Finish | Schedule % Complete | Performance % Complete | Total Float | Critical
MS.EN.P1.ALL.101 | Receive of Geophysical report and soil improvement proposal for Phase 1 | 0 | Completed | Con.Phase 01 |  | 2025-10-23 |  | 13-Oct-25 A | 100% | 100% |  | No
MS.EN.P1.ALL.105 | Soil Improvement (By Other) | 10 | Completed | Con.Phase 01 | 2025-11-29 | 2025-12-09 | 29-Nov-25 A | 22-Dec-25 A | 100% | 100% |  | No
MS.CO.P1.FO.280 | Earthing and Lightning Protection System | 6 | Completed | Con.Phase 01 | 2026-01-18 | 2026-01-24 | 02-Dec-25 A | 06-Jan-26 A | 100% | 100% |  | No
MS.EN.P3.ALL.102 | Geophysical and soil improvement proposal | 0 | Completed | Con.Phase 03 | 2025-12-10 | 2025-12-10 | 10-Dec-25 A | 27-Dec-25 A | 100% | 100% |  | No
A1000 | Post-Grouting Verification Test | 6 | Completed | Con.Phase 01 | 2025-12-10 | 2025-12-16 | 10-Dec-25 A | 28-Dec-25 A | 100% | 100% |  | No
MS.EN.P2.ALL.108 | Soil Improvement (By Other) | 82 | Completed | Con.Phase 02 | 2026-03-10 | 2026-06-22 | 21-Dec-25 A | 15-Jun-26 A | 95.12% | 100% |  | No
MS.EN.P3.ALL.107 | Soil Improvement (By Other) | 21 | Completed | Con.Phase 03 | 2026-01-12 | 2026-02-04 | 28-Dec-25 A | 14-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.100 | Excavation for drop Panels and Trenches | 9 | Completed | Con.Phase 01 | 2026-01-01 | 2026-01-11 | 01-Jan-26 A | 03-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.140 | Earthing and Lightning Protection System | 6 | Completed | Con.Phase 01 | 2026-01-27 | 2026-02-02 | 04-Jan-26 A | 07-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.270 | Excavation for drop Panels and Trenches | 5 | Completed | Con.Phase 01 | 2026-01-12 | 2026-01-17 | 04-Jan-26 A | 10-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.101 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 01 | 2026-02-03 | 2026-02-07 | 06-Jan-26 A | 02-Feb-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.169 | Report preparation and Soil Improvement Proposal | 8 | Completed | Con.Phase 02 | 2026-02-26 | 2026-03-09 | 06-Jan-26 A | 11-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.340 | Excavation for drop Panels and Trenches | 5 | Completed | Con.Phase 01 | 2026-01-18 | 2026-01-22 | 08-Jan-26 A | 17-Jan-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.139 | Perform Geophysical Activity | 0 | Completed | Con.Phase 05 | 2026-02-01 | 2026-02-01 | 10-Jan-26 A | 11-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.410 | Excavation for drop Panels and Trenches | 5 | Completed | Con.Phase 01 | 2026-01-24 | 2026-01-28 | 10-Jan-26 A | 19-Jan-26 A | 100% | 100% |  | No
A1030 | Temporary Alternative Ramp Construction | 18 | Completed | Con.Phase 03 | 2026-03-03 | 2026-03-30 | 10-Jan-26 A | 12-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.350 | Earthing and Lightning Protection System | 4 | Completed | Con.Phase 01 | 2026-01-24 | 2026-01-27 | 11-Jan-26 A | 13-Jan-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.149 | Report preparation and Soil Improvement Proposal | 7 | Completed | Con.Phase 05 | 2026-02-01 | 2026-02-08 | 12-Jan-26 A | 18-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.290 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 01 | 2026-02-08 | 2026-02-11 | 12-Jan-26 A | 14-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.102 | Block work for Drop Panels | 3 | Completed | Con.Phase 01 | 2026-02-08 | 2026-02-10 | 13-Jan-26 A | 17-Jan-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.129 | Soil Improvement (By Other) | 5 | Completed | Con.Phase 05 | 2026-02-09 | 2026-02-14 | 13-Jan-26 A | 28-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.360 | Blinding concrete for lower Part of Foundation | 3 | Completed | Con.Phase 01 | 2026-02-12 | 2026-02-15 | 13-Jan-26 A | 18-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.420 | Earthing and Lightning Protection System | 6 | Completed | Con.Phase 01 | 2026-01-29 | 2026-02-04 | 13-Jan-26 A | 19-Jan-26 A | 100% | 100% |  | No
A1010 | Post-Grouting Verification Test | 19 | Completed | Con.Phase 03 | 2026-02-05 | 2026-03-02 | 14-Jan-26 A | 21-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.103 | Blinding concrete for Upper Part | 3 | Completed | Con.Phase 01 | 2026-02-11 | 2026-02-14 | 19-Jan-26 A | 03-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.300 | Block work for Drop Panels | 3 | Completed | Con.Phase 01 | 2026-02-12 | 2026-02-15 | 19-Jan-26 A | 20-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.310 | Blinding concrete for Upper Part | 3 | Completed | Con.Phase 01 | 2026-02-16 | 2026-02-18 | 19-Jan-26 A | 02-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.370 | Block work for Drop Panels | 2 | Completed | Con.Phase 01 | 2026-02-16 | 2026-02-17 | 19-Jan-26 A | 21-Jan-26 A | 100% | 100% |  | No
MS.CO.P1.FO.430 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 01 | 2026-02-16 | 2026-02-19 | 19-Jan-26 A | 01-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.100 | Excavation for drop Panels and Trenches | 6 | Completed | Con.Phase 03 | 2026-02-14 | 2026-02-19 | 20-Jan-26 A | 23-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.380 | Blinding concrete for Upper Part | 3 | Completed | Con.Phase 01 | 2026-02-19 | 2026-02-24 | 20-Jan-26 A | 03-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.139 | Excavation for drop Panels and Trenches | 6 | Completed | Con.Phase 03 | 2026-02-23 | 2026-03-02 | 21-Jan-26 A | 18-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.189 | Excavation for drop Panels and Trenches | 6 | Completed | Con.Phase 03 | 2026-03-03 | 2026-03-10 | 21-Jan-26 A | 22-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.440 | Block work for Drop Panels | 3 | Completed | Con.Phase 01 | 2026-02-23 | 2026-02-25 | 21-Jan-26 A | 03-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(2).FO.100 | Excavation for drop Panels and Trenches | 8 | Completed | Con.Phase 03 | 2026-06-06 | 2026-06-14 | 25-Jan-26 A | 18-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.104 | Surface preparation and Angle filet at RW Edge | 3 | Completed | Con.Phase 01 | 2026-02-15 | 2026-02-17 | 26-Jan-26 A | 08-Feb-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.159 | Perform Geophysical Activity | 6 | Completed | Con.Phase 02 | 2026-01-26 | 2026-02-01 | 26-Jan-26 A | 09-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.105 | Water Proofing Membrane under Raft Foundation | 9 | Completed | Con.Phase 01 | 2026-02-18 | 2026-03-03 | 27-Jan-26 A | 17-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.450 | Blinding concrete for Upper Part | 3 | Completed | Con.Phase 01 | 2026-02-26 | 2026-03-02 | 27-Jan-26 A | 11-Feb-26 A | 100% | 100% |  | No
A1050 | Post-Grouting Verification Test | 5 | Completed | Con.Phase 05 | 2026-02-15 | 2026-02-19 | 29-Jan-26 A | 01-Mar-26 A | 100% | 100% |  | No
MS.EN.P1.ALL.125 | Soil Improvement For Part 5 (By Other) | 15 | Completed | Con.Phase 01 | 2026-02-07 | 2026-02-25 | 02-Feb-26 A | 19-Feb-26 A | 100% | 100% |  | No
MS.EN.P4.ALL.104 | Package Preparation and Signed Contract with Subs | 10 | Completed | Con.Phase 04 | 2026-02-07 | 2026-02-17 | 04-Feb-26 A | 22-Feb-26 A | 100% | 100% |  | No
MS.EN.P4.ALL.102 | Receive of Geophysical report and soil improvement proposal | 0 | Completed | Con.Phase 04 | 2026-02-07 |  | 04-Feb-26 A |  | 100% | 100% |  | No
MS.CO.P1.FO.320 | Surface preparation and Angle filet at RW Edge | 4 | Completed | Con.Phase 01 | 2026-02-19 | 2026-02-25 | 07-Feb-26 A | 10-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.101 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 03 | 2026-03-03 | 2026-03-08 | 08-Feb-26 A | 28-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.149 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 03 | 2026-03-09 | 2026-03-12 | 08-Feb-26 A | 28-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.209 | Block work for Drop Panels | 4 | Completed | Con.Phase 03 | 2026-03-26 | 2026-03-30 | 09-Feb-26 A | 09-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.550 | Earthing and Lightning Protection System | 4 | Completed | Con.Phase 03 | 2026-03-11 | 2026-03-16 | 09-Feb-26 A | 28-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.510 | Earthing and Lightning Protection System | 4 | Completed | Con.Phase 03 | 2026-03-03 | 2026-03-08 | 10-Feb-26 A | 28-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.199 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 03 | 2026-03-17 | 2026-03-25 | 10-Feb-26 A | 04-Mar-26 A | 100% | 100% |  | No
MS.CO.P5.FO.100 | Excavation for drop Panels and Trenches | 20 | Completed | Con.Phase 05 | 2026-02-23 | 2026-03-25 | 11-Feb-26 A | 01-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(2).FO.101 | Blinding concrete for lower Part of Foundation | 4 | Completed | Con.Phase 03 | 2026-06-17 | 2026-06-21 | 11-Feb-26 A | 22-Mar-26 A | 25% | 100% |  | No
MS.CO.P1.FO.260 | Earthing and Lightning Protection System | 2 | Completed | Con.Phase 03 | 2026-06-15 | 2026-06-16 | 11-Feb-26 A | 23-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.330 | Water Proofing Membrane under Raft Foundation | 8 | Completed | Con.Phase 01 | 2026-02-26 | 2026-03-09 | 11-Feb-26 A | 18-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.390 | Surface preparation and Angle filet at RW Edge | 3 | Completed | Con.Phase 01 | 2026-02-25 | 2026-03-01 | 11-Feb-26 A | 15-Feb-26 A | 100% | 100% |  | No
MS.CO.P1.FO.460 | Surface preparation and Angle filet at RW Edge | 4 | Completed | Con.Phase 01 | 2026-03-03 | 2026-03-08 | 11-Feb-26 A | 16-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.102 | Block work for Drop Panels | 4 | Completed | Con.Phase 03 | 2026-03-09 | 2026-03-12 | 12-Feb-26 A | 29-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.159 | Block work for Drop Panels | 4 | Completed | Con.Phase 03 | 2026-03-15 | 2026-03-18 | 12-Feb-26 A | 28-Feb-26 A | 100% | 100% |  | No
MS.EN.P5.ALL.104 | Ramp Removal | 82 | In Progress | Con.Phase 05 | 2026-03-17 | 2026-06-28 | 12-Feb-26 A | 2026-06-28 | 89.02% | 93% | 0 | Yes
MS.CO.P3(2).FO.102 | Block work for Drop Panels | 4 | Completed | Con.Phase 03 | 2026-06-22 | 2026-06-25 | 14-Feb-26 A | 24-Mar-26 A | 0% | 100% |  | No
MS.CO.P3(1).FO.103 | Blinding concrete for Upper Part | 2 | Completed | Con.Phase 03 | 2026-03-15 | 2026-03-16 | 15-Feb-26 A | 03-May-26 A | 100% | 100% |  | No
MS.CO.P3(2).FO.103 | Blinding concrete for Upper Part | 2 | Completed | Con.Phase 03 | 2026-06-27 | 2026-06-28 | 15-Feb-26 A | 06-Apr-26 A | 0% | 100% |  | No
MS.CO.P1.FO.150 | Earthing and Lightning Protection System | 6 | Completed | Con.Phase 03 | 2026-02-23 | 2026-03-02 | 15-Feb-26 A | 01-Mar-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.219 | Blinding concrete for Upper Part | 2 | Completed | Con.Phase 03 | 2026-03-31 | 2026-04-01 | 16-Feb-26 A | 11-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.106 | Rebars for 1st layer for Foundation | 15 | Completed | Con.Phase 01 | 2026-03-04 | 2026-03-28 | 17-Feb-26 A | 29-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.400 | Water Proofing Membrane under Raft Foundation | 4 | Completed | Con.Phase 01 | 2026-03-02 | 2026-03-05 | 18-Feb-26 A | 28-Feb-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.169 | Blinding concrete for Upper Part | 2 | Completed | Con.Phase 03 | 2026-03-19 | 2026-03-25 | 18-Feb-26 A | 04-Mar-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.112 | Water Proofing Membrane under Raft Foundation | 12 | Completed | Con.Phase 03 | 2026-03-17 | 2026-04-04 | 23-Feb-26 A | 03-May-26 A | 100% | 100% |  | No
MS.EN.P4.ALL.111 | CMC Engineering and Tests Works | 22 | Completed | Con.Phase 04 | 2026-02-18 | 2026-03-25 | 23-Feb-26 A | 26-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.229 | Water Proofing Membrane under Raft Foundation | 12 | Completed | Con.Phase 03 | 2026-04-02 | 2026-04-15 | 26-Feb-26 A | 18-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.470 | Water Proofing Membrane under Raft Foundation | 3 | Completed | Con.Phase 01 | 2026-03-09 | 2026-03-11 | 01-Mar-26 A | 21-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.111 | Rebars for 1st layer for Foundation | 9 | Completed | Con.Phase 01 | 2026-03-11 | 2026-03-26 | 04-Mar-26 A | 16-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.116 | Rebars for 1st layer for Foundation | 9 | Completed | Con.Phase 01 | 2026-03-28 | 2026-04-06 | 08-Mar-26 A | 30-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.105 | Rebars for 1st layer for Foundation | 9 | Completed | Con.Phase 03 | 2026-04-05 | 2026-04-14 | 08-Mar-26 A | 12-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.160 | Excavation for drop Panels and Trenches | 7 | Completed | Con.Phase 01 | 2026-03-08 | 2026-03-16 | 08-Mar-26 A | 01-Apr-26 A | 100% | 100% |  | No
MS.EN.P4.ALL.147 | CMC Drilling and casting | 55 | Completed | Con.Phase 04 | 2026-03-26 | 2026-06-01 | 15-Mar-26 A | 01-Jun-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.179 | Water Proofing Membrane under Raft Foundation | 12 | Completed | Con.Phase 03 | 2026-03-26 | 2026-04-08 | 18-Mar-26 A | 25-Mar-26 A | 100% | 100% |  | No
MS.CO.P1.FO.114 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Completed | Con.Phase 01 | 2026-04-07 | 2026-04-16 | 22-Mar-26 A | 16-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.107 | Installation for Mechanical and Electrical Embeds | 9 | Completed | Con.Phase 01 | 2026-03-17 | 2026-03-31 | 24-Mar-26 A | 01-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.112 | Installation for Mechanical and Electrical Embeds | 9 | Completed | Con.Phase 01 | 2026-03-28 | 2026-04-06 | 24-Mar-26 A | 01-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.109 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Completed | Con.Phase 01 | 2026-04-01 | 2026-04-11 | 25-Mar-26 A | 11-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.104 | Rebars for 1st layer for Foundation | 9 | Completed | Con.Phase 03 | 2026-04-09 | 2026-04-19 | 25-Mar-26 A | 12-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.109 | Rebars for 1st layer for Foundation | 6 | Completed | Con.Phase 03 | 2026-04-20 | 2026-04-26 | 25-Mar-26 A | 12-May-26 A | 100% | 100% |  | No
A1040 | Post-Grouting Verification Test For 25% | 6 | Completed | Con.Phase 01 | 2026-02-26 | 2026-03-05 | 26-Mar-26 A | 26-Mar-26 A | 100% | 100% |  | No
MS.CO.P3(2).FO.106 | Water Proofing Membrane under Raft Foundation | 12 | Completed | Con.Phase 03 | 2026-03-29 | 2026-04-11 | 29-Mar-26 A | 14-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.170 | Earthing and Lightning Protection System | 3 | Completed | Con.Phase 01 | 2026-03-29 | 2026-04-01 | 29-Mar-26 A | 08-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.107 | Installation for Mechanical and Electrical Embeds | 9 | Completed | Con.Phase 03 | 2026-03-30 | 2026-04-08 | 30-Mar-26 A | 24-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.106 | Installation for Mechanical and Electrical Embeds | 6 | Completed | Con.Phase 03 | 2026-03-31 | 2026-04-06 | 31-Mar-26 A | 19-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.180 | Blinding concrete for lower Part of Foundation | 2 | Completed | Con.Phase 01 | 2026-03-31 | 2026-04-02 | 31-Mar-26 A | 02-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.117 | Installation for Mechanical and Electrical Embeds | 9 | Completed | Con.Phase 01 | 2026-04-01 | 2026-04-11 | 01-Apr-26 A | 15-Apr-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.114 | Installation for Mechanical and Electrical Embeds | 11 | Completed | Con.Phase 03 | 2026-04-01 | 2026-04-13 | 01-Apr-26 A | 24-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.230 | Earthing and Lightning Protection System | 4 | Completed | Con.Phase 05 | 2026-04-01 | 2026-04-05 | 01-Apr-26 A | 18-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.190 | Block work for Drop Panels | 2 | Completed | Con.Phase 01 | 2026-04-02 | 2026-04-05 | 02-Apr-26 A | 05-Apr-26 A | 100% | 100% |  | No
MS.CO.P1.FO.121 | Rebars for 1st layer for Foundation | 9 | Completed | Con.Phase 01 | 2026-04-07 | 2026-04-16 | 04-Apr-26 A | 14-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.113 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Completed | Con.Phase 03 | 2026-04-04 | 2026-04-13 | 04-Apr-26 A | 03-Jun-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.111 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Completed | Con.Phase 03 | 2026-04-04 | 2026-04-13 | 04-Apr-26 A | 24-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.122 | Installation for Mechanical and Electrical Embeds | 9 | Completed | Con.Phase 01 | 2026-04-05 | 2026-04-14 | 05-Apr-26 A | 19-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.116 | Formwork for Foundations | 62 | Completed | Con.Phase 03 | 2026-04-05 | 2026-06-18 | 05-Apr-26 A | 16-Jun-26 A | 98.39% | 100% |  | No
MS.CO.P1.FO.200 | Blinding concrete for Upper Part | 55 | In Progress | Con.Phase 01 | 2026-04-05 | 2026-06-11 | 05-Apr-26 A | 2026-06-18 | 100% | 99.82% | 237 | No
MS.CO.P5.FO.101 | Blinding concrete for lower Part of Foundation | 62 | In Progress | Con.Phase 05 | 2026-04-07 | 2026-06-21 | 07-Apr-26 A | 2026-06-28 | 95.16% | 95% | 228 | No
MS.CO.P1.FO.113 | Formwork for Foundations | 6 | Completed | Con.Phase 01 | 2026-04-09 | 2026-04-15 | 09-Apr-26 A | 17-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.210 | Surface preparation and Angle filet at RW Edge | 51 | In Progress | Con.Phase 01 | 2026-04-09 | 2026-06-11 | 09-Apr-26 A | 2026-06-18 | 100% | 99.9% | 237 | No
MS.CO.P1.FO.220 | Water Proofing Membrane under Raft Foundation | 52 | In Progress | Con.Phase 01 | 2026-04-11 | 2026-06-14 | 11-Apr-26 A | 2026-06-21 | 100% | 95% | 234 | No
MS.CO.P3(1).FO.118 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 53 | Completed | Con.Phase 03 | 2026-04-12 | 2026-06-15 | 12-Apr-26 A | 16-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.108 | Formwork for Foundations | 6 | Completed | Con.Phase 01 | 2026-04-13 | 2026-04-19 | 13-Apr-26 A | 18-May-26 A | 100% | 100% |  | No
MS.CO.P5.FO.102 | Block work for Drop Panels | 6 | Completed | Con.Phase 05 | 2026-04-13 | 2026-04-20 | 13-Apr-26 A | 09-May-26 A | 100% | 100% |  | No
MS.CO.P1.FO.119 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Completed | Con.Phase 01 | 2026-04-14 | 2026-04-23 | 14-Apr-26 A | 02-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.124 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 7 | Completed | Con.Phase 01 | 2026-04-15 | 2026-04-22 | 15-Apr-26 A | 19-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.110 | Formwork for Foundations | 45 | Completed | Con.Phase 03 | 2026-04-19 | 2026-06-13 | 19-Apr-26 A | 13-Jun-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.108 | Formwork for Foundations | 44 | Completed | Con.Phase 03 | 2026-04-25 | 2026-06-17 | 20-Apr-26 A | 09-Jun-26 A | 100% | 100% |  | No
MS.CO.P3(2).FO.118 | Rebars for 1st layer for Foundation | 49 | In Progress | Con.Phase 03 | 2026-04-20 | 2026-06-18 | 20-Apr-26 A | 2026-06-25 | 97.96% | 65% | 28 | No
MS.CO.P5.FO.103 | Blinding concrete for Upper Part | 50 | In Progress | Con.Phase 05 | 2026-04-21 | 2026-06-22 | 21-Apr-26 A | 2026-06-29 | 93.6% | 85% | 227 | No
MS.CO.P1.FO.118 | Formwork for Foundations | 46 | Completed | Con.Phase 01 | 2026-04-25 | 2026-06-20 | 25-Apr-26 A | 15-Jun-26 A | 95.65% | 100% |  | No
MS.CO.P5.FO.104 | Water Proofing Membrane under Raft Foundation | 47 | In Progress | Con.Phase 05 | 2026-04-28 | 2026-06-24 | 28-Apr-26 A | 2026-07-01 | 87.23% | 90% | 225 | No
MS.CO.P1.FO.123 | Formwork for Foundations | 8 | Completed | Con.Phase 01 | 2026-05-07 | 2026-05-16 | 05-May-26 A | 19-May-26 A | 100% | 100% |  | No
MS.EN.P4.ALL.157 | trimming for CMC (up to bottom level of drop panel) | 31 | In Progress | Con.Phase 04 | 2026-05-14 | 2026-06-22 | 10-May-26 A | 2026-06-29 | 87.1% | 95% | 8 | No
MS.CO.P1.FO.110 | Foundations Concrete Pouring | 28 | Completed | Con.Phase 01 | 2026-05-10 | 2026-06-14 | 12-May-26 A | 12-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.120 | Foundations Concrete Pouring | 16 | Completed | Con.Phase 01 | 2026-05-24 | 2026-06-14 | 14-May-26 A | 15-Jun-26 A | 100% | 100% |  | No
MS.CO.P5.FO.105 | Rebars for 1st layer for Foundation | 27 | In Progress | Con.Phase 05 | 2026-05-25 | 2026-06-28 | 18-May-26 A | 2026-07-05 | 66.67% | 80% | 25 | No
MS.CO.P3(1).FO.117 | Foundations Concrete Pouring | 6 | Completed | Con.Phase 03 | 2026-06-10 | 2026-06-16 | 19-May-26 A | 13-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.115 | Foundations Concrete Pouring | 3 | Completed | Con.Phase 01 | 2026-05-21 | 2026-05-24 | 20-May-26 A | 31-May-26 A | 100% | 100% |  | No
MS.CO.P3(1).FO.120 | Foundations Concrete Pouring | 17 | Completed | Con.Phase 03 | 2026-05-23 | 2026-06-14 | 20-May-26 A | 16-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.125 | Foundations Concrete Pouring | 18 | In Progress | Con.Phase 01 | 2026-05-21 | 2026-06-14 | 24-May-26 A | 2026-06-21 | 100% | 95% | 4 | No
A1070 | Post-Grouting Verification Test | 5 | Completed | Con.Phase 02 | 2026-06-06 | 2026-06-10 | 31-May-26 A | 09-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.B2.100 | B2 - Columns Steel Fix | 10 | In Progress | Con.Phase 01 | 2026-06-07 | 2026-06-17 | 01-Jun-26 A | 2026-06-24 | 100% | 50% | 1 | No
MS.CO.P2.FO.320 | Excavation for drop Panels and Trenches | 13 | In Progress | Con.Phase 02 | 2026-06-01 | 2026-06-15 | 01-Jun-26 A | 2026-06-22 | 100% | 90% | 233 | No
MS.CO.P1.FO.126 | Rebars for 1st layer for Foundation | 8 | In Progress | Con.Phase 01 | 2026-06-11 | 2026-06-20 | 08-Jun-26 A | 2026-06-24 | 75% | 40% | 0 | No
MS.CO.P3(1).FO.115 | Foundations Concrete Pouring | 10 | Completed | Con.Phase 03 | 2026-06-01 | 2026-06-11 | 09-Jun-26 A | 09-Jun-26 A | 100% | 100% |  | No
MS.CO.P1.FO.127 | Installation for Mechanical and Electrical Embeds | 4 | In Progress | Con.Phase 01 | 2026-06-23 | 2026-06-27 | 10-Jun-26 A | 2026-06-28 | 0% | 40% | 0 | No
MS.CO.P1.B2.101 | B2 - Columns Formwork | 12 | In Progress | Con.Phase 01 | 2026-06-11 | 2026-06-24 | 11-Jun-26 A | 2026-06-29 | 50% | 10% | 2 | No
MS.CO.P2.FO.100 | Excavation for drop Panels and Trenches | 5 | In Progress | Con.Phase 02 | 2026-06-16 | 2026-06-21 | 11-Jun-26 A | 2026-06-23 | 40% | 60% | 0 | Yes
MS.CO.P1.B2.103 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 2026-06-11 | 2026-06-24 | 13-Jun-26 A | 2026-06-24 | 50% | 30% | 1 | No
MS.CO.P1.B2.106 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 2026-06-15 | 2026-06-28 | 14-Jun-26 A | 2026-07-01 | 25% | 25% | 0 | Yes
A1310 | Remaining Post-Grouting Verification Test | 5 | Completed |  | 2026-06-23 | 2026-06-28 | 14-Jun-26 A | 16-Jun-26 A | 0% | 100% |  | No
MS.CO.P1.B2.113 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 15-Jun-26 A | 2026-07-01 | 0% | 20% | 7 | No
MS.CO.P5.FO.118 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | In Progress | Con.Phase 05 | 2026-07-02 | 2026-07-12 | 15-Jun-26 A | 2026-06-28 | 0% | 30% | 14 | No
MS.CO.P5.FO.109 | Installation for Mechanical and Electrical Embeds | 6 | In Progress | Con.Phase 05 | 2026-06-29 | 2026-07-05 | 15-Jun-26 A | 2026-06-24 | 0% | 50% | 14 | No
MS.CO.P3(1).B2.100 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 03 | 2026-06-29 | 2026-07-12 | 15-Jun-26 A | 2026-06-29 | 0% | 20% | 13 | No
MS.CO.P3(2).FO.124 | Installation for Mechanical and Electrical Embeds | 6 | In Progress | Con.Phase 03 | 2026-06-16 | 2026-06-22 | 15-Jun-26 A | 2026-06-29 | 33.33% | 30% | 28 | No
MS.CO.P3(1).B2.101 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 03 | 2026-06-29 | 2026-07-12 | 16-Jun-26 A | 2026-06-30 | 0% | 10% | 14 | No
MS.CO.P1.B2.145 | B2 - Walls Steel Fix | 12 | In Progress | Con.Phase 01 | 2026-06-15 | 2026-06-28 | 16-Jun-26 A | 2026-06-30 | 25% | 10% | 2 | No
MS.CO.P2.FO.330 | Blinding concrete for lower Part of Foundation | 3 | In Progress | Con.Phase 02 | 2026-06-21 | 2026-06-23 | 16-Jun-26 A | 2026-06-21 | 0% | 30% | 2 | No
MS.CO.P1.FO.540 | Earthing and Lightning Protection System | 4 | In Progress | Con.Phase 02 | 2026-06-16 | 2026-06-20 | 16-Jun-26 A | 2026-06-21 | 50% | 40% | 3 | No
MS.CO.P1.B2.104 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-15 | 2026-06-28 | 2026-06-18 | 2026-07-01 | 25% | 0% | 1 | No
MS.CO.P1.B2.175 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-11 | 2026-06-24 | 2026-06-18 | 2026-07-01 | 50% | 0% | 3 | No
MS.CO.P1.B2.205 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-15 | 2026-06-28 | 2026-06-18 | 2026-07-01 | 25% | 0% | 4 | No
MS.CO.P3(1).B2.200 | B2 - Walls Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-06-17 | 2026-06-24 | 2026-06-18 | 2026-06-25 | 14.29% | 0% | 1 | No
MS.EN.P4.ALL.177 | Perform Geophysical Activity | 4 | Not Started |  | 2026-06-11 | 2026-06-15 | 2026-06-18 | 2026-06-22 | 100% | 0% | -1 | Yes
MS.CO.P5.FO.114 | Formwork for Foundations | 6 | Not Started | Con.Phase 05 | 2026-06-30 | 2026-07-06 | 2026-06-20 | 2026-06-25 | 0% | 0% | 16 | No
MS.CO.P1.B2.116 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-21 | 2026-07-04 | 2026-06-21 | 2026-07-04 | 0% | 0% | 7 | No
MS.CO.P3(1).B2.103 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-07-04 | 2026-07-16 | 2026-06-21 | 2026-07-04 | 0% | 0% | 13 | No
MS.CO.P1.B2.107 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 2026-06-22 | 2026-07-05 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.104 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-07-04 | 2026-07-16 | 2026-06-22 | 2026-07-05 | 0% | 0% | 14 | No
MS.CO.P1.B2.155 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-20 | 2026-07-02 | 2026-06-22 | 2026-07-05 | 0% | 0% | 2 | No
MS.CO.P2.FO.340 | Block work for Drop Panels | 1 | Not Started | Con.Phase 02 | 2026-06-24 | 2026-06-24 | 2026-06-22 | 2026-06-22 | 0% | 0% | 2 | No
MS.CO.P1.B2.185 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-16 | 2026-06-29 | 2026-06-23 | 2026-07-06 | 16.67% | 0% | 3 | No
MS.CO.P1.B2.215 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-20 | 2026-07-02 | 2026-06-23 | 2026-07-06 | 0% | 0% | 4 | No
MS.CO.P3(1).B2.203 | B2 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-06-22 | 2026-06-29 | 2026-06-23 | 2026-06-30 | 0% | 0% | 1 | No
MS.CO.P2.FO.350 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 02 | 2026-06-25 | 2026-06-25 | 2026-06-23 | 2026-06-23 | 0% | 0% | 2 | No
MS.EN.P4.ALL.187 | Soil Improvement | 16 | Not Started |  | 2026-06-16 | 2026-07-04 | 2026-06-23 | 2026-07-11 | 12.5% | 0% | -1 | Yes
A1570 | Dewatering system | 18 | Not Started |  | 2026-06-16 | 2026-07-06 | 2026-06-23 | 2026-07-13 | 11.11% | 0% | 15 | No
MS.CO.P3(2).FO.126 | Formwork for Foundations | 6 | Not Started | Con.Phase 03 | 2026-06-17 | 2026-06-23 | 2026-06-24 | 2026-06-30 | 16.67% | 0% | 30 | No
MS.CO.P1.FO.250 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 02 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-06-27 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.140 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 02 | 2026-06-22 | 2026-06-29 | 2026-06-24 | 2026-07-01 | 0% | 0% | 2 | No
MS.CO.P2.FO.360 | Surface preparation and Angle filet at RW Edge | 4 | Not Started | Con.Phase 02 | 2026-06-27 | 2026-06-30 | 2026-06-24 | 2026-06-28 | 0% | 0% | 2 | No
MS.CO.P3(1).B2.107 | B2 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-07-08 | 2026-07-21 | 2026-06-25 | 2026-07-08 | 0% | 0% | 13 | No
MS.CO.P1.B2.235 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 2026-06-25 | 2026-07-08 | 0% | 0% | 1 | No
MS.CO.P1.FO.128 | Formwork for Foundations | 5 | Not Started | Con.Phase 01 | 2026-06-27 | 2026-07-01 | 2026-06-27 | 2026-07-01 | 0% | 0% | 0 | No
MS.CO.P1.FO.129 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 5 | Not Started | Con.Phase 01 | 2026-06-27 | 2026-07-01 | 2026-06-27 | 2026-07-01 | 0% | 0% | 0 | No
MS.CO.P3(1).B2.108 | B2 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-07-08 | 2026-07-21 | 2026-06-27 | 2026-07-09 | 0% | 0% | 14 | No
MS.CO.P3(2).FO.128 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6 | Not Started | Con.Phase 03 | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-07-02 | 0% | 0% | 28 | No
MS.CO.P2.FO.101 | Blinding concrete for lower Part of Foundation | 3 | Not Started | Con.Phase 02 | 2026-06-25 | 2026-06-28 | 2026-06-28 | 2026-06-30 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.207 | B2 - Walls Concreting work | 7 | Not Started | Con.Phase 03 | 2026-06-27 | 2026-07-04 | 2026-06-28 | 2026-07-05 | 0% | 0% | 1 | No
MS.CO.F4.FO.100 | Backfilling Including Drop Panels and Trenches | 9 | Not Started | Con.Phase 04 | 2026-06-25 | 2026-07-05 | 2026-06-29 | 2026-07-08 | 0% | 0% | -1 | Yes
MS.CO.P5.FO.124 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 05 | 2026-07-13 | 2026-07-14 | 2026-06-29 | 2026-06-30 | 0% | 0% | 14 | No
MS.EN.P5.ALL.106 | Perform Geophysical Activity | 0 | Not Started | Con.Phase 05 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 0% | 0% | 0 | Yes
MS.EN.P5.ALL.107 | Report preparation and Soil Improvement Proposal | 1 | Not Started | Con.Phase 05 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.370 | Water Proofing Membrane under Raft Foundation | 6 | Not Started | Con.Phase 02 | 2026-07-01 | 2026-07-07 | 2026-06-29 | 2026-07-05 | 0% | 0% | 2 | No
MS.CO.P1.B2.102 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 01 | 2026-06-25 | 2026-07-01 | 2026-06-30 | 2026-07-06 | 0% | 0% | 2 | No
MS.CO.P3(1).B2.102 | B2 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-06-29 | 2026-07-12 | 2026-06-30 | 2026-07-13 | 0% | 0% | 11 | No
MS.EN.P5.ALL.110 | Soil Improvement (By Other) | 6 | Not Started | Con.Phase 05 | 2026-06-30 | 2026-07-06 | 2026-06-30 | 2026-07-06 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.245 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-23 | 2026-07-06 | 2026-06-30 | 2026-07-13 | 0% | 0% | 1 | No
MS.CO.P3(1).B2.201 | B2 - Walls Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-06-29 | 2026-07-06 | 2026-06-30 | 2026-07-07 | 0% | 0% | 2 | No
MS.CO.P3(1).B2.202 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-06-29 | 2026-07-12 | 2026-06-30 | 2026-07-13 | 0% | 0% | 8 | No
MS.EN.P4.ALL.167 | Remaining CMC | 6 | Not Started |  | 2026-06-23 | 2026-06-29 | 2026-06-30 | 2026-07-06 | 0% | 0% | 6 | No
MS.CO.P2.FO.102 | Block work for Drop Panels | 2 | Not Started | Con.Phase 02 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.130 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 01 | 2026-07-02 | 2026-07-04 | 2026-07-02 | 2026-07-04 | 0% | 0% | 0 | No
MS.CO.P1.B2.105 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 01 | 2026-06-29 | 2026-07-05 | 2026-07-02 | 2026-07-08 | 0% | 0% | 1 | No
MS.CO.P1.FO.480 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 02 | 2026-06-30 | 2026-07-02 | 2026-07-02 | 2026-07-05 | 0% | 0% | 2 | No
MS.CO.P2.FO.200 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 02 | 2026-06-30 | 2026-07-07 | 2026-07-02 | 2026-07-09 | 0% | 0% | 2 | No
MS.CO.P2.FO.103 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 02 | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-05 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.129 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 03 | 2026-06-27 | 2026-06-27 | 2026-07-04 | 2026-07-04 | 0% | 0% | 28 | No
MS.CO.P1.B2.118 | B2 - Columns Concreting work | 5 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-09 | 2026-07-05 | 2026-07-09 | 0% | 0% | 7 | No
MS.CO.P1.B2.119 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-11 | 2026-07-05 | 2026-07-11 | 0% | 0% | 0 | No
MS.CO.P3(1).B2.105 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-07-04 | 2026-07-16 | 2026-07-05 | 2026-07-18 | 0% | 0% | 11 | No
MS.CO.P1.B2.265 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-11 | 2026-07-05 | 2026-07-11 | 0% | 0% | 7 | No
MS.CO.P1.B2.109 | B2 - Columns Concreting work | 5 | Not Started | Con.Phase 01 | 2026-07-02 | 2026-07-07 | 2026-07-06 | 2026-07-11 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.104 | Surface preparation and Angle filet at RW Edge | 4 | Not Started | Con.Phase 02 | 2026-07-04 | 2026-07-07 | 2026-07-06 | 2026-07-09 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.100 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-07-15 | 2026-07-21 | 2026-07-06 | 2026-07-12 | 0% | 0% | 10 | No
MS.CO.P1.B2.165 | B2 - Walls Concreting work | 3 | Not Started | Con.Phase 01 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 0% | 0% | 2 | No
MS.CO.P2.FO.150 | Blinding concrete for lower Part of Foundation | 3 | Not Started | Con.Phase 02 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 0% | 0% | 2 | No
MS.CO.P5.FO.165 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 05 | 2026-07-06 | 2026-07-13 | 2026-07-06 | 2026-07-13 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.200 | Walls Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-07-15 | 2026-07-21 | 2026-07-06 | 2026-07-12 | 0% | 0% | 10 | No
MS.CO.P3(1).B2.204 | B2 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-07-05 | 2026-07-12 | 2026-07-06 | 2026-07-13 | 0% | 0% | 1 | No
A1060 | Post-Grouting Verification Test | 3 | Not Started | Con.Phase 05 | 2026-07-07 | 2026-07-09 | 2026-07-07 | 2026-07-09 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.195 | B2 - Walls Concreting work | 8 | Not Started | Con.Phase 01 | 2026-06-30 | 2026-07-08 | 2026-07-07 | 2026-07-15 | 0% | 0% | 3 | No
MS.CO.P1.B2.225 | B2 - Walls Concreting work | 8 | Not Started | Con.Phase 01 | 2026-07-04 | 2026-07-12 | 2026-07-07 | 2026-07-15 | 0% | 0% | 4 | No
MS.CO.P1.B2.122 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 01 | 2026-07-08 | 2026-07-14 | 2026-07-08 | 2026-07-14 | 0% | 0% | 0 | No
MS.CO.P2.FO.118 | Rebars for 1st layer for Foundation | 8 | Not Started | Con.Phase 02 | 2026-07-08 | 2026-07-16 | 2026-07-08 | 2026-07-16 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.105 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 05 | 2026-07-18 | 2026-07-23 | 2026-07-08 | 2026-07-14 | 0% | 0% | 10 | No
MS.CO.P5.B2.205 | Walls Formwork | 6 | Not Started | Con.Phase 05 | 2026-07-18 | 2026-07-23 | 2026-07-08 | 2026-07-14 | 0% | 0% | 10 | No
MS.CO.P1.B2.112 | B2 - Beams and Slab Formwork | 12 | Not Started | Con.Phase 01 | 2026-07-06 | 2026-07-19 | 2026-07-09 | 2026-07-22 | 0% | 0% | 1 | No
MS.CO.P3(1).B2.109 | B2 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-07-08 | 2026-07-21 | 2026-07-09 | 2026-07-22 | 0% | 0% | 11 | No
MS.CO.P1.FO.240 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 04 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-12 | 0% | 0% | -1 | Yes
MS.CO.P1.B2.275 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 01 | 2026-07-09 | 2026-07-15 | 2026-07-09 | 2026-07-15 | 0% | 0% | 7 | No
MS.CO.P2.FO.160 | Block work for Drop Panels | 2 | Not Started | Con.Phase 02 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 0% | 0% | 2 | No
MS.CO.F4.FO.130 | Backfilling Including Drop Panels and Trenches | 8 | Not Started | Con.Phase 04 | 2026-07-06 | 2026-07-14 | 2026-07-09 | 2026-07-18 | 0% | 0% | 1 | No
MS.CO.P2.FO.105 | Water Proofing Membrane under Raft Foundation | 6 | Not Started | Con.Phase 02 | 2026-07-08 | 2026-07-14 | 2026-07-11 | 2026-07-16 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.490 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 02 | 2026-07-08 | 2026-07-11 | 2026-07-11 | 2026-07-13 | 0% | 0% | 2 | No
MS.CO.P3(1).B2.208 | B2 - Walls Concreting work | 7 | Not Started | Con.Phase 03 | 2026-07-09 | 2026-07-16 | 2026-07-11 | 2026-07-18 | 0% | 0% | 1 | No
MS.CO.P1.B2.108 | B2 - Beams and Slab Formwork | 12 | Not Started | Con.Phase 01 | 2026-07-07 | 2026-07-20 | 2026-07-12 | 2026-07-25 | 0% | 0% | -2 | Yes
MS.CO.P1.B2.117 | B2 - Beams and Slab Formwork | 12 | Not Started | Con.Phase 01 | 2026-07-09 | 2026-07-22 | 2026-07-12 | 2026-07-25 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.115 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 03 | 2026-07-12 | 2026-07-25 | 2026-07-12 | 2026-07-25 | 0% | 0% | 2 | No
MS.CO.P3(1).B2.116 | Beams and Slab Formwork | 13 | Not Started | Con.Phase 03 | 2026-07-12 | 2026-07-26 | 2026-07-12 | 2026-07-26 | 0% | 0% | 4 | No
MS.CO.P2.FO.170 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 02 | 2026-07-09 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 0% | 0% | 2 | No
MS.CO.F4.FO.112 | Blinding concrete for lower Part of Foundation | 4 | Not Started | Con.Phase 04 | 2026-07-09 | 2026-07-13 | 2026-07-13 | 2026-07-16 | 0% | 0% | -1 | Yes
MS.CO.P1.B2.125 | B2 - Beams and Slab Formwork | 12 | Not Started | Con.Phase 01 | 2026-07-13 | 2026-07-26 | 2026-07-14 | 2026-07-27 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.124 | Installation for Mechanical and Electrical Embeds | 10 | Not Started | Con.Phase 02 | 2026-07-13 | 2026-07-23 | 2026-07-14 | 2026-07-25 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.110 | B2 - Columns Concreting work | 3 | Not Started | Con.Phase 05 | 2026-07-23 | 2026-07-26 | 2026-07-14 | 2026-07-16 | 0% | 0% | 10 | No
MS.CO.P3(2).B2.100 | B2 - Columns Steel Fix | 15 | Not Started | Con.Phase 03 | 2026-07-13 | 2026-07-29 | 2026-07-14 | 2026-07-30 | 0% | 0% | 20 | No
MS.CO.P1.B2.255 | B2 - Walls Concreting work | 8 | Not Started | Con.Phase 01 | 2026-07-07 | 2026-07-15 | 2026-07-14 | 2026-07-22 | 0% | 0% | 1 | No
MS.CO.P2.FO.180 | Surface preparation and Angle filet at RW Edge | 5 | Not Started | Con.Phase 02 | 2026-07-12 | 2026-07-16 | 2026-07-14 | 2026-07-19 | 0% | 0% | 2 | No
MS.CO.P2.FO.210 | Blinding concrete for lower Part of Foundation | 3 | Not Started | Con.Phase 02 | 2026-07-12 | 2026-07-14 | 2026-07-14 | 2026-07-16 | 0% | 0% | 2 | No
MS.CO.P1.FO.530 | Earthing and Lightning Protection System | 2 | Not Started | Con.Phase 05 | 2026-07-14 | 2026-07-15 | 2026-07-14 | 2026-07-15 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.210 | Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-07-23 | 2026-07-26 | 2026-07-14 | 2026-07-16 | 0% | 0% | 10 | No
MS.CO.P3(2).B2.200 | B2 - Walls Steel Fix | 15 | Not Started | Con.Phase 03 | 2026-07-13 | 2026-07-29 | 2026-07-14 | 2026-07-30 | 0% | 0% | 20 | No
MS.CO.P1.B2.123 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 01 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 0% | 0% | 0 | No
MS.CO.P5.B2.115 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 05 | 2026-07-25 | 2026-08-06 | 2026-07-15 | 2026-07-28 | 0% | 0% | 10 | No
MS.CO.P1.B2.129 | B2 - Beams and Slab Formwork | 12 | Not Started | Con.Phase 01 | 2026-07-16 | 2026-07-29 | 2026-07-16 | 2026-07-29 | 0% | 0% | 0 | No
MS.CO.P2.FO.126 | Formwork for Foundations | 10 | Not Started | Con.Phase 02 | 2026-07-15 | 2026-07-26 | 2026-07-16 | 2026-07-27 | 0% | 0% | 7 | No
MS.CO.P3(2).B2.103 | B2 - Columns Formwork | 15 | Not Started | Con.Phase 03 | 2026-07-15 | 2026-08-01 | 2026-07-16 | 2026-08-02 | 0% | 0% | 20 | No
MS.CO.P1.B2.285 | B2 - Walls Concreting work | 3 | Not Started | Con.Phase 01 | 2026-07-16 | 2026-07-19 | 2026-07-16 | 2026-07-19 | 0% | 0% | 7 | No
MS.CO.P5.FO.135 | Blinding concrete for lower Part of Foundation | 2 | Not Started | Con.Phase 05 | 2026-07-16 | 2026-07-18 | 2026-07-16 | 2026-07-18 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.203 | B2 - Walls Formwork | 15 | Not Started | Con.Phase 03 | 2026-07-15 | 2026-08-01 | 2026-07-16 | 2026-08-02 | 0% | 0% | 20 | No
MS.CO.P2.FO.106 | Rebars for 1st layer for Foundation | 10 | Not Started | Con.Phase 02 | 2026-07-18 | 2026-07-28 | 2026-07-18 | 2026-07-28 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.115 | Block work for Drop Panels | 3 | Not Started | Con.Phase 04 | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 0% | 0% | -1 | Yes
MS.CO.P2.FO.220 | Block work for Drop Panels | 2 | Not Started | Con.Phase 02 | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-19 | 0% | 0% | 2 | No
MS.CO.P3(2).B2.108 | B2 - Columns Concreting work | 15 | Not Started | Con.Phase 03 | 2026-07-18 | 2026-08-03 | 2026-07-19 | 2026-08-04 | 0% | 0% | 20 | No
MS.CO.P5.FO.155 | Block work for Drop Panels | 1 | Not Started | Con.Phase 05 | 2026-07-19 | 2026-07-19 | 2026-07-19 | 2026-07-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.205 | B2 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-07-18 | 2026-07-25 | 2026-07-19 | 2026-07-26 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.208 | B2 - Walls Concreting work | 15 | Not Started | Con.Phase 03 | 2026-07-18 | 2026-08-03 | 2026-07-19 | 2026-08-04 | 0% | 0% | 20 | No
MS.CO.P1.FO.580 | Earthing and Lightning Protection System | 4 | Not Started | Con.Phase 04 | 2026-07-15 | 2026-07-19 | 2026-07-19 | 2026-07-22 | 0% | 0% | 1 | No
MS.CO.F4.FO.180 | Backfilling Including Drop Panels and Trenches | 10 | Not Started | Con.Phase 04 | 2026-07-15 | 2026-07-26 | 2026-07-19 | 2026-07-29 | 0% | 0% | 1 | No
MS.CO.P1.B2.114 | B2 - Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 01 | 2026-07-16 | 2026-07-27 | 2026-07-20 | 2026-07-30 | 0% | 0% | 1 | No
MS.CO.P2.FO.190 | Water Proofing Membrane under Raft Foundation | 6 | Not Started | Con.Phase 02 | 2026-07-18 | 2026-07-23 | 2026-07-20 | 2026-07-26 | 0% | 0% | 2 | No
MS.CO.P2.FO.230 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 02 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 0% | 0% | 2 | No
MS.CO.P5.FO.145 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 05 | 2026-07-20 | 2026-07-21 | 2026-07-20 | 2026-07-21 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.117 | Blinding concrete for Upper Part | 4 | Not Started | Con.Phase 04 | 2026-07-18 | 2026-07-21 | 2026-07-21 | 2026-07-25 | 0% | 0% | -1 | Yes
MS.CO.P1.B2.110 | B2 - Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 01 | 2026-07-18 | 2026-07-28 | 2026-07-22 | 2026-08-02 | 0% | 0% | -2 | Yes
MS.CO.P2.FO.240 | Surface preparation and Angle filet at RW Edge | 5 | Not Started | Con.Phase 02 | 2026-07-20 | 2026-07-25 | 2026-07-22 | 2026-07-27 | 0% | 0% | 2 | No
MS.CO.P5.FO.175 | Water Proofing Membrane under Raft Foundation | 8 | Not Started | Con.Phase 05 | 2026-07-22 | 2026-07-30 | 2026-07-22 | 2026-07-30 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.209 | B2 - Walls Concreting work | 7 | Not Started | Con.Phase 03 | 2026-07-22 | 2026-07-29 | 2026-07-23 | 2026-07-30 | 0% | 0% | 1 | No
MS.CO.F4.FO.140 | Blinding concrete for lower Part of Foundation | 4 | Not Started | Con.Phase 04 | 2026-07-20 | 2026-07-23 | 2026-07-23 | 2026-07-27 | 0% | 0% | 1 | No
MS.CO.F4.FO.120 | Water Proofing Membrane under Raft Foundation | 13 | Not Started | Con.Phase 04 | 2026-07-22 | 2026-08-05 | 2026-07-26 | 2026-08-09 | 0% | 0% | -1 | Yes
MS.CO.P1.B2.120 | B2 - Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 01 | 2026-07-23 | 2026-08-03 | 2026-07-26 | 2026-08-05 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.128 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 8 | Not Started | Con.Phase 02 | 2026-07-26 | 2026-08-03 | 2026-07-27 | 2026-08-04 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.107 | Installation for Mechanical and Electrical Embeds | 6 | Not Started | Con.Phase 02 | 2026-07-27 | 2026-08-02 | 2026-07-27 | 2026-08-02 | 0% | 0% | 4 | No
MS.CO.P3(1).B2.117 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 03 | 2026-07-26 | 2026-08-05 | 2026-07-27 | 2026-08-06 | 0% | 0% | 1 | No
MS.CO.P1.B2.127 | B2 - Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 01 | 2026-07-27 | 2026-08-06 | 2026-07-28 | 2026-08-08 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.108 | Formwork for Foundations | 6 | Not Started | Con.Phase 02 | 2026-07-28 | 2026-08-03 | 2026-07-28 | 2026-08-03 | 0% | 0% | 4 | No
MS.CO.P3(1).B2.118 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-07-26 | 2026-08-05 | 2026-07-28 | 2026-08-08 | 0% | 0% | 0 | No
MS.CO.P2.FO.250 | Water Proofing Membrane under Raft Foundation | 6 | Not Started | Con.Phase 02 | 2026-07-26 | 2026-08-01 | 2026-07-28 | 2026-08-03 | 0% | 0% | 2 | No
MS.CO.F4.FO.150 | Block work for Drop Panels | 4 | Not Started | Con.Phase 04 | 2026-07-25 | 2026-07-28 | 2026-07-28 | 2026-08-01 | 0% | 0% | 1 | No
MS.CO.P2.FO.110 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6 | Not Started | Con.Phase 02 | 2026-07-29 | 2026-08-04 | 2026-07-29 | 2026-08-04 | 0% | 0% | 4 | No
MS.CO.P2.FO.109 | Rebars for 1st layer for Foundation | 7 | Not Started | Con.Phase 02 | 2026-07-29 | 2026-08-05 | 2026-07-29 | 2026-08-05 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.120 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 05 | 2026-08-08 | 2026-08-18 | 2026-07-29 | 2026-08-09 | 0% | 0% | 10 | No
MS.CO.P1.B2.131 | B2 - Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 01 | 2026-07-30 | 2026-08-08 | 2026-07-30 | 2026-08-08 | 0% | 0% | 0 | No
MS.CO.P3(1).B2.119 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-07-27 | 2026-08-06 | 2026-07-30 | 2026-08-10 | 0% | 0% | 1 | No
MS.CO.P1.B2.115 | B2 - Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-07-28 | 2026-07-28 | 2026-08-01 | 2026-08-01 | 0% | 0% | 1 | No
MS.CO.P5.FO.106 | Rebars for 1st layer for Foundation | 9 | Not Started | Con.Phase 05 | 2026-08-01 | 2026-08-10 | 2026-08-01 | 2026-08-10 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.102 | B1 - Columns Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-07-29 | 2026-08-05 | 2026-08-02 | 2026-08-09 | 0% | 0% | 12 | No
MS.CO.P1.B1.202 | B1 - Walls Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-07-29 | 2026-08-05 | 2026-08-02 | 2026-08-09 | 0% | 0% | 12 | No
MS.CO.F4.FO.160 | Blinding concrete for Upper Part | 4 | Not Started | Con.Phase 04 | 2026-07-29 | 2026-08-02 | 2026-08-02 | 2026-08-05 | 0% | 0% | 1 | No
MS.CO.P1.B2.111 | B2 - Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-07-29 | 2026-07-29 | 2026-08-03 | 2026-08-03 | 0% | 0% | -2 | Yes
MS.CO.P2.FO.111 | Installation for Mechanical and Electrical Embeds | 7 | Not Started | Con.Phase 02 | 2026-08-03 | 2026-08-10 | 2026-08-03 | 2026-08-10 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.100 | B1 - Columns Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-07-30 | 2026-08-06 | 2026-08-04 | 2026-08-11 | 0% | 0% | 10 | No
MS.CO.P5.FO.110 | Installation for Mechanical and Electrical Embeds | 9 | Not Started | Con.Phase 05 | 2026-08-04 | 2026-08-13 | 2026-08-04 | 2026-08-13 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.200 | B1 - Walls Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-07-30 | 2026-08-06 | 2026-08-04 | 2026-08-11 | 0% | 0% | 10 | No
MS.CO.P2.FO.130 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 02 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.113 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 02 | 2026-08-05 | 2026-08-06 | 2026-08-05 | 2026-08-06 | 0% | 0% | 4 | No
MS.CO.P5.FO.115 | Formwork for Foundations | 9 | Not Started | Con.Phase 05 | 2026-08-05 | 2026-08-15 | 2026-08-05 | 2026-08-15 | 0% | 0% | 2 | No
MS.CO.P1.B2.121 | B2 - Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-08-04 | 2026-08-04 | 2026-08-06 | 2026-08-06 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.104 | B1 - Columns Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-03 | 2026-08-10 | 2026-08-06 | 2026-08-13 | 0% | 0% | 12 | No
MS.CO.P2.FO.115 | Rebars for 1st layer for Foundation | 7 | Not Started | Con.Phase 02 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.204 | B1 - Walls Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-03 | 2026-08-10 | 2026-08-06 | 2026-08-13 | 0% | 0% | 12 | No
MS.CO.F4.FO.170 | Water Proofing Membrane under Raft Foundation | 12 | Not Started | Con.Phase 04 | 2026-08-03 | 2026-08-16 | 2026-08-06 | 2026-08-19 | 0% | 0% | 1 | No
MS.CO.P1.B1.106 | B1 - Columns Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-08-05 | 2026-08-12 | 2026-08-08 | 2026-08-15 | 0% | 0% | 5 | No
MS.CO.P2.FO.114 | Formwork for Foundations | 4 | Not Started | Con.Phase 02 | 2026-08-08 | 2026-08-11 | 2026-08-08 | 2026-08-11 | 0% | 0% | 3 | No
MS.CO.P5.FO.119 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Not Started | Con.Phase 05 | 2026-08-08 | 2026-08-17 | 2026-08-08 | 2026-08-17 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.206 | B1 - Walls Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-08-05 | 2026-08-12 | 2026-08-08 | 2026-08-15 | 0% | 0% | 5 | No
MS.CO.P1.B2.128 | B2 - Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-08-08 | 2026-08-08 | 2026-08-09 | 2026-08-09 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.132 | B2 - Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 0% | 0% | 0 | No
MS.CO.P1.B1.101 | B1 - Columns Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-04 | 2026-08-11 | 2026-08-09 | 2026-08-16 | 0% | 0% | 10 | No
MS.CO.P2.B3.107 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-08 | 2026-08-13 | 2026-08-09 | 2026-08-15 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.100 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-09 | 2026-08-15 | 2026-08-09 | 2026-08-15 | 0% | 0% | 4 | No
MS.CO.P3(1).B2.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-08-06 | 2026-08-06 | 2026-08-09 | 2026-08-09 | 0% | 0% | 0 | No
MS.CO.P3(1).B2.120 | Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 03 | 2026-08-06 | 2026-08-15 | 2026-08-09 | 2026-08-17 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.201 | B1 - Walls Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-04 | 2026-08-11 | 2026-08-09 | 2026-08-16 | 0% | 0% | 10 | No
MS.CO.P2.B3.207 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-08 | 2026-08-13 | 2026-08-09 | 2026-08-15 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.200 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-09 | 2026-08-15 | 2026-08-09 | 2026-08-15 | 0% | 0% | 4 | No
MS.CO.P1.B1.113 | B1 - Columns Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-08-09 | 2026-08-16 | 2026-08-10 | 2026-08-17 | 0% | 0% | 11 | No
MS.CO.P1.B1.119 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-08-10 | 2026-08-16 | 2026-08-10 | 2026-08-16 | 0% | 0% | 12 | No
MS.CO.F4.FO.111 | Rebars for 1st layer for Foundation | 10 | Not Started | Con.Phase 04 | 2026-08-06 | 2026-08-17 | 2026-08-10 | 2026-08-20 | 0% | 0% | -1 | Yes
MS.CO.P5.B2.124 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-08-19 | 2026-08-19 | 2026-08-10 | 2026-08-10 | 0% | 0% | 10 | No
MS.CO.P3(1).B1.100 | B1 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-08 | 2026-08-20 | 2026-08-10 | 2026-08-23 | 0% | 0% | 13 | No
MS.CO.P1.B1.213 | B1 - Walls Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-08-09 | 2026-08-16 | 2026-08-10 | 2026-08-17 | 0% | 0% | 11 | No
MS.CO.P1.B1.219 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-08-10 | 2026-08-16 | 2026-08-10 | 2026-08-16 | 0% | 0% | 12 | No
MS.CO.P3(1).B1.200 | B1 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-08 | 2026-08-20 | 2026-08-10 | 2026-08-23 | 0% | 0% | 13 | No
MS.CO.P1.B1.105 | B1 - Columns Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-08 | 2026-08-15 | 2026-08-11 | 2026-08-18 | 0% | 0% | 12 | No
MS.CO.P2.FO.116 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 4 | Not Started | Con.Phase 02 | 2026-08-11 | 2026-08-15 | 2026-08-11 | 2026-08-15 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.100 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-08-20 | 2026-08-26 | 2026-08-11 | 2026-08-17 | 0% | 0% | 12 | No
MS.CO.P3(1).B2.123 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-08-08 | 2026-08-08 | 2026-08-11 | 2026-08-11 | 0% | 0% | 1 | No
MS.CO.P5.B1.200 | Walls Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-08-20 | 2026-08-26 | 2026-08-11 | 2026-08-17 | 0% | 0% | 10 | No
MS.CO.P1.B1.205 | B1 - Walls Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-08 | 2026-08-15 | 2026-08-11 | 2026-08-18 | 0% | 0% | 12 | No
MS.CO.P1.B1.107 | B1 - Columns Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-10 | 2026-08-17 | 2026-08-12 | 2026-08-19 | 0% | 0% | 5 | No
MS.CO.P2.B3.111 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-11 | 2026-08-17 | 2026-08-12 | 2026-08-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.101 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | 0% | 0% | 4 | No
MS.CO.P3(1).B1.101 | B1 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-09 | 2026-08-22 | 2026-08-12 | 2026-08-25 | 0% | 0% | 11 | No
MS.CO.P1.B1.207 | B1 - Walls Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-10 | 2026-08-17 | 2026-08-12 | 2026-08-19 | 0% | 0% | 5 | No
MS.CO.P2.B3.211 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-11 | 2026-08-17 | 2026-08-12 | 2026-08-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.201 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | 0% | 0% | 4 | No
MS.CO.P3(1).B1.201 | B1 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-09 | 2026-08-22 | 2026-08-12 | 2026-08-25 | 0% | 0% | 12 | No
MS.CO.P1.B1.103 | B1 - Columns Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-09 | 2026-08-16 | 2026-08-13 | 2026-08-20 | 0% | 0% | 10 | No
MS.CO.P5.B1.105 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 05 | 2026-08-23 | 2026-08-29 | 2026-08-13 | 2026-08-19 | 0% | 0% | 12 | No
MS.CO.P1.B1.203 | B1 - Walls Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-09 | 2026-08-16 | 2026-08-13 | 2026-08-20 | 0% | 0% | 10 | No
MS.CO.P1.B1.116 | B1 - Columns Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-13 | 2026-08-20 | 2026-08-15 | 2026-08-22 | 0% | 0% | 11 | No
MS.CO.P1.B1.122 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 01 | 2026-08-15 | 2026-08-20 | 2026-08-15 | 2026-08-20 | 0% | 0% | 12 | No
MS.CO.P3(1).B1.103 | B1 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-12 | 2026-08-25 | 2026-08-15 | 2026-08-27 | 0% | 0% | 13 | No
MS.CO.P1.B1.216 | B1 - Walls Formwork | 7 | Not Started | Con.Phase 01 | 2026-08-13 | 2026-08-20 | 2026-08-15 | 2026-08-22 | 0% | 0% | 11 | No
MS.CO.P1.B1.222 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 01 | 2026-08-15 | 2026-08-20 | 2026-08-15 | 2026-08-20 | 0% | 0% | 12 | No
MS.CO.P3(1).B1.203 | B1 - Walls Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-12 | 2026-08-25 | 2026-08-15 | 2026-08-27 | 0% | 0% | 13 | No
MS.CO.P2.FO.121 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 02 | 2026-08-16 | 2026-08-17 | 2026-08-16 | 2026-08-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.114 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-15 | 2026-08-20 | 2026-08-16 | 2026-08-22 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.103 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-16 | 2026-08-22 | 2026-08-16 | 2026-08-22 | 0% | 0% | 4 | No
MS.CO.P5.B1.205 | Walls Formwork | 6 | Not Started | Con.Phase 05 | 2026-08-25 | 2026-08-31 | 2026-08-16 | 2026-08-22 | 0% | 0% | 10 | No
MS.CO.P2.B3.214 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-15 | 2026-08-20 | 2026-08-16 | 2026-08-22 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.203 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-16 | 2026-08-22 | 2026-08-16 | 2026-08-22 | 0% | 0% | 4 | No
MS.CO.P1.B1.109 | B1 - Columns Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-15 | 2026-08-22 | 2026-08-17 | 2026-08-24 | 0% | 0% | 5 | No
MS.CO.P2.FO.119 | Installation for Mechanical and Electrical Embeds | 6 | Not Started | Con.Phase 02 | 2026-08-17 | 2026-08-23 | 2026-08-17 | 2026-08-23 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.122 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-08-16 | 2026-08-26 | 2026-08-17 | 2026-08-27 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.115 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-08-17 | 2026-08-27 | 2026-08-17 | 2026-08-27 | 0% | 0% | 4 | No
MS.CO.P3(1).B1.104 | B1 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-13 | 2026-08-26 | 2026-08-17 | 2026-08-30 | 0% | 0% | 11 | No
MS.CO.P1.B1.209 | B1 - Walls Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-15 | 2026-08-22 | 2026-08-17 | 2026-08-24 | 0% | 0% | 5 | No
MS.CO.P3(1).B1.204 | B1 - Walls Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-13 | 2026-08-26 | 2026-08-17 | 2026-08-30 | 0% | 0% | 12 | No
MS.CO.P5.FO.125 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 05 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.110 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 05 | 2026-08-27 | 2026-09-02 | 2026-08-18 | 2026-08-24 | 0% | 0% | 12 | No
MS.CO.P3(1).B2.124 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-08-16 | 2026-08-16 | 2026-08-18 | 2026-08-18 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.118 | B2 - Columns Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-18 | 2026-08-25 | 2026-08-19 | 2026-08-26 | 0% | 0% | 11 | No
MS.CO.P1.B1.123 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 01 | 2026-08-19 | 2026-08-25 | 2026-08-19 | 2026-08-25 | 0% | 0% | 12 | No
MS.CO.P5.B2.101 | B2 - Columns Steel Fix | 4 | Not Started | Con.Phase 05 | 2026-08-19 | 2026-08-23 | 2026-08-19 | 2026-08-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.107 | B1 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-17 | 2026-08-30 | 2026-08-19 | 2026-09-01 | 0% | 0% | 13 | No
MS.CO.P3(1).B1.102 | B1 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-17 | 2026-08-30 | 2026-08-19 | 2026-09-01 | 0% | 0% | 13 | No
MS.CO.P3(2).B2.115 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 03 | 2026-08-17 | 2026-08-27 | 2026-08-19 | 2026-08-30 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.201 | Walls Steel Fix | 4 | Not Started | Con.Phase 05 | 2026-08-19 | 2026-08-23 | 2026-08-19 | 2026-08-23 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.218 | B2 - Walls Concreting work | 7 | Not Started | Con.Phase 01 | 2026-08-18 | 2026-08-25 | 2026-08-19 | 2026-08-26 | 0% | 0% | 11 | No
MS.CO.P1.B1.223 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 01 | 2026-08-19 | 2026-08-25 | 2026-08-19 | 2026-08-25 | 0% | 0% | 12 | No
MS.CO.P3(1).B1.207 | B1 - Walls Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-17 | 2026-08-30 | 2026-08-19 | 2026-09-01 | 0% | 0% | 13 | No
MS.CO.P3(1).B1.202 | B1 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-08-17 | 2026-08-30 | 2026-08-19 | 2026-09-01 | 0% | 0% | 13 | No
MS.CO.P2.FO.122 | Formwork for Foundations | 4 | Not Started | Con.Phase 02 | 2026-08-20 | 2026-08-24 | 2026-08-20 | 2026-08-24 | 0% | 0% | 3 | No
MS.CO.P2.B3.102 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-20 | 2026-08-26 | 2026-08-20 | 2026-08-26 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.106 | Rebars for 1st layer for Foundation | 10 | Not Started | Con.Phase 04 | 2026-08-17 | 2026-08-27 | 2026-08-20 | 2026-08-31 | 0% | 0% | 1 | No
MS.CO.P5.B1.210 | Walls Concreting work | 6 | Not Started | Con.Phase 05 | 2026-08-30 | 2026-09-05 | 2026-08-20 | 2026-08-26 | 0% | 0% | 10 | No
MS.CO.P2.B3.202 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-08-20 | 2026-08-26 | 2026-08-20 | 2026-08-26 | 0% | 0% | 1 | No
- | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | Not Started | Con.Phase 04 | 2026-08-18 | 2026-08-27 | 2026-08-22 | 2026-08-31 | 0% | 0% | -1 | Yes
MS.CO.F4.FO.113 | Installation for Mechanical and Electrical Embeds | 6 | Not Started | Con.Phase 04 | 2026-08-18 | 2026-08-24 | 2026-08-22 | 2026-08-27 | 0% | 0% | 2 | No
MS.CO.P5.B2.106 | B2 - Columns Formwork | 4 | Not Started | Con.Phase 05 | 2026-08-22 | 2026-08-25 | 2026-08-22 | 2026-08-25 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.108 | B1 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-18 | 2026-08-31 | 2026-08-22 | 2026-09-03 | 0% | 0% | 11 | No
MS.CO.P5.B2.206 | Walls Formwork | 4 | Not Started | Con.Phase 05 | 2026-08-22 | 2026-08-25 | 2026-08-22 | 2026-08-25 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.208 | B1 - Walls Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-18 | 2026-08-31 | 2026-08-22 | 2026-09-03 | 0% | 0% | 12 | No
MS.CO.P2.FO.125 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 4 | Not Started | Con.Phase 02 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.104 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-24 | 2026-08-30 | 2026-08-24 | 2026-08-30 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.115 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 05 | 2026-09-02 | 2026-09-15 | 2026-08-24 | 2026-09-06 | 0% | 0% | 10 | No
MS.CO.P3(1).B1.105 | B1 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-22 | 2026-09-03 | 2026-08-24 | 2026-09-06 | 0% | 0% | 13 | No
MS.CO.P2.B3.204 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-08-24 | 2026-08-30 | 2026-08-24 | 2026-08-30 | 0% | 0% | 1 | No
MS.CO.P3(1).B1.205 | B1 - Walls Formwork | 12 | Not Started | Con.Phase 03 | 2026-08-22 | 2026-09-03 | 2026-08-24 | 2026-09-06 | 0% | 0% | 13 | No
MS.CO.P1.B2.126 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-24 | 0% | 0% | 1 | No
MS.CO.P1.B1.112 | B2 - Beams and Slab Formwork | 10 | Not Started | Con.Phase 01 | 2026-08-22 | 2026-09-01 | 2026-08-25 | 2026-09-05 | 0% | 0% | 1 | No
MS.CO.P5.B2.111 | B2 - Columns Concreting work | 3 | Not Started | Con.Phase 05 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.211 | Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.114 | Formwork for Foundations | 5 | Not Started | Con.Phase 04 | 2026-08-23 | 2026-08-27 | 2026-08-26 | 2026-08-31 | 0% | 0% | -1 | Yes
MS.CO.P5.B2.116 | Beams and Slab Formwork | 7 | Not Started | Con.Phase 05 | 2026-08-26 | 2026-09-02 | 2026-08-26 | 2026-09-02 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.124 | B2 - DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-08-21 | 2026-08-22 | 2026-08-26 | 2026-08-27 | 0% | 0% | -2 | Yes
MS.CO.P2.B3.108 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-27 | 2026-09-02 | 2026-08-27 | 2026-09-02 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.107 | Installation for Mechanical and Electrical Embeds | 7 | Not Started | Con.Phase 04 | 2026-08-24 | 2026-08-31 | 2026-08-27 | 2026-09-03 | 0% | 0% | 2 | No
MS.CO.P2.B3.208 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-08-27 | 2026-09-02 | 2026-08-27 | 2026-09-02 | 0% | 0% | 1 | No
MS.CO.P1.B1.108 | B2 - Beams and Slab Formwork | 10 | Not Started | Con.Phase 01 | 2026-08-23 | 2026-09-02 | 2026-08-29 | 2026-09-08 | 0% | 0% | -2 | Yes
MS.CO.P2.FO.129 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 02 | 2026-08-29 | 2026-08-30 | 2026-08-29 | 2026-08-30 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.124 | Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 02 | 2026-08-27 | 2026-09-05 | 2026-08-29 | 2026-09-06 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.117 | Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 02 | 2026-08-29 | 2026-09-06 | 2026-08-29 | 2026-09-06 | 0% | 0% | 4 | No
MS.CO.P2.B3.116 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-08-29 | 2026-09-08 | 2026-08-29 | 2026-09-08 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.109 | B1 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-26 | 2026-09-08 | 2026-08-29 | 2026-09-10 | 0% | 0% | 13 | No
MS.CO.P3(1).B1.209 | B1 - Walls Concreting work | 12 | Not Started | Con.Phase 03 | 2026-08-26 | 2026-09-08 | 2026-08-29 | 2026-09-10 | 0% | 0% | 13 | No
MS.CO.P1.B2.130 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-08-27 | 2026-08-27 | 2026-08-30 | 2026-08-30 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.117 | B2 - Beams and Slab Formwork | 9 | Not Started | Con.Phase 01 | 2026-08-29 | 2026-09-07 | 2026-08-31 | 2026-09-09 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.118 | Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 03 | 2026-08-29 | 2026-09-06 | 2026-08-31 | 2026-09-08 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.109 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 8 | Not Started | Con.Phase 04 | 2026-08-29 | 2026-09-06 | 2026-09-01 | 2026-09-09 | 0% | 0% | 1 | No
MS.CO.F4.FO.118 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 04 | 2026-08-29 | 2026-08-30 | 2026-09-01 | 2026-09-02 | 0% | 0% | -1 | Yes
MS.CO.P3(2).FO.139 | Excavation for drop Panels and Trenches | 10 | Not Started | Con.Phase 03 | 2026-09-01 | 2026-09-12 | 2026-09-01 | 2026-09-12 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.133 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 0% | 0% | 0 | Yes
MS.CO.P1.B2.134 | B2 - DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-09-01 | 2026-09-02 | 2026-09-01 | 2026-09-02 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B2.130 | DE shuttering for Slab | 6 | Not Started | Con.Phase 03 | 2026-08-30 | 2026-09-04 | 2026-09-01 | 2026-09-06 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.125 | B2 - Beams and Slab Formwork | 9 | Not Started | Con.Phase 01 | 2026-09-01 | 2026-09-10 | 2026-09-02 | 2026-09-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.106 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-02 | 2026-09-08 | 2026-09-02 | 2026-09-08 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.108 | Formwork for Foundations | 7 | Not Started | Con.Phase 04 | 2026-08-30 | 2026-09-06 | 2026-09-02 | 2026-09-09 | 0% | 0% | 1 | No
MS.CO.P2.B3.206 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-02 | 2026-09-08 | 2026-09-02 | 2026-09-08 | 0% | 0% | 3 | No
MS.CO.P5.B2.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-09-11 | 2026-09-12 | 2026-09-02 | 2026-09-03 | 0% | 0% | 39 | No
MS.CO.P1.B2.135 | B2 - Block Works | 42 | Not Started | Con.Phase 01 | 2026-09-03 | 2026-10-22 | 2026-09-03 | 2026-10-22 | 0% | 0% | 10 | No
MS.CO.P1.B1.129 | B2 - Beams and Slab Formwork | 10 | Not Started | Con.Phase 01 | 2026-09-03 | 2026-09-14 | 2026-09-03 | 2026-09-14 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.106 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-08-31 | 2026-09-06 | 2026-09-03 | 2026-09-09 | 0% | 0% | 2 | No
MS.CO.P5.B2.121 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 05 | 2026-09-03 | 2026-09-08 | 2026-09-03 | 2026-09-08 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.206 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-08-31 | 2026-09-06 | 2026-09-03 | 2026-09-09 | 0% | 0% | -1 | Yes
MS.CO.P3(1).B2.131 | DE shuttering for Slab | 3 | Not Started | Con.Phase 03 | 2026-08-31 | 2026-09-02 | 2026-09-03 | 2026-09-05 | 0% | 0% | 1 | No
MS.CO.P1.B1.114 | B2 - Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-09-02 | 2026-09-09 | 2026-09-06 | 2026-09-13 | 0% | 0% | 1 | No
MS.CO.P2.B3.110 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-06 | 2026-09-12 | 2026-09-06 | 2026-09-12 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.116 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-03 | 2026-09-16 | 2026-09-06 | 2026-09-19 | 0% | 0% | 1 | No
MS.CO.P2.B3.210 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-06 | 2026-09-12 | 2026-09-06 | 2026-09-12 | 0% | 0% | 3 | No
MS.CO.P2.B3.129 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-09-06 | 2026-09-06 | 2026-09-07 | 2026-09-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.125 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 0% | 0% | 4 | No
MS.CO.P5.B1.120 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 05 | 2026-09-16 | 2026-09-28 | 2026-09-07 | 2026-09-17 | 0% | 0% | 10 | No
MS.CO.P3(1).B1.115 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-05 | 2026-09-17 | 2026-09-07 | 2026-09-20 | 0% | 0% | 0 | No
MS.CO.F4.B3.207 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-09-03 | 2026-09-09 | 2026-09-07 | 2026-09-13 | 0% | 0% | -1 | Yes
MS.CO.P2.B2.108 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-07 | 2026-09-13 | 2026-09-08 | 2026-09-14 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.100 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-08 | 2026-09-14 | 2026-09-08 | 2026-09-14 | 0% | 0% | 4 | No
MS.CO.F4.B3.107 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-09-05 | 2026-09-10 | 2026-09-08 | 2026-09-14 | 0% | 0% | 2 | No
MS.CO.P2.B2.208 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-07 | 2026-09-13 | 2026-09-08 | 2026-09-14 | 0% | 0% | 2 | No
MS.CO.P2.B2.200 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-08 | 2026-09-14 | 2026-09-08 | 2026-09-14 | 0% | 0% | 5 | No
MS.CO.P1.B1.110 | B2 - Beams and Slab Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-09-03 | 2026-09-09 | 2026-09-09 | 2026-09-15 | 0% | 0% | -2 | Yes
MS.CO.P2.B3.119 | Beams and Slab Steel Fix | 8 | Not Started | Con.Phase 02 | 2026-09-09 | 2026-09-17 | 2026-09-09 | 2026-09-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.113 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.125 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.120 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-09 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.213 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0% | 0% | 3 | No
MS.CO.P1.B1.120 | B2 - Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-09-08 | 2026-09-15 | 2026-09-10 | 2026-09-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.120 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 02 | 2026-09-10 | 2026-09-24 | 2026-09-10 | 2026-09-24 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.110 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 04 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-12 | 0% | 0% | 1 | No
MS.CO.F4.B3.120 | Beams and Slab Formwork | 11 | Not Started | Con.Phase 04 | 2026-09-07 | 2026-09-19 | 2026-09-10 | 2026-09-22 | 0% | 0% | -1 | Yes
MS.CO.P5.B1.101 | B1 - Columns Steel Fix | 4 | Not Started | Con.Phase 05 | 2026-09-10 | 2026-09-14 | 2026-09-10 | 2026-09-14 | 0% | 0% | 2 | No
MS.CO.P3(2).B1.100 | B1 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-09-08 | 2026-09-21 | 2026-09-10 | 2026-09-24 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.201 | Walls Steel Fix | 4 | Not Started | Con.Phase 05 | 2026-09-10 | 2026-09-14 | 2026-09-10 | 2026-09-14 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.209 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-09-07 | 2026-09-13 | 2026-09-10 | 2026-09-16 | 0% | 0% | -1 | Yes
MS.CO.P3(2).B1.200 | B1 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-09-08 | 2026-09-21 | 2026-09-10 | 2026-09-24 | 0% | 0% | 7 | No
MS.CO.P3(1).B2.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 0% | 0% | 4 | No
MS.CO.P2.B2.112 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-10 | 2026-09-16 | 2026-09-12 | 2026-09-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.102 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-12 | 2026-09-17 | 2026-09-12 | 2026-09-17 | 0% | 0% | 4 | No
MS.CO.F4.B3.109 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-09-08 | 2026-09-14 | 2026-09-12 | 2026-09-17 | 0% | 0% | 2 | No
MS.CO.P3(1).B1.117 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-10 | 2026-09-24 | 2026-09-12 | 2026-09-26 | 0% | 0% | 4 | No
MS.CO.P2.B2.212 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-10 | 2026-09-16 | 2026-09-12 | 2026-09-17 | 0% | 0% | 2 | No
MS.CO.P2.B2.202 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-12 | 2026-09-17 | 2026-09-12 | 2026-09-17 | 0% | 0% | 5 | No
MS.CO.P3(2).B1.203 | B1 - Walls Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-09 | 2026-09-22 | 2026-09-12 | 2026-09-26 | 0% | 0% | 7 | No
MS.CO.P1.B1.127 | B2 - Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 01 | 2026-09-12 | 2026-09-19 | 2026-09-13 | 2026-09-20 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.103 | B3 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-09-09 | 2026-09-15 | 2026-09-13 | 2026-09-19 | 0% | 0% | 1 | No
MS.CO.P5.B1.106 | B1 - Columns Formwork | 4 | Not Started | Con.Phase 05 | 2026-09-13 | 2026-09-16 | 2026-09-13 | 2026-09-16 | 0% | 0% | 2 | No
MS.CO.P3(2).B1.103 | B1 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-10 | 2026-09-24 | 2026-09-13 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.520 | Earthing and Lightning Protection System | 2 | Not Started | Con.Phase 03 | 2026-09-13 | 2026-09-14 | 2026-09-13 | 2026-09-14 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.206 | Walls Formwork | 4 | Not Started | Con.Phase 05 | 2026-09-13 | 2026-09-16 | 2026-09-13 | 2026-09-16 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.203 | B3 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-09-09 | 2026-09-15 | 2026-09-13 | 2026-09-19 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.208 | B1 - Walls Concreting work | 12 | Not Started | Con.Phase 03 | 2026-09-10 | 2026-09-24 | 2026-09-13 | 2026-09-27 | 0% | 0% | 7 | No
MS.CO.P1.B1.115 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-10 | 2026-09-10 | 2026-09-14 | 2026-09-14 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.108 | B1 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-09-12 | 2026-09-26 | 2026-09-14 | 2026-09-28 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.131 | B2 - Beams and Slab Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-09-15 | 2026-09-21 | 2026-09-15 | 2026-09-21 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.100 | Columns & Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-09-12 | 2026-09-17 | 2026-09-15 | 2026-09-21 | 0% | 0% | 1 | No
MS.CO.P2.B2.114 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-14 | 2026-09-20 | 2026-09-15 | 2026-09-21 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.106 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-15 | 2026-09-21 | 2026-09-15 | 2026-09-21 | 0% | 0% | 4 | No
MS.CO.P5.B1.111 | B1 - Columns Concreting work | 4 | Not Started | Con.Phase 05 | 2026-09-15 | 2026-09-19 | 2026-09-15 | 2026-09-19 | 0% | 0% | 2 | No
MS.CO.P3(2).FO.149 | Blinding concrete for lower Part of Foundation | 4 | Not Started | Con.Phase 03 | 2026-09-15 | 2026-09-19 | 2026-09-15 | 2026-09-19 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.214 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-14 | 2026-09-20 | 2026-09-15 | 2026-09-21 | 0% | 0% | 2 | No
MS.CO.P2.B2.206 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-15 | 2026-09-21 | 2026-09-15 | 2026-09-21 | 0% | 0% | 5 | No
MS.CO.P1.B1.111 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-10 | 2026-09-10 | 2026-09-16 | 2026-09-16 | 0% | 0% | -2 | Yes
MS.CO.P2.B2.124 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-09-15 | 2026-09-27 | 2026-09-16 | 2026-09-28 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.115 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-09-16 | 2026-09-28 | 2026-09-16 | 2026-09-28 | 0% | 0% | 4 | No
MS.CO.P1.FAI.100 | Columns & Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-09-12 | 2026-09-17 | 2026-09-17 | 2026-09-24 | 0% | 0% | 4 | No
MS.CO.F4.B3.104 | B3 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-09-14 | 2026-09-20 | 2026-09-17 | 2026-09-24 | 0% | 0% | 1 | No
MS.CO.P5.B1.211 | Walls Concreting work | 4 | Not Started | Con.Phase 05 | 2026-09-17 | 2026-09-21 | 2026-09-17 | 2026-09-21 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.204 | B3 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-09-14 | 2026-09-20 | 2026-09-17 | 2026-09-24 | 0% | 0% | 1 | No
MS.CO.P1.B1.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-16 | 2026-09-16 | 2026-09-19 | 2026-09-19 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.126 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.124 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-09-29 | 2026-09-29 | 2026-09-19 | 2026-09-19 | 0% | 0% | 10 | No
MS.CO.P5.B1.116 | Beams and Slab Formwork | 7 | Not Started | Con.Phase 05 | 2026-09-19 | 2026-09-27 | 2026-09-19 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.101 | Columns & Walls Formwork | 6 | Not Started | Con.Phase 01 | 2026-09-16 | 2026-09-22 | 2026-09-20 | 2026-09-27 | 0% | 0% | 1 | No
MS.CO.P1.FAG.100 | Columns & Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-09-17 | 2026-09-24 | 2026-09-20 | 2026-09-27 | 0% | 0% | 7 | No
MS.CO.P2.B2.101 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-20 | 2026-09-27 | 2026-09-20 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.119 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-09-17 | 2026-09-29 | 2026-09-20 | 2026-10-01 | 0% | 0% | 1 | No
MS.CO.P3(2).FO.159 | Block work for Drop Panels | 1 | Not Started | Con.Phase 03 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.201 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-09-20 | 2026-09-27 | 2026-09-20 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.128 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-20 | 2026-09-20 | 2026-09-21 | 2026-09-21 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.118 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-09-19 | 2026-09-30 | 2026-09-21 | 2026-10-03 | 0% | 0% | 0 | No
MS.CO.P3(2).B1.115 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 03 | 2026-09-19 | 2026-10-03 | 2026-09-21 | 2026-10-05 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.169 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 03 | 2026-09-21 | 2026-09-22 | 2026-09-21 | 2026-09-22 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.132 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-22 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.101 | Columns & Walls Formwork | 6 | Not Started | Con.Phase 01 | 2026-09-16 | 2026-09-22 | 2026-09-22 | 2026-09-29 | 0% | 0% | 4 | No
MS.CO.P1.FAF.100 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-09-21 | 2026-09-26 | 2026-09-22 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.105 | B3 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-09-19 | 2026-09-26 | 2026-09-22 | 2026-09-29 | 0% | 0% | 1 | No
MS.CO.P1.FAE.100 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2026-09-24 | 2026-09-27 | 2026-09-24 | 2026-09-27 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.104 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-24 | 2026-09-30 | 2026-09-24 | 2026-09-30 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.122 | Beams and Slab Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-09-20 | 2026-09-27 | 2026-09-24 | 2026-09-30 | 0% | 0% | -1 | Yes
MS.CO.P3(2).FO.179 | Water Proofing Membrane under Raft Foundation | 8 | Not Started | Con.Phase 03 | 2026-09-24 | 2026-10-03 | 2026-09-24 | 2026-10-03 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.204 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-09-24 | 2026-09-30 | 2026-09-24 | 2026-09-30 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.102 | Columns & Walls Concreting work | 6 | Not Started | Con.Phase 01 | 2026-09-21 | 2026-09-28 | 2026-09-26 | 2026-10-01 | 0% | 0% | 1 | No
MS.CO.P1.FAG.101 | Columns & Walls Formwork | 6 | Not Started | Con.Phase 01 | 2026-09-22 | 2026-09-29 | 2026-09-26 | 2026-10-01 | 0% | 0% | 7 | No
MS.CO.P1.FAF.101 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-09-24 | 2026-09-28 | 2026-09-26 | 2026-09-29 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.123 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 02 | 2026-09-26 | 2026-10-06 | 2026-09-26 | 2026-10-06 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.114 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 04 | 2026-09-21 | 2026-10-05 | 2026-09-26 | 2026-10-08 | 0% | 0% | 1 | No
MS.CO.F4.B3.205 | B3 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-09-21 | 2026-09-28 | 2026-09-26 | 2026-10-01 | 0% | 0% | 1 | No
MS.CO.P1.FAE.101 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2026-09-27 | 2026-09-29 | 2026-09-27 | 2026-09-29 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.120 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-09-26 | 2026-10-06 | 2026-09-27 | 2026-10-07 | 0% | 0% | 4 | No
MS.CO.P1.FAI.102 | Columns & Walls Concreting work | 6 | Not Started | Con.Phase 01 | 2026-09-21 | 2026-09-28 | 2026-09-28 | 2026-10-04 | 0% | 0% | 4 | No
MS.CO.P2.B2.109 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-28 | 2026-10-04 | 2026-09-28 | 2026-10-04 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.121 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 05 | 2026-09-28 | 2026-10-03 | 2026-09-28 | 2026-10-03 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.209 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-09-28 | 2026-10-04 | 2026-09-28 | 2026-10-04 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-09-26 | 2026-09-30 | 2026-09-29 | 2026-10-04 | 0% | 0% | 1 | No
MS.CO.P2.B2.128 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 02 | 2026-09-28 | 2026-10-05 | 2026-09-29 | 2026-10-06 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.117 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 02 | 2026-09-29 | 2026-10-06 | 2026-09-29 | 2026-10-06 | 0% | 0% | 4 | No
MS.CO.P2.B2.116 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-09-29 | 2026-10-10 | 2026-09-29 | 2026-10-10 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.102 | Columns & Walls Concreting work | 6 | Not Started | Con.Phase 01 | 2026-09-28 | 2026-10-04 | 2026-09-30 | 2026-10-06 | 0% | 0% | 7 | No
MS.CO.P1.FAF.102 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-29 | 2026-09-29 | 2026-09-30 | 2026-09-30 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.102 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-09-30 | 2026-10-05 | 2026-10-01 | 2026-10-06 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-01 | 2026-10-06 | 2026-10-01 | 2026-10-06 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.123 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-01 | 0% | 0% | -1 | Yes
MS.CO.P2.B3.134 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-09-30 | 2026-10-01 | 2026-10-01 | 2026-10-02 | 0% | 0% | 13 | No
MS.CO.P2.B3.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | 0% | 0% | 18 | No
MS.CO.F4.B2.106 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-09-29 | 2026-10-05 | 2026-10-03 | 2026-10-08 | 0% | 0% | -1 | Yes
MS.CO.P3(1).B1.123 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-09-30 | 2026-09-30 | 2026-10-03 | 2026-10-03 | 0% | 0% | 1 | No
MS.CO.F4.B2.206 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-09-29 | 2026-10-05 | 2026-10-03 | 2026-10-08 | 0% | 0% | 3 | No
MS.CO.P5.B1.125 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-10-04 | 2026-10-04 | 2026-10-04 | 2026-10-04 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-01 | 2026-10-01 | 2026-10-04 | 2026-10-04 | 0% | 0% | 0 | No
MS.CO.P3(1).FAN.100 | Columns & Walls Steel Fix | 6 | Not Started | Con.Phase 03 | 2026-10-01 | 2026-10-07 | 2026-10-04 | 2026-10-10 | 0% | 0% | 13 | No
MS.CO.P3(2).FO.104 | Rebars for 1st layer for Foundation | 8 | Not Started | Con.Phase 03 | 2026-10-04 | 2026-10-12 | 2026-10-04 | 2026-10-12 | 0% | 0% | 0 | Yes
MS.CO.P5.B2.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-10-04 | 2026-10-05 | 2026-10-04 | 2026-10-05 | 0% | 0% | 12 | No
MS.CO.P3(2).B2.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-10-01 | 2026-10-02 | 2026-10-04 | 2026-10-05 | 0% | 0% | 160 | No
MS.CO.P1.FAH.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-01 | 2026-10-05 | 2026-10-05 | 2026-10-08 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.100 | Columns & Walls Steel Fix | 8 | Not Started | Con.Phase 03 | 2026-10-03 | 2026-10-11 | 2026-10-05 | 2026-10-13 | 0% | 0% | 9 | No
MS.CO.P5.B2.135 | B2 - Block Works | 28 | Not Started | Con.Phase 05 | 2026-10-06 | 2026-11-07 | 2026-10-06 | 2026-11-07 | 0% | 0% | 20 | No
MS.CO.F4.B2.108 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-10-03 | 2026-10-08 | 2026-10-06 | 2026-10-12 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.100 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 05 | 2026-10-06 | 2026-10-10 | 2026-10-06 | 2026-10-10 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.118 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 03 | 2026-10-04 | 2026-10-14 | 2026-10-06 | 2026-10-17 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.208 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-10-03 | 2026-10-08 | 2026-10-06 | 2026-10-12 | 0% | 0% | 3 | No
MS.CO.P1.FAF.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-06 | 2026-10-10 | 2026-10-07 | 2026-10-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-07 | 2026-10-11 | 2026-10-07 | 2026-10-11 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.128 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.129 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-10-06 | 2026-10-06 | 2026-10-07 | 2026-10-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.119 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.101 | Columns & Walls Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-05 | 2026-10-11 | 2026-10-07 | 2026-10-13 | 0% | 0% | 13 | No
MS.CO.P2.B2.105 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-08 | 2026-10-14 | 2026-10-08 | 2026-10-14 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.108 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-07 | 2026-10-13 | 2026-10-08 | 2026-10-14 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.100 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-08 | 2026-10-14 | 2026-10-08 | 2026-10-14 | 0% | 0% | 4 | No
MS.CO.P5.FA.101 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 05 | 2026-10-08 | 2026-10-12 | 2026-10-08 | 2026-10-12 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.124 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-07 | 2026-10-07 | 2026-10-08 | 2026-10-08 | 0% | 0% | 4 | No
MS.CO.P3(1).FAM.101 | Columns & Walls Formwork | 8 | Not Started | Con.Phase 03 | 2026-10-06 | 2026-10-14 | 2026-10-08 | 2026-10-17 | 0% | 0% | 9 | No
MS.CO.P2.B1.208 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-07 | 2026-10-13 | 2026-10-08 | 2026-10-14 | 0% | 0% | 6 | No
MS.CO.P2.B1.200 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-08 | 2026-10-14 | 2026-10-08 | 2026-10-14 | 0% | 0% | 9 | No
MS.CO.P2.B2.205 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-08 | 2026-10-14 | 2026-10-08 | 2026-10-14 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.126 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-10-05 | 2026-10-05 | 2026-10-08 | 2026-10-08 | 0% | 0% | 23 | No
MS.CO.P1.FAH.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-06 | 2026-10-06 | 2026-10-10 | 2026-10-10 | 0% | 0% | 1 | No
MS.CO.F4.B3.117 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 04 | 2026-10-06 | 2026-10-13 | 2026-10-10 | 2026-10-17 | 0% | 0% | 1 | No
MS.CO.F4.B2.110 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-10-06 | 2026-10-12 | 2026-10-10 | 2026-10-15 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAO.100 | Columns & Walls Steel Fix | 6 | Not Started | Con.Phase 03 | 2026-10-08 | 2026-10-14 | 2026-10-10 | 2026-10-15 | 0% | 0% | 8 | No
MS.CO.F4.B2.210 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-10-06 | 2026-10-12 | 2026-10-10 | 2026-10-15 | 0% | 0% | 3 | No
MS.CO.P1.FAH.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-07 | 2026-10-12 | 2026-10-11 | 2026-10-15 | 0% | 0% | 1 | No
MS.CO.P2.B2.120 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 02 | 2026-10-11 | 2026-10-18 | 2026-10-11 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.120 | Beams and Slab Formwork | 11 | Not Started | Con.Phase 04 | 2026-10-07 | 2026-10-19 | 2026-10-11 | 2026-10-22 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.102 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 05 | 2026-10-11 | 2026-10-14 | 2026-10-11 | 2026-10-14 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.102 | Columns & Walls Concreting work | 6 | Not Started | Con.Phase 03 | 2026-10-08 | 2026-10-14 | 2026-10-11 | 2026-10-17 | 0% | 0% | 13 | No
MS.CO.P3(2).FO.107 | Installation for Mechanical and Electrical Embeds | 4 | Not Started | Con.Phase 03 | 2026-10-11 | 2026-10-14 | 2026-10-11 | 2026-10-14 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.124 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-10-05 | 2026-10-05 | 2026-10-11 | 2026-10-11 | 0% | 0% | -3 | Yes
MS.CO.P1.B1.130 | B2 - DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2026-10-11 | 2026-10-11 | 2026-10-11 | 2026-10-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.103 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 01 | 2026-10-06 | 2026-10-12 | 2026-10-12 | 2026-10-18 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-12 | 2026-10-17 | 2026-10-12 | 2026-10-17 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-11 | 2026-10-11 | 2026-10-12 | 2026-10-12 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.110 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.112 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-11 | 2026-10-17 | 2026-10-12 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.102 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 | 0% | 0% | 4 | No
MS.CO.P3(2).FO.109 | Formwork for Foundations | 5 | Not Started | Con.Phase 03 | 2026-10-12 | 2026-10-17 | 2026-10-12 | 2026-10-17 | 0% | 0% | 1 | No
MS.CO.P2.B1.212 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-11 | 2026-10-17 | 2026-10-12 | 2026-10-18 | 0% | 0% | 6 | No
MS.CO.P2.B1.202 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 | 0% | 0% | 9 | No
MS.CO.P2.B2.210 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-10 | 2026-10-14 | 2026-10-13 | 2026-10-18 | 0% | 0% | 1 | No
MS.CO.P1.FAF.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-12 | 2026-10-17 | 2026-10-13 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-13 | 2026-10-18 | 2026-10-13 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.103 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 05 | 2026-10-13 | 2026-10-17 | 2026-10-13 | 2026-10-17 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.102 | Columns & Walls Concreting work | 8 | Not Started | Con.Phase 03 | 2026-10-11 | 2026-10-19 | 2026-10-13 | 2026-10-21 | 0% | 0% | 9 | No
MS.CO.P3(2).FO.112 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 5 | Not Started | Con.Phase 03 | 2026-10-13 | 2026-10-18 | 2026-10-13 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-10-13 | 2026-10-14 | 2026-10-13 | 2026-10-14 | 0% | 0% | 14 | No
MS.CO.P5.B1.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-10-22 | 2026-10-23 | 2026-10-13 | 2026-10-14 | 0% | 0% | 12 | No
MS.CO.P1.FAH.108 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-10-12 | 2026-10-17 | 2026-10-15 | 2026-10-20 | 0% | 0% | 1 | No
MS.CO.P1.FAF.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-14 | 2026-10-19 | 2026-10-15 | 2026-10-20 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.113 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-15 | 2026-10-21 | 2026-10-15 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.114 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-14 | 2026-10-20 | 2026-10-15 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.106 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-15 | 2026-10-21 | 2026-10-15 | 2026-10-21 | 0% | 0% | 4 | No
MS.CO.P2.B1.214 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-14 | 2026-10-20 | 2026-10-15 | 2026-10-21 | 0% | 0% | 6 | No
MS.CO.P2.B1.206 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-15 | 2026-10-21 | 2026-10-15 | 2026-10-21 | 0% | 0% | 9 | No
MS.CO.P2.B2.213 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-15 | 2026-10-21 | 2026-10-15 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.133 | B2 - DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-10-14 | 2026-10-15 | 2026-10-15 | 2026-10-16 | 0% | 0% | 18 | No
MS.CO.P1.B1.134 | B2 - DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-10-16 | 2026-10-17 | 2026-10-16 | 2026-10-17 | 0% | 0% | 17 | No
MS.CO.P1.FAE.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-17 | 2026-10-21 | 2026-10-17 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.121 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 02 | 2026-10-17 | 2026-10-27 | 2026-10-17 | 2026-10-27 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.124 | Beams and Slab Formwork | 14 | Not Started | Con.Phase 02 | 2026-10-15 | 2026-10-31 | 2026-10-17 | 2026-11-01 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.115 | Beams and Slab Formwork | 14 | Not Started | Con.Phase 02 | 2026-10-17 | 2026-11-01 | 2026-10-17 | 2026-11-01 | 0% | 0% | 4 | No
MS.CO.P1.FAH.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-14 | 2026-10-19 | 2026-10-18 | 2026-10-22 | 0% | 0% | 1 | No
MS.CO.P1.FAG.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-18 | 2026-10-21 | 2026-10-18 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.118 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-10-14 | 2026-10-14 | 2026-10-18 | 2026-10-18 | 0% | 0% | 1 | No
MS.CO.P5.FA.104 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-10-18 | 2026-10-20 | 2026-10-18 | 2026-10-20 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.120 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-15 | 2026-10-15 | 2026-10-18 | 2026-10-18 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.104 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-13 | 2026-10-18 | 2026-10-19 | 2026-10-24 | 0% | 0% | -2 | Yes
MS.CO.P2.B2.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.103 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-10-15 | 2026-10-21 | 2026-10-19 | 2026-10-25 | 0% | 0% | 2 | No
MS.CO.P3(2).FAL.100 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-10-17 | 2026-10-21 | 2026-10-19 | 2026-10-24 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.119 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 03 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.203 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-10-15 | 2026-10-21 | 2026-10-19 | 2026-10-25 | 0% | 0% | 1 | No
MS.CO.P2.B1.101 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-20 | 2026-10-26 | 2026-10-20 | 2026-10-26 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.101 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-10-18 | 2026-10-22 | 2026-10-20 | 2026-10-25 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.101 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 03 | 2026-10-20 | 2026-10-26 | 2026-10-20 | 2026-10-26 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.201 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-10-20 | 2026-10-26 | 2026-10-20 | 2026-10-26 | 0% | 0% | 7 | No
MS.CO.P3(2).B2.201 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 03 | 2026-10-20 | 2026-10-26 | 2026-10-20 | 2026-10-26 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.108 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-20 | 2026-10-20 | 2026-10-21 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-10-21 | 2026-10-21 | 2026-10-21 | 2026-10-21 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.101 | Columns & Walls Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-20 | 2026-10-26 | 2026-10-21 | 2026-10-27 | 0% | 0% | 8 | No
MS.CO.P3(2).B2.105 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-21 | 2026-10-27 | 2026-10-21 | 2026-10-27 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.205 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-21 | 2026-10-27 | 2026-10-21 | 2026-10-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-21 | 2026-10-26 | 2026-10-22 | 2026-10-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.108 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.104 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-10-19 | 2026-10-25 | 2026-10-22 | 2026-10-28 | 0% | 0% | 2 | No
MS.CO.P5.FA.106 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-10-22 | 2026-10-25 | 2026-10-22 | 2026-10-25 | 0% | 0% | 0 | Yes
MS.CO.P1.B1.135 | B2 - Block Works | 30 | Not Started | Con.Phase 01 | 2026-10-24 | 2026-11-26 | 2026-10-24 | 2026-11-26 | 0% | 0% | 10 | No
MS.CO.P1.FAH.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-20 | 2026-10-24 | 2026-10-24 | 2026-10-27 | 0% | 0% | 1 | No
MS.CO.P1.FAG.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-24 | 2026-10-28 | 2026-10-24 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-24 | 2026-10-28 | 2026-10-24 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.104 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-24 | 2026-10-29 | 2026-10-24 | 2026-10-29 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.122 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 04 | 2026-10-20 | 2026-10-31 | 2026-10-24 | 2026-11-03 | 0% | 0% | -1 | Yes
MS.CO.P2.B1.204 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-10-24 | 2026-10-29 | 2026-10-24 | 2026-10-29 | 0% | 0% | 7 | No
MS.CO.F4.B2.204 | B2 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-10-20 | 2026-10-26 | 2026-10-24 | 2026-10-29 | 0% | 0% | 1 | No
MS.CO.P1.FAI.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-19 | 2026-10-19 | 2026-10-25 | 2026-10-25 | 0% | 0% | -2 | Yes
MS.CO.P5.FA.107 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-10-25 | 2026-10-27 | 2026-10-25 | 2026-10-27 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2026-10-21 | 2026-10-22 | 2026-10-25 | 2026-10-26 | 0% | 0% | 15 | No
MS.CO.P1.FAI.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-20 | 2026-10-24 | 2026-10-26 | 2026-10-29 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-26 | 2026-10-31 | 2026-10-26 | 2026-10-31 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.108 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-10-26 | 2026-10-28 | 2026-10-26 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.102 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-24 | 2026-10-24 | 2026-10-26 | 2026-10-26 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-10-23 | 2026-10-24 | 2026-10-26 | 2026-10-27 | 0% | 0% | 1 | No
MS.CO.P2.B1.109 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-27 | 2026-11-02 | 2026-10-27 | 2026-11-02 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.105 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-10-24 | 2026-10-29 | 2026-10-27 | 2026-11-02 | 0% | 0% | 2 | No
MS.CO.P5.FA.110 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 05 | 2026-10-27 | 2026-10-31 | 2026-10-27 | 2026-10-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.103 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2026-10-25 | 2026-11-02 | 2026-10-27 | 2026-11-04 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.209 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-10-27 | 2026-11-02 | 2026-10-27 | 2026-11-02 | 0% | 0% | 7 | No
MS.CO.P5.B1.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-10-27 | 2026-10-28 | 2026-10-27 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-10-25 | 2026-10-25 | 2026-10-28 | 2026-10-28 | 0% | 0% | 1 | No
MS.CO.P1.FAG.108 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-10-28 | 2026-11-02 | 2026-10-28 | 2026-11-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-27 | 2026-10-31 | 2026-10-28 | 2026-11-01 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.125 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 02 | 2026-10-28 | 2026-11-04 | 2026-10-28 | 2026-11-04 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.103 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-25 | 2026-10-31 | 2026-10-28 | 2026-11-03 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.102 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 03 | 2026-10-27 | 2026-10-28 | 2026-10-28 | 2026-10-29 | 0% | 0% | 8 | No
MS.CO.P3(2).B2.110 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.205 | B2 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-10-25 | 2026-10-31 | 2026-10-28 | 2026-11-03 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.210 | B2 - Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-10-24 | 2026-10-27 | 2026-10-29 | 2026-11-02 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.114 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-10-26 | 2026-10-31 | 2026-10-29 | 2026-11-03 | 0% | 0% | 1 | No
MS.CO.P1.FAE.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-10-29 | 2026-11-02 | 2026-10-29 | 2026-11-02 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.116 | Beams and Slab Formwork | 14 | Not Started | Con.Phase 02 | 2026-10-29 | 2026-11-14 | 2026-10-29 | 2026-11-14 | 0% | 0% | 0 | Yes
MS.CO.P5.B1.135 | B2 - Block Works | 28 | Not Started | Con.Phase 05 | 2026-10-29 | 2026-11-30 | 2026-10-29 | 2026-11-30 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.103 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-10-27 | 2026-11-02 | 2026-10-29 | 2026-11-04 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.116 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2026-10-29 | 2026-11-07 | 2026-10-29 | 2026-11-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.133 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-10-30 | 2026-10-31 | 2026-10-30 | 2026-10-31 | 0% | 0% | 77 | No
MS.CO.P2.B2.134 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-10-29 | 2026-10-30 | 2026-10-30 | 2026-10-31 | 0% | 0% | 21 | No
MS.CO.P2.B2.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-10-30 | 2026-10-31 | 2026-10-30 | 2026-10-31 | 0% | 0% | 103 | No
MS.CO.P1.FAG.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-31 | 2026-11-04 | 2026-10-31 | 2026-11-04 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.114 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 04 | 2026-10-27 | 2026-11-07 | 2026-10-31 | 2026-11-10 | 0% | 0% | 1 | No
MS.CO.P1.FAH.115 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-28 | 2026-11-02 | 2026-11-01 | 2026-11-05 | 0% | 0% | 1 | No
MS.CO.P5.FA.111 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-11-01 | 2026-11-03 | 2026-11-01 | 2026-11-03 | 0% | 0% | 0 | Yes
MS.CO.P3(1).B1.132 | DE shuttering for Slab | 4 | Not Started | Con.Phase 03 | 2026-10-30 | 2026-11-02 | 2026-11-01 | 2026-11-04 | 0% | 0% | 4 | No
MS.CO.P1.FAI.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-05 | 0% | 0% | -2 | Yes
MS.CO.P1.FAF.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-01 | 2026-11-01 | 2026-11-02 | 2026-11-02 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.128 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 02 | 2026-11-01 | 2026-11-11 | 2026-11-02 | 2026-11-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.117 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 02 | 2026-11-02 | 2026-11-12 | 2026-11-02 | 2026-11-12 | 0% | 0% | 4 | No
MS.CO.P1.FAH.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 0% | 0% | 1 | No
MS.CO.P1.FAI.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-10-28 | 2026-11-02 | 2026-11-03 | 2026-11-08 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.117 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-10-31 | 2026-11-03 | 2026-11-03 | 2026-11-07 | 0% | 0% | 1 | No
MS.CO.P1.FAF.114 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-11-02 | 2026-11-07 | 2026-11-03 | 2026-11-08 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-03 | 2026-11-03 | 2026-11-03 | 2026-11-03 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.113 | External Block Work | 20 | Not Started | Con.Phase 01 | 2026-10-31 | 2026-11-22 | 2026-11-04 | 2026-11-26 | 0% | 0% | 4 | No
MS.CO.P1.FAH.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-01 | 2026-11-05 | 2026-11-04 | 2026-11-09 | 0% | 0% | 1 | No
MS.CO.P1.FAE.114 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2026-11-04 | 2026-11-07 | 2026-11-04 | 2026-11-07 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.123 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-11-01 | 2026-11-01 | 2026-11-04 | 2026-11-04 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.104 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-01 | 2026-11-05 | 2026-11-04 | 2026-11-09 | 0% | 0% | 1 | No
MS.CO.P1.FAF.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-03 | 2026-11-04 | 2026-11-04 | 2026-11-05 | 0% | 0% | 3 | No
MS.CO.P1.FAE.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-04 | 2026-11-05 | 2026-11-04 | 2026-11-05 | 0% | 0% | 7 | No
MS.CO.P1.FAG.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-05 | 2026-11-09 | 2026-11-05 | 2026-11-09 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.115 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-04 | 2026-11-09 | 2026-11-05 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.127 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.106 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-11-02 | 2026-11-08 | 2026-11-05 | 2026-11-11 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.113 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-11-05 | 2026-11-08 | 2026-11-05 | 2026-11-08 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.104 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-03 | 2026-11-08 | 2026-11-05 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.103 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-11-03 | 2026-11-09 | 2026-11-05 | 2026-11-11 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.104 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-03 | 2026-11-08 | 2026-11-05 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.206 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-11-02 | 2026-11-08 | 2026-11-05 | 2026-11-11 | 0% | 0% | -1 | Yes
MS.CO.P1.FAF.113 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-05 | 2026-11-21 | 2026-11-07 | 2026-11-22 | 0% | 0% | 2 | No
MS.CO.P1.FAE.113 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-07 | 2026-11-22 | 2026-11-07 | 2026-11-22 | 0% | 0% | 6 | No
MS.CO.P1.FAE.115 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2026-11-07 | 2026-11-09 | 2026-11-07 | 2026-11-09 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.105 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-11-07 | 2026-11-12 | 2026-11-07 | 2026-11-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.205 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 02 | 2026-11-07 | 2026-11-12 | 2026-11-07 | 2026-11-12 | 0% | 0% | 7 | No
MS.CO.P1.FAF.117 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-11-07 | 2026-11-11 | 2026-11-08 | 2026-11-12 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.108 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-11-05 | 2026-11-11 | 2026-11-08 | 2026-11-14 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.114 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-11-08 | 2026-11-10 | 2026-11-08 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.121 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-11-08 | 2026-11-15 | 2026-11-08 | 2026-11-15 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.208 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-11-05 | 2026-11-11 | 2026-11-08 | 2026-11-14 | 0% | 0% | -1 | Yes
MS.CO.P1.FAI.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-12 | 0% | 0% | -2 | Yes
MS.CO.P5.FA.116 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-11-09 | 2026-11-11 | 2026-11-09 | 2026-11-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-07 | 2026-11-10 | 2026-11-10 | 2026-11-14 | 0% | 0% | 1 | No
MS.CO.P1.FAG.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-09 | 2026-11-14 | 2026-11-10 | 2026-11-15 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.117 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.110 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 02 | 2026-11-10 | 2026-11-16 | 2026-11-10 | 2026-11-16 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.119 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 05 | 2026-11-10 | 2026-11-14 | 2026-11-10 | 2026-11-14 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-07 | 2026-11-07 | 2026-11-10 | 2026-11-10 | 0% | 0% | 1 | No
MS.CO.P2.B1.210 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 02 | 2026-11-10 | 2026-11-16 | 2026-11-10 | 2026-11-16 | 0% | 0% | 7 | No
MS.CO.F4.B3.128 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2026-11-06 | 2026-11-07 | 2026-11-10 | 2026-11-11 | 0% | 0% | 19 | No
MS.CO.P3(2).B1.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 0% | 0% | 131 | No
MS.CO.P1.FAG.114 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-11-11 | 2026-11-16 | 2026-11-11 | 2026-11-16 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-11 | 2026-11-16 | 2026-11-11 | 2026-11-16 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.117 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 04 | 2026-11-08 | 2026-11-15 | 2026-11-11 | 2026-11-18 | 0% | 0% | 1 | No
MS.CO.F4.B1.111 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-11-09 | 2026-11-15 | 2026-11-11 | 2026-11-17 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAM.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-09 | 2026-11-09 | 2026-11-11 | 2026-11-11 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-11-08 | 2026-11-11 | 2026-11-11 | 2026-11-15 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-09 | 2026-11-09 | 2026-11-11 | 2026-11-11 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.211 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-11-09 | 2026-11-15 | 2026-11-11 | 2026-11-17 | 0% | 0% | -1 | Yes
MS.CO.P2.B2.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-11-11 | 2026-11-12 | 2026-11-11 | 2026-11-12 | 0% | 0% | 18 | No
MS.CO.F4.B1.120 | Beams and Slab Formwork | 10 | Not Started | Con.Phase 04 | 2026-11-10 | 2026-11-21 | 2026-11-12 | 2026-11-23 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAM.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-11-10 | 2026-11-14 | 2026-11-12 | 2026-11-16 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.104 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-10 | 2026-11-15 | 2026-11-12 | 2026-11-17 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-10 | 2026-11-15 | 2026-11-12 | 2026-11-17 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-11-13 | 2026-11-14 | 2026-11-13 | 2026-11-14 | 0% | 0% | 16 | No
MS.CO.P1.FAI.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-08 | 2026-11-08 | 2026-11-14 | 2026-11-14 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.115 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-14 | 2026-11-18 | 2026-11-14 | 2026-11-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.129 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-11-12 | 2026-11-12 | 2026-11-14 | 2026-11-14 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.119 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-11-14 | 2026-11-14 | 2026-11-14 | 2026-11-14 | 0% | 0% | 4 | No
MS.CO.P2.B1.113 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 02 | 2026-11-14 | 2026-11-19 | 2026-11-14 | 2026-11-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-11-10 | 2026-11-14 | 2026-11-14 | 2026-11-17 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-11-11 | 2026-11-16 | 2026-11-14 | 2026-11-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.213 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 02 | 2026-11-14 | 2026-11-19 | 2026-11-14 | 2026-11-19 | 0% | 0% | 7 | No
MS.CO.P1.FAI.114 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2026-11-18 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.116 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-11-10 | 2026-12-02 | 2026-11-15 | 2026-12-07 | 0% | 0% | 8 | No
MS.CO.P1.FAH.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-11 | 2026-11-11 | 2026-11-15 | 2026-11-15 | 0% | 0% | 1 | No
MS.CO.P2.B1.120 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 02 | 2026-11-15 | 2026-11-25 | 2026-11-15 | 2026-11-25 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.100 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-11-15 | 2026-11-18 | 2026-11-15 | 2026-11-18 | 0% | 0% | 5 | No
MS.CO.P2.RB.100 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 02 | 2026-11-14 | 2026-11-18 | 2026-11-15 | 2026-11-19 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.120 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-11-15 | 2026-11-17 | 2026-11-15 | 2026-11-17 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-11-12 | 2026-11-16 | 2026-11-15 | 2026-11-18 | 0% | 0% | 1 | No
MS.CO.P1.FAG.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-15 | 2026-11-16 | 2026-11-15 | 2026-11-16 | 0% | 0% | 1 | No
MS.CO.P1.FAH.123 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-11-12 | 2026-11-17 | 2026-11-16 | 2026-11-21 | 0% | 0% | 1 | No
MS.CO.P1.FAG.117 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-11-16 | 2026-11-21 | 2026-11-16 | 2026-11-21 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-15 | 2026-11-18 | 2026-11-16 | 2026-11-19 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.121 | Beams and Slab Formwork | 14 | Not Started | Con.Phase 02 | 2026-11-16 | 2026-12-01 | 2026-11-16 | 2026-12-01 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.101 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-11-16 | 2026-11-19 | 2026-11-16 | 2026-11-19 | 0% | 0% | 5 | No
MS.CO.P3(1).FAN.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-11-12 | 2026-11-16 | 2026-11-16 | 2026-11-19 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.115 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-11-11 | 2026-11-15 | 2026-11-17 | 2026-11-21 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.113 | External Block Work | 20 | Not Started | Con.Phase 01 | 2026-11-17 | 2026-12-09 | 2026-11-17 | 2026-12-09 | 0% | 0% | 8 | No
MS.CO.P1.FAF.116 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-11-16 | 2026-12-08 | 2026-11-17 | 2026-12-09 | 0% | 0% | 2 | No
MS.CO.P1.FAE.116 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-11-17 | 2026-12-09 | 2026-11-17 | 2026-12-09 | 0% | 0% | 6 | No
MS.CO.P1.FAE.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-17 | 2026-11-21 | 2026-11-17 | 2026-11-21 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.102 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-11-17 | 2026-11-21 | 2026-11-17 | 2026-11-21 | 0% | 0% | 5 | No
MS.CO.P2.RB.101 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 02 | 2026-11-16 | 2026-11-21 | 2026-11-17 | 2026-11-22 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-11-15 | 2026-11-18 | 2026-11-17 | 2026-11-21 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.110 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-11-14 | 2026-11-19 | 2026-11-17 | 2026-11-23 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.101 | B1 - Columns Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-11-17 | 2026-11-24 | 2026-11-17 | 2026-11-24 | 0% | 0% | 2 | No
MS.CO.P3(2).B1.201 | B1 - Walls Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-11-17 | 2026-11-24 | 2026-11-17 | 2026-11-24 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-11 | 2026-11-12 | 2026-11-17 | 2026-11-18 | 0% | 0% | -1 | Yes
MS.CO.P1.FAH.124 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-15 | 2026-11-19 | 2026-11-18 | 2026-11-23 | 0% | 0% | 1 | No
MS.CO.P1.FAG.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-18 | 2026-11-23 | 2026-11-18 | 2026-11-23 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-11-18 | 2026-11-23 | 2026-11-18 | 2026-11-23 | 0% | 0% | 5 | No
MS.CO.P5.FA.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 03 | 2026-11-16 | 2026-11-21 | 2026-11-18 | 2026-11-23 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-16 | 2026-11-16 | 2026-11-18 | 2026-11-18 | 0% | 0% | 3 | No
MS.CO.P1.FAI.117 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-11-14 | 2026-11-17 | 2026-11-19 | 2026-11-23 | 0% | 0% | -2 | Yes
MS.CO.P2.RB.102 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 02 | 2026-11-18 | 2026-11-23 | 2026-11-19 | 2026-11-24 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.118 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-11-16 | 2026-11-16 | 2026-11-19 | 2026-11-19 | 0% | 0% | 1 | No
MS.CO.P5.FA.122 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-11-19 | 2026-11-22 | 2026-11-19 | 2026-11-22 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-17 | 2026-11-22 | 2026-11-19 | 2026-11-24 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.108 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-17 | 2026-11-17 | 2026-11-19 | 2026-11-19 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-21 | 0% | 0% | 2 | No
MS.CO.P1.FAI.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-15 | 2026-11-19 | 2026-11-21 | 2026-11-25 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.126 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-11-17 | 2026-11-22 | 2026-11-21 | 2026-11-25 | 0% | 0% | 1 | No
MS.CO.P1.FAF.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-19 | 2026-11-19 | 2026-11-21 | 2026-11-21 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.103 | B1 - Columns Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-11-17 | 2026-11-23 | 2026-11-21 | 2026-11-26 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.109 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2026-11-18 | 2026-11-26 | 2026-11-21 | 2026-11-29 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.203 | B1 - Walls Steel Fix | 6 | Not Started | Con.Phase 04 | 2026-11-17 | 2026-11-23 | 2026-11-21 | 2026-11-26 | 0% | 0% | 1 | No
MS.CO.P1.FAF.123 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-21 | 2026-11-24 | 2026-11-22 | 2026-11-25 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-22 | 2026-11-22 | 2026-11-22 | 2026-11-22 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-11-21 | 2026-11-25 | 2026-11-22 | 2026-11-26 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.123 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-11-22 | 2026-11-24 | 2026-11-22 | 2026-11-24 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.105 | B1 - Columns Formwork | 7 | Not Started | Con.Phase 03 | 2026-11-22 | 2026-11-29 | 2026-11-22 | 2026-11-29 | 0% | 0% | 2 | No
MS.CO.P1.FAH.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-19 | 2026-11-24 | 2026-11-23 | 2026-11-28 | 0% | 0% | 1 | No
MS.CO.P1.FAE.123 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.125 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-11-21 | 2026-11-25 | 2026-11-23 | 2026-11-28 | 0% | 0% | 3 | No
MS.CO.P1.FAG.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-24 | 2026-11-28 | 2026-11-24 | 2026-11-28 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-11-24 | 2026-11-28 | 2026-11-24 | 2026-11-28 | 0% | 0% | 5 | No
MS.CO.F4.B1.104 | B1 - Columns Formwork | 6 | Not Started | Con.Phase 04 | 2026-11-21 | 2026-11-26 | 2026-11-24 | 2026-11-30 | 0% | 0% | 1 | No
MS.CO.F4.B1.123 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 04 | 2026-11-22 | 2026-11-29 | 2026-11-24 | 2026-12-01 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAM.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-11-22 | 2026-11-25 | 2026-11-24 | 2026-11-28 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.111 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-21 | 2026-11-25 | 2026-11-24 | 2026-11-29 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.108 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 03 | 2026-11-22 | 2026-11-26 | 2026-11-24 | 2026-11-29 | 0% | 0% | 3 | No
MS.CO.F4.B1.204 | B1 - Walls Formwork | 6 | Not Started | Con.Phase 04 | 2026-11-21 | 2026-11-26 | 2026-11-24 | 2026-11-30 | 0% | 0% | 1 | No
MS.CO.P1.FAF.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-11-24 | 2026-11-28 | 2026-11-25 | 2026-11-29 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.124 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2026-11-25 | 2026-11-28 | 2026-11-25 | 2026-11-28 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.128 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2026-11-25 | 2026-11-28 | 2026-11-25 | 2026-11-28 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.110 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-11-23 | 2026-11-29 | 2026-11-25 | 2026-12-01 | 0% | 0% | 3 | No
MS.CO.P3(2).B1.205 | B1 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-11-25 | 2026-12-02 | 2026-11-25 | 2026-12-02 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.210 | B1 - Walls Concreting work | 7 | Not Started | Con.Phase 03 | 2026-11-25 | 2026-12-02 | 2026-11-25 | 2026-12-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-24 | 2026-11-25 | 2026-11-25 | 2026-11-26 | 0% | 0% | 5 | No
MS.CO.P1.FAI.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-21 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 0% | 0% | -2 | Yes
MS.CO.P2.B1.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-11-26 | 2026-11-27 | 2026-11-26 | 2026-11-27 | 0% | 0% | 9 | No
MS.CO.F4.B2.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2026-11-24 | 2026-11-25 | 2026-11-27 | 2026-11-28 | 0% | 0% | 8 | No
MS.CO.P5.FA.117 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-11-27 | 2026-11-28 | 2026-11-27 | 2026-11-28 | 0% | 0% | 16 | No
MS.CO.P1.FAI.113 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-28 | 2026-12-13 | 2026-11-28 | 2026-12-13 | 0% | 0% | 10 | No
MS.CO.P1.FAH.122 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-23 | 2026-12-08 | 2026-11-28 | 2026-12-13 | 0% | 0% | 4 | No
MS.CO.P1.FAG.116 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-11-28 | 2026-12-20 | 2026-11-28 | 2026-12-20 | 0% | 0% | 11 | No
MS.CO.P1.FAF.122 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-26 | 2026-12-12 | 2026-11-28 | 2026-12-13 | 0% | 0% | 4 | No
MS.CO.P1.FAE.122 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-11-28 | 2026-12-13 | 2026-11-28 | 2026-12-13 | 0% | 0% | 8 | No
MS.CO.P2.RB.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-11-26 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.100 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 02 | 2026-11-28 | 2026-12-02 | 2026-11-28 | 2026-12-02 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.105 | B1 - Columns Concreting work | 6 | Not Started | Con.Phase 04 | 2026-11-24 | 2026-11-30 | 2026-11-28 | 2026-12-03 | 0% | 0% | 1 | No
MS.CO.F4.B1.205 | B1 - Walls Concreting work | 6 | Not Started | Con.Phase 04 | 2026-11-24 | 2026-11-30 | 2026-11-28 | 2026-12-03 | 0% | 0% | 1 | No
MS.CO.P1.FAH.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-25 | 2026-11-29 | 2026-11-29 | 2026-12-02 | 0% | 0% | 1 | No
MS.CO.P1.FAG.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.126 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-11-28 | 2026-12-01 | 2026-11-29 | 2026-12-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.126 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 2026-11-29 | 0% | 0% | 5 | No
MS.CO.P2.FBC.101 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 02 | 2026-11-29 | 2026-12-03 | 2026-11-29 | 2026-12-03 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.129 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2026-11-29 | 2026-11-30 | 2026-11-29 | 2026-11-30 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-26 | 2026-11-26 | 2026-11-29 | 2026-11-29 | 0% | 0% | 1 | No
MS.CO.P2.B2.133 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-11-29 | 2026-11-30 | 2026-11-29 | 2026-11-30 | 0% | 0% | 20 | No
MS.CO.P1.FAG.123 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-11-30 | 2026-12-05 | 2026-11-30 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-29 | 2026-12-03 | 2026-11-30 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-11-30 | 2026-12-05 | 2026-11-30 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-11-30 | 2026-12-03 | 2026-11-30 | 2026-12-03 | 0% | 0% | 9 | No
MS.CO.P2.FBC.102 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 02 | 2026-11-30 | 2026-12-05 | 2026-11-30 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.114 | Beams and Slab Formwork | 12 | Not Started | Con.Phase 04 | 2026-11-26 | 2026-12-09 | 2026-11-30 | 2026-12-13 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-11-28 | 2026-12-01 | 2026-11-30 | 2026-12-03 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-26 | 2026-11-26 | 2026-11-30 | 2026-11-30 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.110 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-28 | 2026-12-02 | 2026-11-30 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.110 | B1 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 0% | 0% | 2 | No
MS.CO.P1.FAI.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-25 | 2026-11-25 | 2026-12-01 | 2026-12-01 | 0% | 0% | -2 | Yes
MS.CO.P2.HO.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-01 | 2026-12-05 | 2026-12-01 | 2026-12-05 | 0% | 0% | 9 | No
MS.CO.P2.FBC.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-12-01 | 2026-12-06 | 2026-12-01 | 2026-12-06 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.115 | External Block Work | 12 | Not Started | Con.Phase 05 | 2026-12-01 | 2026-12-14 | 2026-12-01 | 2026-12-14 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-11-28 | 2026-12-01 | 2026-12-01 | 2026-12-05 | 0% | 0% | 1 | No
MS.CO.P1.FAI.123 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-11-26 | 2026-11-30 | 2026-12-02 | 2026-12-06 | 0% | 0% | -1 | Yes
MS.CO.P1.FAG.124 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-02 | 2026-12-07 | 2026-12-02 | 2026-12-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.125 | Beams and Slab Steel Fix | 10 | Not Started | Con.Phase 02 | 2026-12-02 | 2026-12-13 | 2026-12-02 | 2026-12-13 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-02 | 2026-12-06 | 2026-12-02 | 2026-12-06 | 0% | 0% | 9 | No
MS.CO.P2.RB.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-01 | 2026-12-01 | 2026-12-02 | 2026-12-02 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.124 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-02 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.131 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-12-02 | 2026-12-05 | 2026-12-02 | 2026-12-05 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.114 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-11-30 | 2026-12-03 | 2026-12-02 | 2026-12-06 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.111 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-11-30 | 2026-12-05 | 2026-12-02 | 2026-12-07 | 0% | 0% | 3 | No
MS.CO.P1.FAH.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-11-30 | 2026-11-30 | 2026-12-03 | 2026-12-03 | 0% | 0% | 1 | No
MS.CO.P2.RB.106 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 02 | 2026-12-02 | 2026-12-07 | 2026-12-03 | 2026-12-08 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.100 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 04 | 2026-12-01 | 2026-12-03 | 2026-12-03 | 2026-12-06 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.132 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-03 | 2026-12-06 | 2026-12-03 | 2026-12-06 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.114 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-11-30 | 2026-12-03 | 2026-12-03 | 2026-12-07 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.116 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2026-12-03 | 2026-12-12 | 2026-12-03 | 2026-12-12 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-03 | 2026-12-04 | 2026-12-03 | 2026-12-04 | 0% | 0% | 3 | No
MS.CO.P3(1).FAN.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-11-30 | 2026-12-01 | 2026-12-03 | 2026-12-04 | 0% | 0% | 5 | No
MS.CO.P3(1).FAM.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.111 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 0% | 0% | 45 | No
MS.CO.P1.FAI.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-11-29 | 2026-12-02 | 2026-12-05 | 2026-12-08 | 0% | 0% | -1 | Yes
MS.CO.P1.FAH.132 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-12-01 | 2026-12-06 | 2026-12-05 | 2026-12-09 | 0% | 0% | 1 | No
MS.CO.P1.FAG.126 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-12-05 | 2026-12-09 | 2026-12-05 | 2026-12-09 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.101 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 04 | 2026-12-02 | 2026-12-05 | 2026-12-05 | 2026-12-07 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.118 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2026-12-05 | 2026-12-17 | 2026-12-05 | 2026-12-17 | 0% | 0% | 7 | No
MS.CO.P5.FA.134 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-12-05 | 2026-12-07 | 2026-12-05 | 2026-12-07 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.115 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-12-02 | 2026-12-06 | 2026-12-05 | 2026-12-08 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.116 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-02 | 2026-12-17 | 2026-12-05 | 2026-12-20 | 0% | 0% | 6 | No
MS.CO.P1.FAF.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-05 | 2026-12-08 | 2026-12-06 | 2026-12-09 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-06 | 2026-12-09 | 2026-12-06 | 2026-12-09 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.102 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 04 | 2026-12-03 | 2026-12-06 | 2026-12-06 | 2026-12-08 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAM.116 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-05 | 2026-12-20 | 2026-12-06 | 2026-12-21 | 0% | 0% | 5 | No
MS.CO.P3(1).FAM.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 03 | 2026-12-05 | 2026-12-09 | 2026-12-06 | 2026-12-10 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.117 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-05 | 2026-12-20 | 2026-12-06 | 2026-12-21 | 0% | 0% | 39 | No
MS.CO.P3(2).FAL.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-03 | 2026-12-03 | 2026-12-06 | 2026-12-06 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.126 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-12-01 | 2026-12-05 | 2026-12-07 | 2026-12-10 | 0% | 0% | -1 | Yes
MS.CO.P1.FAH.133 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-03 | 2026-12-08 | 2026-12-07 | 2026-12-12 | 0% | 0% | 1 | No
MS.CO.P2.RB.107 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 02 | 2026-12-06 | 2026-12-10 | 2026-12-07 | 2026-12-12 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-07 | 2026-12-10 | 2026-12-07 | 2026-12-10 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.137 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-07 | 2026-12-09 | 2026-12-07 | 2026-12-09 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.113 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-05 | 2026-12-09 | 2026-12-07 | 2026-12-12 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-01 | 2026-12-02 | 2026-12-07 | 2026-12-08 | 0% | 0% | -2 | Yes
MS.CO.P2.B1.134 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-12-06 | 2026-12-07 | 2026-12-07 | 2026-12-08 | 0% | 0% | 4 | No
MS.CO.P2.B1.130 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-12-07 | 2026-12-08 | 2026-12-07 | 2026-12-08 | 0% | 0% | 5 | No
MS.CO.P1.FAI.116 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-08 | 2026-12-23 | 2026-12-08 | 2026-12-23 | 0% | 0% | 10 | No
MS.CO.P1.FAH.125 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-12-03 | 2026-12-26 | 2026-12-08 | 2026-12-30 | 0% | 0% | 8 | No
MS.CO.P1.FAG.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-08 | 2026-12-13 | 2026-12-08 | 2026-12-13 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.103 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 04 | 2026-12-06 | 2026-12-09 | 2026-12-08 | 2026-12-12 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAN.115 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-05 | 2026-12-05 | 2026-12-08 | 2026-12-08 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-06 | 2026-12-06 | 2026-12-08 | 2026-12-08 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.114 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-12-06 | 2026-12-10 | 2026-12-08 | 2026-12-13 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-04 | 2026-12-05 | 2026-12-08 | 2026-12-09 | 0% | 0% | 9 | No
MS.CO.P1.FAI.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-03 | 2026-12-08 | 2026-12-09 | 2026-12-14 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.135 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-12-06 | 2026-12-10 | 2026-12-09 | 2026-12-14 | 0% | 0% | 1 | No
MS.CO.P2.HO.110 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-09 | 2026-12-13 | 2026-12-09 | 2026-12-13 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.119 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-12-06 | 2026-12-12 | 2026-12-09 | 2026-12-15 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-12-07 | 2026-12-10 | 2026-12-09 | 2026-12-13 | 0% | 0% | 3 | No
MS.CO.P3(2).B2.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-09 | 2026-12-10 | 2026-12-09 | 2026-12-10 | 0% | 0% | 94 | No
MS.CO.P1.FAG.122 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-10 | 2026-12-26 | 2026-12-10 | 2026-12-26 | 0% | 0% | 8 | No
MS.CO.P1.FAF.125 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-09 | 2026-12-24 | 2026-12-10 | 2026-12-26 | 0% | 0% | 2 | No
MS.CO.P1.FAF.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-09 | 2026-12-09 | 2026-12-10 | 2026-12-10 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.125 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-12-10 | 2027-01-02 | 2026-12-10 | 2027-01-02 | 0% | 0% | 6 | No
MS.CO.P1.FAE.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-10 | 2026-12-10 | 2026-12-10 | 2026-12-10 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.108 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 02 | 2026-12-09 | 2026-12-14 | 2026-12-10 | 2026-12-15 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.138 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2026-12-10 | 2026-12-12 | 2026-12-10 | 2026-12-12 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.114 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-12-08 | 2026-12-12 | 2026-12-10 | 2026-12-14 | 0% | 0% | 3 | No
MS.CO.P5.FA.126 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-12-11 | 2026-12-12 | 2026-12-11 | 2026-12-12 | 0% | 0% | 14 | No
MS.CO.P3(1).FAO.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 0% | 0% | 16 | No
MS.CO.P1.FAH.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-08 | 2026-12-13 | 2026-12-12 | 2026-12-16 | 0% | 0% | 1 | No
MS.CO.P1.FAF.132 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-10 | 2026-12-14 | 2026-12-12 | 2026-12-15 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.132 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2026-12-12 | 2026-12-14 | 2026-12-12 | 2026-12-14 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-12 | 2026-12-12 | 2026-12-12 | 2026-12-12 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-12-10 | 2026-12-14 | 2026-12-12 | 2026-12-15 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.115 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-12-09 | 2026-12-13 | 2026-12-12 | 2026-12-15 | 0% | 0% | 3 | No
MS.CO.P1.FAE.133 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2026-12-13 | 2026-12-15 | 2026-12-13 | 2026-12-15 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-12-12 | 2026-12-16 | 2026-12-13 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-13 | 2026-12-16 | 2026-12-13 | 2026-12-16 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.104 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2026-12-10 | 2026-12-13 | 2026-12-13 | 2026-12-15 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-12-13 | 2026-12-13 | 2026-12-13 | 2026-12-13 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.116 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-12 | 2026-12-27 | 2026-12-13 | 2026-12-28 | 0% | 0% | 14 | No
MS.CO.P3(1).FAO.119 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-12-10 | 2026-12-16 | 2026-12-13 | 2026-12-19 | 0% | 0% | 3 | No
MS.CO.P3(2).B1.121 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-13 | 2026-12-17 | 2026-12-13 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.128 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2026-12-09 | 2026-12-10 | 2026-12-13 | 2026-12-14 | 0% | 0% | 13 | No
MS.CO.P1.FAI.122 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-14 | 2026-12-29 | 2026-12-14 | 2026-12-29 | 0% | 0% | 10 | No
MS.CO.P1.FAH.131 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-09 | 2026-12-24 | 2026-12-14 | 2026-12-29 | 0% | 0% | 4 | No
MS.CO.P1.FAG.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-14 | 2026-12-17 | 2026-12-14 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.133 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-12-13 | 2026-12-16 | 2026-12-14 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.127 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-14 | 2026-12-14 | 2026-12-14 | 2026-12-14 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.111 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2026-12-14 | 2026-12-16 | 2026-12-14 | 2026-12-16 | 0% | 0% | 4 | No
MS.CO.P2.FBC.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-14 | 2026-12-17 | 2026-12-14 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.117 | Beams and Slab Steel Fix | 7 | Not Started | Con.Phase 04 | 2026-12-10 | 2026-12-17 | 2026-12-14 | 2026-12-21 | 0% | 0% | 1 | No
MS.CO.P5.FA.140 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-12-14 | 2026-12-16 | 2026-12-14 | 2026-12-16 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.115 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-12 | 2026-12-12 | 2026-12-14 | 2026-12-14 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-13 | 2026-12-14 | 2026-12-14 | 2026-12-15 | 0% | 0% | 2 | No
MS.CO.P1.FAI.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-09 | 2026-12-13 | 2026-12-15 | 2026-12-19 | 0% | 0% | -2 | Yes
MS.CO.P2.FBC.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-15 | 2026-12-19 | 2026-12-15 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.100 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-15 | 2026-12-19 | 2026-12-15 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.124 | External Block Work | 10 | Not Started | Con.Phase 05 | 2026-12-15 | 2026-12-26 | 2026-12-15 | 2026-12-26 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.141 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-15 | 2026-12-17 | 2026-12-15 | 2026-12-17 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.118 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2026-12-13 | 2027-01-04 | 2026-12-15 | 2027-01-06 | 0% | 0% | 6 | No
MS.CO.P3(2).FAL.116 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2026-12-13 | 2026-12-21 | 2026-12-15 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-15 | 2026-12-16 | 2026-12-15 | 2026-12-16 | 0% | 0% | 13 | No
MS.CO.P1.FAF.131 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-15 | 2026-12-30 | 2026-12-16 | 2026-12-31 | 0% | 0% | 2 | No
MS.CO.P1.FAF.135 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-12-15 | 2026-12-19 | 2026-12-16 | 2026-12-20 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.135 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.110 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-16 | 2026-12-20 | 2026-12-16 | 2026-12-20 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2026-12-16 | 0% | 0% | -1 | Yes
MS.CO.P5.FA.143 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-12-16 | 2026-12-19 | 2026-12-16 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.118 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2026-12-15 | 2027-01-06 | 2026-12-16 | 2027-01-07 | 0% | 0% | 5 | No
MS.CO.P3(1).FAM.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-15 | 2026-12-15 | 2026-12-16 | 2026-12-16 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.120 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-13 | 2026-12-17 | 2026-12-16 | 2026-12-21 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.121 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2026-12-15 | 2027-01-06 | 2026-12-16 | 2027-01-07 | 0% | 0% | 63 | No
MS.CO.P1.FAH.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-14 | 2026-12-17 | 2026-12-17 | 2026-12-21 | 0% | 0% | 1 | No
MS.CO.P1.FAF.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-16 | 2026-12-21 | 2026-12-17 | 2026-12-22 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.131 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-17 | 2027-01-02 | 2026-12-17 | 2027-01-02 | 0% | 0% | 11 | No
MS.CO.P1.FAE.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-17 | 2026-12-22 | 2026-12-17 | 2026-12-22 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 0% | 0% | 4 | No
MS.CO.P2.FBR.101 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-17 | 2026-12-21 | 2026-12-17 | 2026-12-21 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.106 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.122 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-12-16 | 2026-12-20 | 2026-12-17 | 2026-12-21 | 0% | 0% | 2 | No
MS.CO.P1.FAG.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-19 | 2026-12-19 | 2026-12-19 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.114 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-19 | 2026-12-22 | 2026-12-19 | 2026-12-22 | 0% | 0% | 4 | No
MS.CO.P2.RB.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-17 | 2026-12-21 | 2026-12-19 | 2026-12-22 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.107 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2026-12-16 | 2026-12-17 | 2026-12-19 | 2026-12-20 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.146 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-19 | 2026-12-21 | 2026-12-19 | 2026-12-21 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.122 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-19 | 2026-12-19 | 2026-12-19 | 2026-12-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1)MQ.100 | GF- Columns & Walls Formwork, Steel & Concreting work | 7 | Not Started | Con.Phase 03 | 2026-12-20 | 2026-12-27 | 2026-12-20 | 2026-12-27 | 0% | 0% | 2 | No
MS.CO.P1.FAI.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-14 | 2026-12-14 | 2026-12-20 | 2026-12-20 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.132 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-12-20 | 2026-12-24 | 2026-12-20 | 2026-12-24 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.116 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-20 | 2026-12-23 | 2026-12-20 | 2026-12-23 | 0% | 0% | 4 | No
MS.CO.P2.FBR.102 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-20 | 2026-12-23 | 2026-12-20 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.123 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-12-19 | 2026-12-22 | 2026-12-20 | 2026-12-23 | 0% | 0% | 2 | No
MS.CO.P3(1).FAO.120 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-17 | 2026-12-22 | 2026-12-20 | 2026-12-24 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.100 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2026-12-20 | 2026-12-21 | 2026-12-20 | 2026-12-21 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-12-20 | 2026-12-21 | 2026-12-20 | 2026-12-21 | 0% | 0% | 89 | No
MS.CO.P1.FAI.132 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-15 | 2026-12-19 | 2026-12-21 | 2026-12-24 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.125 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-21 | 2027-01-05 | 2026-12-21 | 2027-01-05 | 0% | 0% | 11 | No
MS.CO.P2.HO.117 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-21 | 2026-12-24 | 2026-12-21 | 2026-12-24 | 0% | 0% | 4 | No
MS.CO.P2.FBC.111 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2026-12-21 | 2026-12-23 | 2026-12-21 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-12-21 | 2026-12-26 | 2026-12-21 | 2026-12-26 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.108 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.101 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2026-12-21 | 2026-12-22 | 2026-12-21 | 2026-12-22 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.260 | Excavation for drop Panels and Trenches | 2 | Not Started | Con.Phase 02 | 2026-12-21 | 2026-12-22 | 2026-12-21 | 2026-12-22 | 0% | 0% | 6 | No
MS.CO.P1.FAH.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-19 | 2026-12-19 | 2026-12-22 | 2026-12-22 | 0% | 0% | 1 | No
MS.CO.P1.FAG.133 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-22 | 2026-12-27 | 2026-12-22 | 2026-12-27 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.119 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-22 | 2026-12-26 | 2026-12-22 | 2026-12-26 | 0% | 0% | 4 | No
MS.CO.F4.B1.118 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-12-19 | 2026-12-19 | 2026-12-22 | 2026-12-22 | 0% | 0% | 1 | No
MS.CO.P5.FA.147 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2026-12-22 | 2026-12-23 | 2026-12-22 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.124 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-12-21 | 2026-12-24 | 2026-12-22 | 2026-12-26 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-19 | 2026-12-19 | 2026-12-22 | 2026-12-22 | 0% | 0% | 1 | No
MS.CO.P1.FAG.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-22 | 2026-12-23 | 2026-12-22 | 2026-12-23 | 0% | 0% | 12 | No
MS.CO.P2.HO.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-12-22 | 2026-12-23 | 2026-12-22 | 2026-12-23 | 0% | 0% | 6 | No
MS.CO.P3(1).FAM.117 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 0% | 0% | 3 | No
MS.CO.P1.FAI.133 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-12-17 | 2026-12-21 | 2026-12-23 | 2026-12-27 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.141 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2026-12-20 | 2026-12-24 | 2026-12-23 | 2026-12-28 | 0% | 0% | 1 | No
MS.CO.P1.FAF.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-22 | 2026-12-26 | 2026-12-23 | 2026-12-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-23 | 2026-12-27 | 2026-12-23 | 2026-12-27 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-22 | 2026-12-22 | 2026-12-23 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.100 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 04 | 2026-12-20 | 2026-12-23 | 2026-12-23 | 2026-12-27 | 0% | 0% | 1 | No
MS.CO.F4.FCD.110 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2026-12-21 | 2026-12-23 | 2026-12-23 | 2026-12-26 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.122 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-20 | 2026-12-24 | 2026-12-23 | 2026-12-28 | 0% | 0% | 3 | No
MS.CO.P3(1).FAO.117 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2026-12-22 | 2027-01-13 | 2026-12-23 | 2027-01-14 | 0% | 0% | 15 | No
MS.CO.P3(2).FAK.102 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.500 | Earthing and Lightning Protection System | 1 | Not Started | Con.Phase 02 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 0% | 0% | 6 | No
MS.CO.P3(1).FAN.117 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-20 | 2026-12-21 | 2026-12-23 | 2026-12-24 | 0% | 0% | 5 | No
MS.CO.P2.HO.113 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2026-12-24 | 2027-01-09 | 2026-12-24 | 2027-01-09 | 0% | 0% | 5 | No
MS.CO.P1.FAI.125 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-24 | 2027-01-09 | 2026-12-24 | 2027-01-09 | 0% | 0% | 10 | No
MS.CO.P1.FAG.135 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-12-24 | 2026-12-29 | 2026-12-24 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-23 | 2026-12-27 | 2026-12-24 | 2026-12-28 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.101 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 04 | 2026-12-21 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 0% | 0% | 1 | No
MS.CO.P5.FA.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.125 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-22 | 2027-01-06 | 2026-12-24 | 2027-01-09 | 0% | 0% | 7 | No
MS.CO.P3(1).FAM.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 03 | 2026-12-23 | 2026-12-28 | 2026-12-24 | 2026-12-29 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.123 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-12-21 | 2026-12-26 | 2026-12-24 | 2026-12-29 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.118 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-22 | 2026-12-27 | 2026-12-24 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.103 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2026-12-24 | 2026-12-27 | 2026-12-24 | 2026-12-27 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.270 | Blinding concrete for lower Part of Foundation | 1 | Not Started | Con.Phase 02 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0% | 0% | 6 | No
MS.CO.P1.FAI.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-18 | 2026-12-19 | 2026-12-24 | 2026-12-25 | 0% | 0% | -2 | Yes
MS.CO.P5.FA.135 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2026-12-24 | 2026-12-25 | 2026-12-24 | 2026-12-25 | 0% | 0% | 15 | No
MS.CO.P2.RB.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2026-12-24 | 2026-12-25 | 2026-12-25 | 2026-12-26 | 0% | 0% | 3 | No
MS.CO.F4.B1.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 0% | 0% | 64 | No
MS.CO.P1.FAI.135 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2026-12-20 | 2026-12-23 | 2026-12-26 | 2026-12-29 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.142 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-22 | 2026-12-27 | 2026-12-26 | 2026-12-30 | 0% | 0% | 1 | No
MS.CO.P2.FBC.114 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-26 | 2026-12-29 | 2026-12-26 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.102 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 04 | 2026-12-22 | 2026-12-26 | 2026-12-26 | 2026-12-29 | 0% | 0% | 1 | No
MS.CO.P5.FA.127 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2026-12-26 | 2027-01-07 | 2026-12-26 | 2027-01-07 | 0% | 0% | 1 | No
MS.CO.P5.FA.149 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2026-12-26 | 2026-12-28 | 2026-12-26 | 2026-12-28 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.125 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-22 | 2027-01-06 | 2026-12-26 | 2027-01-10 | 0% | 0% | 8 | No
MS.CO.P3(1).FAN.124 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 03 | 2026-12-22 | 2026-12-27 | 2026-12-26 | 2026-12-30 | 0% | 0% | 3 | No
MS.CO.P3(1).FAO.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-23 | 2026-12-23 | 2026-12-26 | 2026-12-26 | 0% | 0% | 3 | No
MS.CO.P2.FO.280 | Block work for Drop Panels | 1 | Not Started | Con.Phase 02 | 2026-12-26 | 2026-12-26 | 2026-12-26 | 2026-12-26 | 0% | 0% | 6 | No
MS.CO.P1.FAI.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-21 | 2026-12-26 | 2026-12-27 | 2026-12-31 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.131 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-27 | 2027-01-11 | 2026-12-27 | 2027-01-11 | 0% | 0% | 8 | No
MS.CO.P1.FAF.134 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-26 | 2027-01-10 | 2026-12-27 | 2027-01-11 | 0% | 0% | 2 | No
MS.CO.P2.HO.120 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2026-12-27 | 2026-12-29 | 2026-12-27 | 2026-12-29 | 0% | 0% | 4 | No
MS.CO.P2.RB.114 | GF - External Block Work | 20 | Not Started | Con.Phase 02 | 2026-12-26 | 2027-01-17 | 2026-12-27 | 2027-01-18 | 0% | 0% | 3 | No
MS.CO.P2.RB.115 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-26 | 2026-12-29 | 2026-12-27 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.115 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-27 | 2026-12-30 | 2026-12-27 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-27 | 2026-12-30 | 2026-12-27 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.103 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 04 | 2026-12-23 | 2026-12-28 | 2026-12-27 | 2026-12-31 | 0% | 0% | 1 | No
MS.CO.F4.FCD.111 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2026-12-24 | 2026-12-27 | 2026-12-27 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.133 | External Block Work | 12 | Not Started | Con.Phase 05 | 2026-12-27 | 2027-01-09 | 2026-12-27 | 2027-01-09 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.150 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-27 | 2026-12-29 | 2026-12-27 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.128 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-12-23 | 2026-12-29 | 2026-12-27 | 2027-01-02 | 0% | 0% | 3 | No
MS.CO.P3(1).FAO.122 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-12-24 | 2026-12-28 | 2026-12-27 | 2026-12-30 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.104 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2026-12-27 | 2026-12-29 | 2026-12-27 | 2026-12-29 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.290 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 02 | 2026-12-27 | 2026-12-27 | 2026-12-27 | 2026-12-27 | 0% | 0% | 6 | No
MS.CO.P1.FAH.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2026-12-23 | 2026-12-24 | 2026-12-27 | 2026-12-28 | 0% | 0% | 6 | No
MS.CO.P3(1)MQ.101 | GF- Slabs & Beams Formwork, Steel Fix & Concreting Work | 12 | Not Started | Con.Phase 03 | 2026-12-28 | 2027-01-10 | 2026-12-28 | 2027-01-10 | 0% | 0% | 2 | No
MS.CO.P1.FAH.144 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2026-12-24 | 2026-12-29 | 2026-12-28 | 2027-01-02 | 0% | 0% | 1 | No
MS.CO.P1.FAG.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-28 | 2027-01-02 | 2026-12-28 | 2027-01-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-27 | 2026-12-27 | 2026-12-28 | 2026-12-28 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.117 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-28 | 2026-12-31 | 2026-12-28 | 2026-12-31 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.152 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2026-12-28 | 2026-12-30 | 2026-12-28 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.300 | Surface preparation and Angle filet at RW Edge | 1 | Not Started | Con.Phase 02 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 0% | 0% | 6 | No
MS.CO.P1.FAF.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-28 | 2026-12-31 | 2026-12-29 | 2027-01-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.141 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2026-12-29 | 2026-12-31 | 2026-12-29 | 2026-12-31 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.116 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2026-12-28 | 2026-12-31 | 2026-12-29 | 2027-01-02 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.119 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2026-12-29 | 2027-01-02 | 2026-12-29 | 2027-01-02 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.155 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2026-12-29 | 2026-12-31 | 2026-12-29 | 2026-12-31 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.123 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2026-12-27 | 2026-12-30 | 2026-12-29 | 2027-01-02 | 0% | 0% | 3 | No
MS.CO.P2.FO.310 | Water Proofing Membrane under Raft Foundation | 2 | Not Started | Con.Phase 02 | 2026-12-29 | 2026-12-30 | 2026-12-29 | 2026-12-30 | 0% | 0% | 6 | No
MS.CO.P3(2).FAL.119 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 0% | 0% | 36 | No
MS.CO.P1.FAI.131 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-30 | 2027-01-14 | 2026-12-30 | 2027-01-14 | 0% | 0% | 10 | No
MS.CO.P1.FAH.140 | External Block Work | 14 | Not Started | Con.Phase 01 | 2026-12-26 | 2027-01-10 | 2026-12-30 | 2027-01-14 | 0% | 0% | 4 | No
MS.CO.P1.FAH.146 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2026-12-27 | 2026-12-31 | 2026-12-30 | 2027-01-04 | 0% | 0% | 1 | No
MS.CO.P2.HO.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-30 | 0% | 0% | 4 | No
MS.CO.P2.RB.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2026-12-29 | 2027-01-03 | 2026-12-30 | 2027-01-04 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 03 | 2026-12-29 | 2027-01-02 | 2026-12-30 | 2027-01-03 | 0% | 0% | 2 | No
MS.CO.P3(2).FAL.120 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-30 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.590 | Earthing and Lightning Protection System | 1 | Not Started | Con.Phase 04 | 2026-12-27 | 2026-12-27 | 2026-12-30 | 2026-12-30 | 0% | 0% | 1 | No
MS.CO.P1.FAH.134 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2026-12-27 | 2027-01-18 | 2026-12-31 | 2027-01-23 | 0% | 0% | 8 | No
MS.CO.P1.FAF.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2026-12-30 | 2027-01-03 | 2026-12-31 | 2027-01-04 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.112 | Rebars for 1st layer for Foundation | 2 | Not Started | Con.Phase 02 | 2026-12-31 | 2027-01-02 | 2026-12-31 | 2027-01-02 | 0% | 0% | 6 | No
MS.CO.P2.HO.123 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2026-12-31 | 2027-01-04 | 2026-12-31 | 2027-01-04 | 0% | 0% | 4 | No
MS.CO.P2.FBR.105 | Beams and Slab Concreting work | 7 | Not Started | Con.Phase 02 | 2026-12-31 | 2027-01-07 | 2026-12-31 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.114 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-02 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.124 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2026-12-29 | 2027-01-02 | 2026-12-31 | 2027-01-04 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.126 | External Block Work | 14 | Not Started | Con.Phase 03 | 2026-12-29 | 2027-01-13 | 2026-12-31 | 2027-01-16 | 0% | 0% | 31 | No
MS.CO.P3(2).FAL.122 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-29 | 2027-01-03 | 2026-12-31 | 2027-01-05 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.190 | Blinding concrete for lower Part of Foundation | 1 | Not Started | Con.Phase 04 | 2026-12-28 | 2026-12-28 | 2026-12-31 | 2026-12-31 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.194 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2026-12-31 | 2027-01-02 | 2026-12-31 | 2027-01-02 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 0% | 0% | 12 | No
MS.CO.P1.FAF.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-01 | 2027-01-02 | 2027-01-01 | 2027-01-02 | 0% | 0% | 2 | No
MS.CO.P1.FAI.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2026-12-27 | 2026-12-30 | 2027-01-02 | 2027-01-05 | 0% | 0% | -2 | Yes
MS.CO.P1.FAE.142 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2027-01-02 | 2027-01-04 | 2027-01-02 | 2027-01-04 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.125 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-02 | 2027-01-05 | 2027-01-02 | 2027-01-05 | 0% | 0% | 4 | No
MS.CO.F4.FCQ.104 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 04 | 2026-12-29 | 2027-01-02 | 2027-01-02 | 2027-01-05 | 0% | 0% | 1 | No
MS.CO.F4.FCD.115 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2026-12-30 | 2026-12-31 | 2027-01-02 | 2027-01-03 | 0% | 0% | 1 | No
MS.CO.P5.FA.156 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-01-02 | 2027-01-03 | 2027-01-02 | 2027-01-03 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.125 | External Block Work | 12 | Not Started | Con.Phase 03 | 2026-12-31 | 2027-01-13 | 2027-01-02 | 2027-01-14 | 0% | 0% | 11 | No
MS.CO.P3(1).FAO.128 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2026-12-30 | 2027-01-05 | 2027-01-02 | 2027-01-07 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.123 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2026-12-30 | 2027-01-04 | 2027-01-02 | 2027-01-06 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.200 | Block work for Drop Panels | 1 | Not Started | Con.Phase 04 | 2026-12-29 | 2026-12-29 | 2027-01-02 | 2027-01-02 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.184 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-01-02 | 2027-01-03 | 2027-01-02 | 2027-01-03 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-03 | 2027-01-06 | 2027-01-03 | 2027-01-06 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.140 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-03 | 2027-01-18 | 2027-01-03 | 2027-01-18 | 0% | 0% | 2 | No
MS.CO.P1.FAE.134 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2027-01-03 | 2027-01-25 | 2027-01-03 | 2027-01-25 | 0% | 0% | 6 | No
MS.CO.P2.FO.117 | Installation for Mechanical and Electrical Embeds | 1 | Not Started | Con.Phase 02 | 2027-01-03 | 2027-01-03 | 2027-01-03 | 2027-01-03 | 0% | 0% | 6 | No
MS.CO.P2.HO.126 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-03 | 2027-01-06 | 2027-01-03 | 2027-01-06 | 0% | 0% | 4 | No
MS.CO.P2.FBC.120 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-03 | 2027-01-05 | 2027-01-03 | 2027-01-05 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.129 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2026-12-30 | 2027-01-04 | 2027-01-03 | 2027-01-07 | 0% | 0% | 3 | No
MS.CO.F4.FO.210 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 04 | 2026-12-30 | 2026-12-30 | 2027-01-03 | 2027-01-03 | 0% | 0% | 1 | No
MS.CO.P1.FAE.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-03 | 2027-01-04 | 2027-01-03 | 2027-01-04 | 0% | 0% | 13 | No
MS.CO.P2.HO.115 | GF - Internal Block Work | 20 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-26 | 2027-01-04 | 2027-01-26 | 0% | 0% | 5 | No
MS.CO.P2.FO.120 | Formwork for Foundations | 1 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 0% | 0% | 6 | No
MS.CO.P2.FO.123 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 1 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 0% | 0% | 6 | No
MS.CO.P2.HO.128 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-07 | 2027-01-04 | 2027-01-07 | 0% | 0% | 4 | No
MS.CO.F4.FCD.117 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2027-01-02 | 2027-01-03 | 2027-01-04 | 2027-01-05 | 0% | 0% | 1 | No
MS.CO.P5.FA.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-03 | 2027-01-03 | 2027-01-04 | 2027-01-04 | 0% | 0% | 2 | No
MS.CO.F4.FO.220 | Water Proofing Membrane under Raft Foundation | 2 | Not Started | Con.Phase 04 | 2026-12-31 | 2027-01-02 | 2027-01-04 | 2027-01-05 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.204 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-05 | 2027-01-04 | 2027-01-05 | 0% | 0% | 2 | No
MS.CO.P1.FAH.147 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-02 | 2027-01-05 | 2027-01-05 | 2027-01-09 | 0% | 0% | 1 | No
MS.CO.P1.FAF.144 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-05 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.140 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-05 | 2027-01-20 | 2027-01-05 | 2027-01-20 | 0% | 0% | 11 | No
MS.CO.P1.FAE.144 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 01 | 2027-01-05 | 2027-01-07 | 2027-01-05 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.P2.FO.127 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 02 | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-05 | 0% | 0% | 6 | No
MS.CO.P2.RB.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-04 | 2027-01-07 | 2027-01-05 | 2027-01-09 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.119 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-01-03 | 2027-01-05 | 2027-01-05 | 2027-01-07 | 0% | 0% | 1 | No
MS.CO.P5.FA.158 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2027-01-05 | 2027-01-07 | 2027-01-05 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.131 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2027-01-04 | 2027-01-07 | 2027-01-05 | 2027-01-09 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.214 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-01-05 | 2027-01-07 | 2027-01-05 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.144 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0% | 0% | 17 | No
MS.CO.P1.FAI.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2026-12-31 | 2026-12-31 | 2027-01-06 | 2027-01-06 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.134 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-06 | 2027-01-21 | 2027-01-06 | 2027-01-21 | 0% | 0% | 11 | No
MS.CO.P1.FAF.146 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-05 | 2027-01-10 | 2027-01-06 | 2027-01-11 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.105 | B3 - Columns Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% | 0% | 6 | No
MS.CO.P2.RB.117 | GF - Internal Block Work | 20 | Not Started | Con.Phase 02 | 2027-01-05 | 2027-01-27 | 2027-01-06 | 2027-01-28 | 0% | 0% | 3 | No
MS.CO.P2.FBC.113 | External Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-06 | 2027-01-21 | 2027-01-06 | 2027-01-21 | 0% | 0% | 2 | No
MS.CO.P2.FBC.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.101 | Rebars for 1st layer for Foundation | 3 | Not Started | Con.Phase 04 | 2027-01-03 | 2027-01-05 | 2027-01-06 | 2027-01-09 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.105 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-03 | 2027-01-03 | 2027-01-06 | 2027-01-06 | 0% | 0% | 1 | No
MS.CO.P5.FA.159 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2027-01-06 | 2027-01-09 | 2027-01-06 | 2027-01-09 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.132 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2027-01-05 | 2027-01-09 | 2027-01-06 | 2027-01-10 | 0% | 0% | 2 | No
MS.CO.P2.B3.205 | B3 - Walls Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% | 0% | 7 | No
MS.CO.P2.B1.133 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-06 | 2027-01-07 | 2027-01-06 | 2027-01-07 | 0% | 0% | 4 | No
MS.CO.P1.FAI.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-02 | 2027-01-05 | 2027-01-07 | 2027-01-11 | 0% | 0% | -2 | Yes
MS.CO.P1.FAG.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.146 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-07 | 2027-01-12 | 2027-01-07 | 2027-01-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.109 | B3 - Columns Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 0% | 0% | 6 | No
MS.CO.P2.FBC.123 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-07 | 2027-01-11 | 2027-01-07 | 2027-01-11 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 04 | 2027-01-04 | 2027-01-07 | 2027-01-07 | 2027-01-11 | 0% | 0% | 1 | No
MS.CO.P5.FA.161 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2027-01-07 | 2027-01-10 | 2027-01-07 | 2027-01-10 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.126 | Internal Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-05 | 2027-01-20 | 2027-01-07 | 2027-01-23 | 0% | 0% | 6 | No
MS.CO.P3(2).FAL.124 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-05 | 2027-01-05 | 2027-01-07 | 2027-01-07 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.209 | B3 - Walls Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 0% | 0% | 7 | No
MS.CO.P3(2).FAK.224 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-01-07 | 2027-01-10 | 2027-01-07 | 2027-01-10 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-01-06 | 2027-01-07 | 2027-01-07 | 2027-01-08 | 0% | 0% | -1 | Yes
MS.CO.P3(1).FAM.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-07 | 2027-01-08 | 2027-01-08 | 2027-01-09 | 0% | 0% | 2 | No
MS.CO.P1.FAG.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-09 | 2027-01-12 | 2027-01-09 | 2027-01-12 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.112 | B3 - Columns Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-09 | 2027-01-09 | 2027-01-09 | 0% | 0% | 6 | No
MS.CO.P2.HO.129 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-11 | 2027-01-09 | 2027-01-11 | 0% | 0% | 4 | No
MS.CO.P2.FBC.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-12 | 2027-01-09 | 2027-01-12 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.106 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-12 | 2027-01-09 | 2027-01-12 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 04 | 2027-01-05 | 2027-01-09 | 2027-01-09 | 2027-01-12 | 0% | 0% | 1 | No
MS.CO.F4.FCD.113 | External Block Work | 14 | Not Started | Con.Phase 04 | 2027-01-09 | 2027-01-24 | 2027-01-09 | 2027-01-24 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.120 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-01-06 | 2027-01-09 | 2027-01-09 | 2027-01-11 | 0% | 0% | 1 | No
MS.CO.P5.FA.136 | Internal Block Work | 14 | Not Started | Con.Phase 05 | 2027-01-09 | 2027-01-24 | 2027-01-09 | 2027-01-24 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.126 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2027-01-07 | 2027-01-30 | 2027-01-09 | 2027-01-31 | 0% | 0% | 5 | No
MS.CO.P3(1).FAM.133 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2027-01-07 | 2027-01-11 | 2027-01-09 | 2027-01-12 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-05 | 2027-01-05 | 2027-01-09 | 2027-01-09 | 0% | 0% | 3 | No
MS.CO.P3(1).FAO.129 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2027-01-06 | 2027-01-11 | 2027-01-09 | 2027-01-13 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.125 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2027-01-06 | 2027-01-14 | 2027-01-09 | 2027-01-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.212 | B3 - Walls Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-09 | 2027-01-09 | 2027-01-09 | 0% | 0% | 7 | No
MS.CO.P3(2).FO.189 | Excavation for drop Panels and Trenches | 3 | Not Started | Con.Phase 03 | 2027-01-09 | 2027-01-11 | 2027-01-09 | 2027-01-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.134 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-10 | 2027-01-25 | 2027-01-10 | 2027-01-25 | 0% | 0% | 10 | No
MS.CO.P1.FAI.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2027-01-04 | 2027-01-07 | 2027-01-10 | 2027-01-13 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-06 | 2027-01-06 | 2027-01-10 | 2027-01-10 | 0% | 0% | 1 | No
MS.CO.P1.FAG.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2027-01-10 | 2027-01-13 | 2027-01-10 | 2027-01-13 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.118 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 02 | 2027-01-10 | 2027-01-12 | 2027-01-10 | 2027-01-12 | 0% | 0% | 6 | No
MS.CO.P2.RB.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-09 | 2027-01-09 | 2027-01-10 | 2027-01-10 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.126 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-10 | 2027-01-13 | 2027-01-10 | 2027-01-13 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.107 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-10 | 2027-01-13 | 2027-01-10 | 2027-01-13 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.102 | Installation for Mechanical and Electrical Embeds | 1 | Not Started | Con.Phase 04 | 2027-01-06 | 2027-01-06 | 2027-01-10 | 2027-01-10 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 04 | 2027-01-06 | 2027-01-10 | 2027-01-10 | 2027-01-13 | 0% | 0% | 1 | No
MS.CO.P5.FA.142 | External Block Work | 12 | Not Started | Con.Phase 05 | 2027-01-10 | 2027-01-23 | 2027-01-10 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.134 | External Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-09 | 2027-01-24 | 2027-01-10 | 2027-01-25 | 0% | 0% | 7 | No
MS.CO.P3(1).FAM.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 03 | 2027-01-09 | 2027-01-13 | 2027-01-10 | 2027-01-14 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.131 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2027-01-06 | 2027-01-10 | 2027-01-10 | 2027-01-13 | 0% | 0% | 3 | No
MS.CO.P2.HO.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-10 | 2027-01-11 | 2027-01-10 | 2027-01-11 | 0% | 0% | 10 | No
MS.CO.P3(1)MQ.102 | GF- Slabs & Beams DE shuttering Work | 18 | Not Started | Con.Phase 03 | 2027-01-11 | 2027-01-31 | 2027-01-11 | 2027-01-31 | 0% | 0% | 26 | No
MS.CO.P3(1)MQ.103 | FF- Columns & Walls Formwork, steel Fix & Concreting work | 7 | Not Started | Con.Phase 03 | 2027-01-11 | 2027-01-18 | 2027-01-11 | 2027-01-18 | 0% | 0% | 2 | No
MS.CO.P2.B2.135 | B2 - Block Works | 33 | Not Started | Con.Phase 02 | 2027-01-11 | 2027-02-18 | 2027-01-11 | 2027-02-21 | 0% | 0% | 28 | No
MS.CO.P1.FAH.150 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2027-01-07 | 2027-01-12 | 2027-01-11 | 2027-01-16 | 0% | 0% | 1 | No
MS.CO.P2.RB.123 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-10 | 2027-01-13 | 2027-01-11 | 2027-01-14 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.128 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-11 | 2027-01-14 | 2027-01-11 | 2027-01-14 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.108 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-11 | 2027-01-14 | 2027-01-11 | 2027-01-14 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.103 | Formwork for Foundations | 1 | Not Started | Con.Phase 04 | 2027-01-07 | 2027-01-07 | 2027-01-11 | 2027-01-11 | 0% | 0% | 1 | No
MS.CO.F4.FO.104 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 1 | Not Started | Con.Phase 04 | 2027-01-07 | 2027-01-07 | 2027-01-11 | 2027-01-11 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 04 | 2027-01-07 | 2027-01-12 | 2027-01-11 | 2027-01-16 | 0% | 0% | 1 | No
MS.CO.P5.FA.164 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2027-01-11 | 2027-01-13 | 2027-01-11 | 2027-01-13 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.132 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2027-01-07 | 2027-01-11 | 2027-01-11 | 2027-01-14 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.130 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2027-01-09 | 2027-01-31 | 2027-01-11 | 2027-02-02 | 0% | 0% | 41 | No
MS.CO.P3(2).FAK.234 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-11 | 2027-01-11 | 2027-01-11 | 2027-01-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-11 | 2027-01-12 | 2027-01-11 | 2027-01-12 | 0% | 0% | 8 | No
MS.CO.P3(2).B1.131 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-11 | 2027-01-12 | 2027-01-11 | 2027-01-12 | 0% | 0% | 78 | No
MS.CO.P1.FAI.144 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2027-01-06 | 2027-01-10 | 2027-01-12 | 2027-01-16 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.151 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-10 | 2027-01-14 | 2027-01-12 | 2027-01-17 | 0% | 0% | 1 | No
MS.CO.P1.FAG.144 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2027-01-12 | 2027-01-16 | 2027-01-12 | 2027-01-16 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.143 | Internal Block Work | 20 | Not Started | Con.Phase 01 | 2027-01-13 | 2027-02-04 | 2027-01-12 | 2027-02-03 | 0% | 0% | 2 | No
MS.CO.P1.FAF.147 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-11 | 2027-01-14 | 2027-01-12 | 2027-01-16 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.122 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-12 | 2027-01-27 | 2027-01-12 | 2027-01-27 | 0% | 0% | 9 | No
MS.CO.P2.HO.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 0% | 0% | 4 | No
MS.CO.P2.FBR.110 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2027-01-12 | 2027-01-17 | 2027-01-12 | 2027-01-17 | 0% | 0% | 0 | Yes
MS.CO.F4.FO.105 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 04 | 2027-01-09 | 2027-01-09 | 2027-01-12 | 2027-01-12 | 0% | 0% | 1 | No
MS.CO.F4.FCD.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-10 | 2027-01-10 | 2027-01-12 | 2027-01-12 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.133 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2027-01-09 | 2027-01-12 | 2027-01-12 | 2027-01-16 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.106 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-01-12 | 2027-01-13 | 2027-01-12 | 2027-01-13 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.560 | Earthing and Lightning Protection System | 1 | Not Started | Con.Phase 03 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 0% | 0% | 3 | No
MS.CO.P3(2).FO.239 | Excavation for drop Panels and Trenches | 6 | Not Started | Con.Phase 03 | 2027-01-12 | 2027-01-18 | 2027-01-12 | 2027-01-18 | 0% | 0% | 0 | Yes
MS.CO.P1.FO.570 | Earthing and Lightning Protection System | 1 | Not Started | Con.Phase 03 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 0% | 0% | 6 | No
MS.CO.P1.FAI.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-06 | 2027-01-07 | 2027-01-12 | 2027-01-13 | 0% | 0% | 13 | No
MS.CO.P1.FAI.146 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-07 | 2027-01-12 | 2027-01-13 | 2027-01-18 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.153 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2027-01-12 | 2027-01-17 | 2027-01-13 | 2027-01-18 | 0% | 0% | 1 | No
MS.CO.P1.FAG.140 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-13 | 2027-01-28 | 2027-01-13 | 2027-01-28 | 0% | 0% | 7 | No
MS.CO.P1.FAE.147 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-13 | 2027-01-17 | 2027-01-13 | 2027-01-17 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.121 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-01-13 | 2027-01-14 | 2027-01-13 | 2027-01-14 | 0% | 0% | 6 | No
MS.CO.P2.HO.132 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-13 | 2027-01-17 | 2027-01-13 | 2027-01-17 | 0% | 0% | 4 | No
MS.CO.P2.RB.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-12 | 2027-01-16 | 2027-01-13 | 2027-01-17 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.100 | B3 - Columns Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-01-10 | 2027-01-10 | 2027-01-13 | 2027-01-13 | 0% | 0% | 1 | No
MS.CO.F4.FCD.123 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.107 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-01-13 | 2027-01-14 | 2027-01-13 | 2027-01-14 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.201 | B3 - Walls Formwork | 1 | Not Started | Con.Phase 04 | 2027-01-10 | 2027-01-10 | 2027-01-13 | 2027-01-13 | 0% | 0% | 8 | No
MS.CO.F4.B3.200 | B3 - Walls Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-01-10 | 2027-01-10 | 2027-01-13 | 2027-01-13 | 0% | 0% | 8 | No
MS.CO.P3(2).FO.199 | Blinding concrete for lower Part of Foundation | 1 | Not Started | Con.Phase 03 | 2027-01-13 | 2027-01-13 | 2027-01-13 | 2027-01-13 | 0% | 0% | 3 | No
MS.CO.P2.HO.133 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-14 | 2027-01-18 | 2027-01-14 | 2027-01-18 | 0% | 0% | 4 | No
MS.CO.F4.B3.101 | B3 - Columns Formwork | 1 | Not Started | Con.Phase 04 | 2027-01-11 | 2027-01-11 | 2027-01-14 | 2027-01-14 | 0% | 0% | 1 | No
MS.CO.F4.FCD.124 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-16 | 0% | 0% | 1 | No
MS.CO.P5.FA.165 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-01-14 | 2027-01-16 | 2027-01-14 | 2027-01-16 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-12 | 2027-01-12 | 2027-01-14 | 2027-01-14 | 0% | 0% | 3 | No
MS.CO.F4.B3.202 | B3 - Walls Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-11 | 2027-01-11 | 2027-01-14 | 2027-01-14 | 0% | 0% | 8 | No
MS.CO.P3(2).FO.209 | Block work for Drop Panels | 1 | Not Started | Con.Phase 03 | 2027-01-14 | 2027-01-14 | 2027-01-14 | 2027-01-14 | 0% | 0% | 3 | No
MS.CO.P1.FAH.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-11 | 2027-01-12 | 2027-01-14 | 2027-01-15 | 0% | 0% | 4 | No
MS.CO.F4.B1.128 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-01-11 | 2027-01-12 | 2027-01-14 | 2027-01-15 | 0% | 0% | 44 | No
MS.CO.P3(1).FAN.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-11 | 2027-01-12 | 2027-01-14 | 2027-01-15 | 0% | 0% | 1 | No
MS.CO.P2.RB.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-14 | 2027-01-15 | 2027-01-15 | 2027-01-16 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.140 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-16 | 2027-01-31 | 2027-01-16 | 2027-01-31 | 0% | 0% | 10 | No
MS.CO.P1.FAH.149 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-13 | 2027-01-28 | 2027-01-16 | 2027-01-31 | 0% | 0% | 4 | No
MS.CO.P1.FAH.155 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-14 | 2027-01-19 | 2027-01-16 | 2027-01-20 | 0% | 0% | 1 | No
MS.CO.P1.FAG.146 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-16 | 2027-01-20 | 2027-01-16 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.P2.B3.127 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 0% | 0% | 6 | No
MS.CO.P2.HO.135 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-16 | 2027-01-19 | 2027-01-16 | 2027-01-19 | 0% | 0% | 4 | No
MS.CO.P2.RB.126 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-14 | 2027-01-18 | 2027-01-16 | 2027-01-19 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 03 | 2027-01-14 | 2027-01-18 | 2027-01-16 | 2027-01-19 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.134 | External Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-13 | 2027-01-28 | 2027-01-16 | 2027-01-31 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.137 | Beams and Slab Formwork | 6 | Not Started | Con.Phase 03 | 2027-01-13 | 2027-01-19 | 2027-01-16 | 2027-01-21 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.126 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-01-14 | 2027-01-25 | 2027-01-16 | 2027-01-26 | 0% | 0% | 15 | No
MS.CO.P3(1).FAO.131 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 03 | 2027-01-13 | 2027-01-17 | 2027-01-16 | 2027-01-19 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.108 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.219 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 03 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 2027-01-16 | 0% | 0% | 3 | No
MS.CO.P1.FAF.148 | Beams and Slab Concreting work | 4 | Not Started | Con.Phase 01 | 2027-01-16 | 2027-01-19 | 2027-01-17 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.103 | B2 - Columns Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 0% | 0% | 6 | No
MS.CO.P2.HO.137 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-17 | 2027-01-20 | 2027-01-17 | 2027-01-20 | 0% | 0% | 4 | No
MS.CO.P2.RB.122 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-16 | 2027-01-31 | 2027-01-17 | 2027-02-01 | 0% | 0% | 5 | No
MS.CO.P2.RB.128 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 02 | 2027-01-16 | 2027-01-20 | 2027-01-17 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.116 | Internal Block Work | 20 | Not Started | Con.Phase 02 | 2027-01-17 | 2027-02-08 | 2027-01-17 | 2027-02-08 | 0% | 0% | 8 | No
MS.CO.F4.FCQ.111 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 04 | 2027-01-13 | 2027-01-17 | 2027-01-17 | 2027-01-20 | 0% | 0% | 1 | No
MS.CO.F4.FCD.126 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2027-01-14 | 2027-01-16 | 2027-01-17 | 2027-01-18 | 0% | 0% | 1 | No
MS.CO.P5.FA.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.132 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 03 | 2027-01-14 | 2027-01-18 | 2027-01-17 | 2027-01-20 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.109 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-01-17 | 2027-01-19 | 2027-01-17 | 2027-01-19 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.203 | B2 - Walls Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 2027-01-17 | 0% | 0% | 7 | No
MS.CO.P3(2).FO.229 | Water Proofing Membrane under Raft Foundation | 2 | Not Started | Con.Phase 03 | 2027-01-17 | 2027-01-18 | 2027-01-17 | 2027-01-18 | 0% | 0% | 3 | No
MS.CO.P2.FBC.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-17 | 2027-01-18 | 2027-01-17 | 2027-01-18 | 0% | 0% | 6 | No
MS.CO.P5.FA.153 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-01-17 | 2027-01-18 | 2027-01-17 | 2027-01-18 | 0% | 0% | 19 | No
MS.CO.P1.FAE.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.107 | B2 - Columns Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 0% | 0% | 6 | No
MS.CO.P2.FBC.129 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-18 | 2027-01-20 | 2027-01-18 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.111 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-18 | 2027-01-20 | 2027-01-18 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.128 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-01-16 | 2027-01-18 | 2027-01-18 | 2027-01-20 | 0% | 0% | 1 | No
MS.CO.P5.FA.167 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2027-01-18 | 2027-01-20 | 2027-01-18 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.133 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 03 | 2027-01-16 | 2027-01-19 | 2027-01-18 | 2027-01-21 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.127 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2027-01-16 | 2027-01-20 | 2027-01-18 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.207 | B2 - Walls Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 2027-01-18 | 0% | 0% | 7 | No
MS.CO.P3(1).FAO.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-15 | 2027-01-16 | 2027-01-18 | 2027-01-19 | 0% | 0% | 8 | No
MS.CO.P3(1)MQ.104 | FF- Slabs & Beams Formwork, steel Fix & Concreting work | 12 | Not Started | Con.Phase 03 | 2027-01-19 | 2027-02-01 | 2027-01-19 | 2027-02-01 | 0% | 0% | 2 | No
MS.CO.P1.FAI.147 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-13 | 2027-01-17 | 2027-01-19 | 2027-01-23 | 0% | 0% | -2 | Yes
MS.CO.P1.FAE.150 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-19 | 2027-01-23 | 2027-01-19 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.111 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-19 | 2027-01-19 | 2027-01-19 | 2027-01-19 | 0% | 0% | 6 | No
MS.CO.F4.B3.102 | B3 - Columns Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-16 | 2027-01-16 | 2027-01-19 | 2027-01-19 | 0% | 0% | 1 | No
MS.CO.F4.FCD.116 | Internal Block Work | 20 | Not Started | Con.Phase 04 | 2027-01-19 | 2027-02-10 | 2027-01-19 | 2027-02-10 | 0% | 0% | 2 | No
MS.CO.P5.FA.168 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2027-01-19 | 2027-01-21 | 2027-01-19 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.137 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 03 | 2027-01-17 | 2027-01-21 | 2027-01-19 | 2027-01-24 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.110 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-01-19 | 2027-01-21 | 2027-01-19 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.105 | Rebars for 1st layer for Foundation | 2 | Not Started | Con.Phase 03 | 2027-01-19 | 2027-01-20 | 2027-01-19 | 2027-01-20 | 0% | 0% | 3 | No
MS.CO.P2.B2.211 | B2 - Walls Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-19 | 2027-01-19 | 2027-01-19 | 2027-01-19 | 0% | 0% | 7 | No
MS.CO.P2.B2.118 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 02 | 2027-01-20 | 2027-01-23 | 2027-01-20 | 2027-01-23 | 0% | 0% | 6 | No
MS.CO.P5.FA.170 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2027-01-20 | 2027-01-23 | 2027-01-20 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-19 | 2027-01-19 | 2027-01-20 | 2027-01-20 | 0% | 0% | 2 | No
MS.CO.P3(1).FAO.134 | External Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-17 | 2027-02-01 | 2027-01-20 | 2027-02-04 | 0% | 0% | 7 | No
MS.CO.P3(2).FO.249 | Blinding concrete for lower Part of Foundation | 1 | Not Started | Con.Phase 03 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-19 | 2027-01-20 | 2027-01-20 | 2027-01-21 | 0% | 0% | 5 | No
MS.CO.P1.FAE.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-20 | 2027-01-21 | 2027-01-20 | 2027-01-21 | 0% | 0% | 12 | No
MS.CO.P1.FAH.156 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-20 | 2027-01-24 | 2027-01-21 | 2027-01-25 | 0% | 0% | 1 | No
MS.CO.P1.FAG.147 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-21 | 2027-01-25 | 2027-01-21 | 2027-01-25 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.150 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2027-01-20 | 2027-01-25 | 2027-01-21 | 2027-01-26 | 0% | 0% | 2 | No
MS.CO.P2.HO.138 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-21 | 2027-01-24 | 2027-01-21 | 2027-01-24 | 0% | 0% | 4 | No
MS.CO.P2.FBC.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-18 | 2027-01-18 | 2027-01-21 | 2027-01-21 | 0% | 0% | 1 | No
MS.CO.F4.FCD.129 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-01-19 | 2027-01-21 | 2027-01-21 | 2027-01-24 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.140 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-01-20 | 2027-01-21 | 2027-01-21 | 2027-01-23 | 0% | 0% | 12 | No
MS.CO.P3(2).FO.259 | Block work for Drop Panels | 1 | Not Started | Con.Phase 03 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-22 | 2027-01-23 | 2027-01-22 | 2027-01-23 | 0% | 0% | 15 | No
MS.CO.F4.FCD.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.128 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 0% | 0% | 32 | No
MS.CO.P3(2).FAK.111 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-22 | 2027-01-23 | 2027-01-22 | 2027-01-23 | 0% | 0% | 10 | No
MS.CO.P1.FAF.149 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-21 | 2027-02-06 | 2027-01-23 | 2027-02-07 | 0% | 0% | 4 | No
MS.CO.P1.FAE.149 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-23 | 2027-02-07 | 2027-01-23 | 2027-02-07 | 0% | 0% | 10 | No
MS.CO.P1.FAE.151 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2027-01-23 | 2027-01-26 | 2027-01-23 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.129 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-21 | 2027-01-25 | 2027-01-23 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.122 | External Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-23 | 2027-02-07 | 2027-01-23 | 2027-02-07 | 0% | 0% | 2 | No
MS.CO.P2.FBC.132 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-23 | 2027-01-26 | 2027-01-23 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-23 | 2027-01-26 | 2027-01-23 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.108 | Beams and Slab Formwork | 2 | Not Started | Con.Phase 04 | 2027-01-19 | 2027-01-20 | 2027-01-23 | 2027-01-24 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.113 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 04 | 2027-01-19 | 2027-01-23 | 2027-01-23 | 2027-01-26 | 0% | 0% | 1 | No
MS.CO.P5.FA.173 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2027-01-23 | 2027-01-25 | 2027-01-23 | 2027-01-25 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.141 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-01-21 | 2027-01-23 | 2027-01-23 | 2027-01-24 | 0% | 0% | 12 | No
MS.CO.P3(1).FAN.138 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2027-01-20 | 2027-01-25 | 2027-01-23 | 2027-01-27 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.110 | Installation for Mechanical and Electrical Embeds | 1 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 0% | 0% | 3 | No
MS.CO.P3(2).FO.269 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-18 | 2027-01-18 | 2027-01-24 | 2027-01-24 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.143 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-19 | 2027-02-03 | 2027-01-24 | 2027-02-08 | 0% | 0% | 8 | No
MS.CO.P1.FAG.143 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-24 | 2027-02-08 | 2027-01-24 | 2027-02-08 | 0% | 0% | 10 | No
MS.CO.P1.FAF.151 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-23 | 2027-01-27 | 2027-01-24 | 2027-01-28 | 0% | 0% | 2 | No
MS.CO.P2.B2.123 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-01-24 | 2027-01-25 | 2027-01-24 | 2027-01-25 | 0% | 0% | 6 | No
MS.CO.P2.HO.131 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-24 | 2027-02-08 | 2027-01-24 | 2027-02-08 | 0% | 0% | 13 | No
MS.CO.P2.FBC.133 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-24 | 2027-01-27 | 2027-01-24 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.115 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-24 | 2027-01-27 | 2027-01-24 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.115 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 04 | 2027-01-20 | 2027-01-24 | 2027-01-24 | 2027-01-27 | 0% | 0% | 1 | No
MS.CO.P5.FA.151 | External Block Work | 12 | Not Started | Con.Phase 05 | 2027-01-24 | 2027-02-06 | 2027-01-24 | 2027-02-06 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.142 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-24 | 2027-01-24 | 2027-01-25 | 0% | 0% | 12 | No
MS.CO.P3(2).FAL.135 | External Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-02-07 | 2027-01-24 | 2027-02-08 | 0% | 0% | 25 | No
MS.CO.P3(2).FAL.129 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-21 | 2027-01-21 | 2027-01-24 | 2027-01-24 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.117 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-01-24 | 2027-02-06 | 2027-01-24 | 2027-02-06 | 0% | 0% | 9 | No
MS.CO.P3(2).FAK.113 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-01-24 | 2027-01-25 | 2027-01-24 | 2027-01-25 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.113 | Formwork for Foundations | 1 | Not Started | Con.Phase 03 | 2027-01-24 | 2027-01-24 | 2027-01-24 | 2027-01-24 | 0% | 0% | 4 | No
MS.CO.P1.FAI.150 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-19 | 2027-01-23 | 2027-01-25 | 2027-01-28 | 0% | 0% | -2 | Yes
MS.CO.P2.HO.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 0% | 0% | 4 | No
MS.CO.P2.FBC.135 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-25 | 2027-01-28 | 2027-01-25 | 2027-01-28 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.116 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-25 | 2027-01-28 | 2027-01-25 | 2027-01-28 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.110 | Beams and Slab Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-01-21 | 2027-01-21 | 2027-01-25 | 2027-01-25 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.116 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 04 | 2027-01-21 | 2027-01-25 | 2027-01-25 | 2027-01-28 | 0% | 0% | 1 | No
MS.CO.F4.FCD.122 | External Block Work | 14 | Not Started | Con.Phase 04 | 2027-01-25 | 2027-02-09 | 2027-01-25 | 2027-02-09 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-23 | 2027-01-23 | 2027-01-25 | 2027-01-25 | 0% | 0% | 1 | No
MS.CO.P5.FA.145 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2027-01-25 | 2027-02-07 | 2027-01-25 | 2027-02-07 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.138 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-26 | 2027-01-25 | 2027-01-28 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.131 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 03 | 2027-01-23 | 2027-01-27 | 2027-01-25 | 2027-01-30 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.114 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-01-25 | 2027-01-26 | 2027-01-25 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.115 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 1 | Not Started | Con.Phase 03 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 0% | 0% | 3 | No
MS.CO.P1.FAI.143 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-26 | 2027-02-10 | 2027-01-26 | 2027-02-10 | 0% | 0% | 10 | No
MS.CO.P1.FAH.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-25 | 2027-01-25 | 2027-01-26 | 2027-01-26 | 0% | 0% | 1 | No
MS.CO.P1.FAG.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.143 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-26 | 2027-02-10 | 2027-01-26 | 2027-02-10 | 0% | 0% | 6 | No
MS.CO.P1.FAE.153 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2027-01-26 | 2027-01-30 | 2027-01-26 | 2027-01-30 | 0% | 0% | 0 | Yes
MS.CO.P2.B2.126 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 0% | 0% | 6 | No
MS.CO.P2.HO.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-26 | 2027-01-30 | 2027-01-26 | 2027-01-30 | 0% | 0% | 4 | No
MS.CO.P2.FBC.137 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-26 | 2027-01-30 | 2027-01-26 | 2027-01-30 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.119 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-26 | 2027-01-30 | 2027-01-26 | 2027-01-30 | 0% | 0% | 0 | Yes
MS.CO.F4.B3.112 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-23 | 2027-01-23 | 2027-01-26 | 2027-01-26 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.119 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 04 | 2027-01-23 | 2027-01-27 | 2027-01-26 | 2027-01-31 | 0% | 0% | 1 | No
MS.CO.F4.FCD.132 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-01-24 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 0% | 0% | 1 | No
MS.CO.P5.FA.174 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-01-26 | 2027-01-27 | 2027-01-26 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.135 | Internal Block Work | 20 | Not Started | Con.Phase 03 | 2027-01-24 | 2027-02-16 | 2027-01-26 | 2027-02-18 | 0% | 0% | 4 | No
MS.CO.P3(2).FAL.132 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 03 | 2027-01-24 | 2027-01-28 | 2027-01-26 | 2027-01-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.122 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 03 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 2027-01-26 | 0% | 0% | 3 | No
MS.CO.P3(2).FO.279 | Water Proofing Membrane under Raft Foundation | 2 | Not Started | Con.Phase 03 | 2027-01-26 | 2027-01-27 | 2027-01-26 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.151 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 01 | 2027-01-21 | 2027-01-25 | 2027-01-27 | 2027-01-31 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.159 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 01 | 2027-01-26 | 2027-01-27 | 2027-01-27 | 2027-01-28 | 0% | 0% | 15 | No
MS.CO.P1.FAG.150 | Columns & Walls Steel Fix | 5 | Not Started | Con.Phase 01 | 2027-01-27 | 2027-02-01 | 2027-01-27 | 2027-02-01 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.155 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-27 | 2027-02-01 | 2027-01-27 | 2027-02-01 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.103 | B1 - Columns Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0% | 0% | 24 | No
MS.CO.P2.HO.124 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-27 | 2027-02-11 | 2027-01-27 | 2027-02-11 | 0% | 0% | 5 | No
MS.CO.P2.HO.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-27 | 2027-01-31 | 2027-01-27 | 2027-01-31 | 0% | 0% | 4 | No
MS.CO.P2.RB.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-26 | 2027-01-26 | 2027-01-27 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.100 | B2 - Columns Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-01-24 | 2027-01-24 | 2027-01-27 | 2027-01-27 | 0% | 0% | 1 | No
MS.CO.F4.FCD.133 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.115 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.102 | B2 - Columns Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0% | 0% | 5 | No
MS.CO.P2.B1.203 | B1 - Walls Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0% | 0% | 22 | No
MS.CO.F4.B2.200 | B2 - Walls Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-01-24 | 2027-01-24 | 2027-01-27 | 2027-01-27 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.202 | B2 - Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0% | 0% | 3 | No
MS.CO.P5.FA.162 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-01-27 | 2027-01-28 | 2027-01-27 | 2027-01-28 | 0% | 0% | 26 | No
MS.CO.P3(1).FAM.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-26 | 2027-01-27 | 2027-01-27 | 2027-01-28 | 0% | 0% | 5 | No
MS.CO.P1.FAG.151 | Columns & Walls Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-28 | 2027-02-02 | 2027-01-28 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.107 | B1 - Columns Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0% | 0% | 24 | No
MS.CO.P2.HO.144 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-28 | 2027-02-01 | 2027-01-28 | 2027-02-01 | 0% | 0% | 4 | No
MS.CO.P2.RB.132 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-01-27 | 2027-01-31 | 2027-01-28 | 2027-02-01 | 0% | 0% | 1 | No
MS.CO.F4.B2.101 | B2 - Columns Formwork | 1 | Not Started | Con.Phase 04 | 2027-01-25 | 2027-01-25 | 2027-01-28 | 2027-01-28 | 0% | 0% | 1 | No
MS.CO.P5.FA.175 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-26 | 2027-01-26 | 2027-01-28 | 2027-01-28 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.136 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-01-26 | 2027-02-06 | 2027-01-28 | 2027-02-08 | 0% | 0% | 14 | No
MS.CO.P3(2).FAK.116 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-31 | 2027-01-28 | 2027-01-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.108 | Rebars for 1st layer for Foundation | 3 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-31 | 2027-01-28 | 2027-01-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.106 | B2 - Columns Formwork | 1 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0% | 0% | 5 | No
MS.CO.P2.B1.207 | B1 - Walls Formwork | 1 | Not Started | Con.Phase 02 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0% | 0% | 22 | No
MS.CO.F4.B2.201 | B2 - Walls Formwork | 1 | Not Started | Con.Phase 04 | 2027-01-25 | 2027-01-25 | 2027-01-28 | 2027-01-28 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.206 | B2 - Walls Formwork | 1 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 2027-01-28 | 0% | 0% | 3 | No
MS.CO.F4.FCQ.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 0% | 0% | 2 | No
MS.CO.P1.FAI.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-24 | 2027-01-25 | 2027-01-29 | 2027-01-30 | 0% | 0% | 12 | No
MS.CO.P2.FBC.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-29 | 2027-01-30 | 2027-01-29 | 2027-01-30 | 0% | 0% | 10 | No
MS.CO.P1.FAI.153 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 01 | 2027-01-24 | 2027-01-27 | 2027-01-30 | 2027-02-02 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.160 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 01 | 2027-01-28 | 2027-01-30 | 2027-01-30 | 2027-01-31 | 0% | 0% | 15 | No
MS.CO.P1.FAG.153 | Columns & Walls Concreting work | 5 | Not Started | Con.Phase 01 | 2027-01-30 | 2027-02-03 | 2027-01-30 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.153 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-28 | 2027-01-28 | 2027-01-30 | 2027-01-30 | 0% | 0% | 2 | No
MS.CO.P2.B1.111 | B1 - Columns Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 0% | 0% | 24 | No
MS.CO.P2.HO.146 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-30 | 2027-02-02 | 2027-01-30 | 2027-02-02 | 0% | 0% | 4 | No
MS.CO.P2.RB.125 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-01-28 | 2027-02-14 | 2027-01-30 | 2027-02-15 | 0% | 0% | 3 | No
MS.CO.P2.RB.133 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-01-28 | 2027-02-01 | 2027-01-30 | 2027-02-02 | 0% | 0% | 1 | No
MS.CO.F4.B2.102 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-26 | 2027-01-26 | 2027-01-30 | 2027-01-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.114 | External Block Work | 14 | Not Started | Con.Phase 04 | 2027-01-28 | 2027-02-14 | 2027-01-30 | 2027-02-15 | 0% | 0% | 2 | No
MS.CO.F4.FCD.135 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2027-01-27 | 2027-01-28 | 2027-01-30 | 2027-01-31 | 0% | 0% | 1 | No
MS.CO.P5.FA.176 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2027-01-30 | 2027-02-01 | 2027-01-30 | 2027-02-01 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.144 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-02-10 | 2027-01-30 | 2027-02-11 | 0% | 0% | 4 | No
MS.CO.P3(1).FAM.143 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-31 | 2027-01-30 | 2027-02-01 | 0% | 0% | 8 | No
MS.CO.P3(1).FAN.140 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-01-27 | 2027-01-28 | 2027-01-30 | 2027-01-31 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-27 | 2027-01-27 | 2027-01-30 | 2027-01-30 | 0% | 0% | 3 | No
MS.CO.P3(2).B2.111 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 0% | 0% | 5 | No
MS.CO.P2.B1.211 | B1 - Walls Concreting work | 1 | Not Started | Con.Phase 02 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 0% | 0% | 22 | No
MS.CO.F4.B2.202 | B2 - Walls Concreting work | 1 | Not Started | Con.Phase 04 | 2027-01-26 | 2027-01-26 | 2027-01-30 | 2027-01-30 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.211 | B2 - Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 0% | 0% | 3 | No
MS.CO.P1.FAI.155 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-25 | 2027-01-30 | 2027-01-31 | 2027-02-04 | 0% | 0% | -2 | Yes
MS.CO.P1.FAF.155 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-01-30 | 2027-02-03 | 2027-01-31 | 2027-02-04 | 0% | 0% | 2 | No
MS.CO.P2.RB.135 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-01-30 | 2027-02-02 | 2027-01-31 | 2027-02-03 | 0% | 0% | 1 | No
MS.CO.P2.FBC.138 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-31 | 2027-02-02 | 2027-01-31 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.120 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-01-31 | 2027-02-02 | 2027-01-31 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.107 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-01-27 | 2027-01-30 | 2027-01-31 | 2027-02-02 | 0% | 0% | 1 | No
MS.CO.F4.FCD.137 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-01-28 | 2027-01-31 | 2027-01-31 | 2027-02-02 | 0% | 0% | 1 | No
MS.CO.P5.FA.177 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2027-01-31 | 2027-02-02 | 2027-01-31 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.141 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-30 | 2027-01-31 | 2027-02-01 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.140 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-31 | 2027-01-31 | 2027-02-02 | 0% | 0% | 3 | No
MS.CO.P3(2).FAK.118 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-01-31 | 2027-02-02 | 2027-01-31 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-31 | 2027-02-01 | 2027-01-31 | 2027-02-01 | 0% | 0% | 5 | No
MS.CO.P2.FBR.109 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-01-31 | 2027-02-01 | 2027-01-31 | 2027-02-01 | 0% | 0% | 1 | No
MS.CO.P3(1)MQ.106 | GF - Block Work | 17 | Not Started | Con.Phase 03 | 2027-02-01 | 2027-02-23 | 2027-02-01 | 2027-02-23 | 0% | 0% | 26 | No
MS.CO.P1.FAI.149 | External Block Work | 12 | Not Started | Con.Phase 01 | 2027-02-01 | 2027-02-15 | 2027-02-01 | 2027-02-15 | 0% | 0% | 10 | No
MS.CO.P1.FAH.161 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-01-31 | 2027-01-31 | 2027-02-01 | 2027-02-01 | 0% | 0% | 15 | No
MS.CO.P1.FAG.155 | Beams and Slab Formwork | 5 | Not Started | Con.Phase 01 | 2027-02-01 | 2027-02-06 | 2027-02-01 | 2027-02-06 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.120 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 04 | 2027-01-28 | 2027-02-01 | 2027-02-01 | 2027-02-04 | 0% | 0% | 1 | No
MS.CO.P5.FA.180 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2027-02-01 | 2027-02-03 | 2027-02-01 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.135 | Internal Block Work | 14 | Not Started | Con.Phase 03 | 2027-01-31 | 2027-02-16 | 2027-02-01 | 2027-02-17 | 0% | 0% | 5 | No
MS.CO.P3(1).FAN.142 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-01-31 | 2027-02-01 | 2027-02-02 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.141 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 2027-02-03 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.133 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.114 | Installation for Mechanical and Electrical Embeds | 1 | Not Started | Con.Phase 03 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-01 | 2027-02-02 | 2027-02-01 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-01-28 | 2027-01-29 | 2027-02-01 | 2027-02-02 | 0% | 0% | 3 | No
MS.CO.P3(1)MQ.107 | FF- Slabs & Beams DE shuttering work | 18 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-25 | 2027-02-02 | 2027-02-25 | 0% | 0% | 7 | No
MS.CO.P3(1)MQ.105 | Top Of Roof- Columns & Walls Formwork, Steel & Concreting work | 5 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-07 | 2027-02-02 | 2027-02-07 | 0% | 0% | 2 | No
MS.CO.F4.B2.135 | B2 - Block Works | 23 | Not Started | Con.Phase 04 | 2027-02-01 | 2027-03-03 | 2027-02-02 | 2027-03-07 | 0% | 0% | 19 | No
MS.CO.P1.FAH.163 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-01 | 2027-02-03 | 2027-02-02 | 2027-02-04 | 0% | 0% | 15 | No
MS.CO.P1.FAG.149 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-02 | 2027-02-18 | 2027-02-02 | 2027-02-18 | 0% | 0% | 4 | No
MS.CO.P1.FAE.156 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-02-02 | 2027-02-06 | 2027-02-02 | 2027-02-06 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.114 | External Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-02 | 2027-02-18 | 2027-02-02 | 2027-02-18 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.145 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-02-01 | 2027-02-02 | 2027-02-02 | 2027-02-03 | 0% | 0% | 8 | No
MS.CO.P3(1).FAO.142 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 03 | 2027-01-31 | 2027-02-02 | 2027-02-02 | 2027-02-04 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.134 | Beams and Slab Formwork | 8 | Not Started | Con.Phase 03 | 2027-01-31 | 2027-02-08 | 2027-02-02 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.122 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-14 | 2027-02-02 | 2027-02-14 | 0% | 0% | 32 | No
MS.CO.P3(2).FO.116 | Formwork for Foundations | 1 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-02 | 2027-02-02 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.120 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 1 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-02 | 2027-02-02 | 2027-02-02 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.117 | Beams and Slab Formwork | 2 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-03 | 2027-02-02 | 2027-02-03 | 0% | 0% | 3 | No
MS.CO.P1.FAH.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-01-29 | 2027-01-30 | 2027-02-02 | 2027-02-03 | 0% | 0% | 2 | No
MS.CO.P2.HO.147 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-03 | 2027-02-06 | 2027-02-03 | 2027-02-06 | 0% | 0% | 4 | No
MS.CO.P2.RB.131 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-03 | 2027-02-21 | 2027-02-03 | 2027-02-21 | 0% | 0% | 4 | No
MS.CO.P2.RB.137 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-03 | 2027-02-07 | 2027-02-03 | 2027-02-07 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.109 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-01-31 | 2027-02-01 | 2027-02-03 | 2027-02-04 | 0% | 0% | 1 | No
MS.CO.F4.FCD.138 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-02-01 | 2027-02-03 | 2027-02-03 | 2027-02-06 | 0% | 0% | 1 | No
MS.CO.P5.FA.182 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2027-02-03 | 2027-02-06 | 2027-02-03 | 2027-02-06 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.144 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-01-30 | 2027-02-11 | 2027-02-03 | 2027-02-17 | 0% | 0% | 11 | No
MS.CO.P3(1).FAO.143 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 03 | 2027-02-01 | 2027-02-04 | 2027-02-03 | 2027-02-07 | 0% | 0% | 3 | No
MS.CO.P3(2).FAL.141 | Internal Block Work | 14 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-18 | 2027-02-03 | 2027-02-21 | 0% | 0% | 27 | No
MS.CO.P3(2).FAK.120 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FO.125 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.244 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-03 | 2027-02-04 | 2027-02-03 | 2027-02-04 | 0% | 0% | 2 | No
MS.CO.P1.FAH.158 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-01-31 | 2027-02-16 | 2027-02-04 | 2027-02-23 | 0% | 0% | 1 | No
MS.CO.P1.FAF.152 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-06 | 2027-02-24 | 2027-02-04 | 2027-02-23 | 0% | 0% | 2 | No
MS.CO.P2.FBC.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-02-04 | 2027-02-08 | 2027-02-04 | 2027-02-08 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.122 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-02-04 | 2027-02-08 | 2027-02-04 | 2027-02-08 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.146 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-03 | 2027-02-03 | 2027-02-04 | 2027-02-04 | 0% | 0% | 8 | No
MS.CO.P3(1).FAN.143 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 03 | 2027-02-02 | 2027-02-06 | 2027-02-04 | 2027-02-08 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.121 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-02-04 | 2027-02-06 | 2027-02-04 | 2027-02-06 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.104 | B2 - Columns Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 0% | 0% | 2 | No
MS.CO.P3(2).B2.123 | Beams and Slab Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 0% | 0% | 3 | No
MS.CO.P3(2).B2.204 | B2 - Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-04 | 2027-02-05 | 2027-02-04 | 2027-02-05 | 0% | 0% | 23 | No
MS.CO.F4.FCD.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 0% | 0% | 4 | No
MS.CO.P5.ALL.206 | Special construction works planter, cross over ,water features ,canal | 22 | Not Started | Con.Phase 05 | 2027-02-06 | 2027-03-08 | 2027-02-06 | 2027-03-08 | 0% | 0% | 17 | No
MS.CO.P1.FAI.156 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-01-31 | 2027-02-03 | 2027-02-06 | 2027-02-09 | 0% | 0% | -2 | Yes
MS.CO.P1.FAH.165 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-04 | 2027-02-07 | 2027-02-06 | 2027-02-08 | 0% | 0% | 15 | No
MS.CO.P1.FAF.156 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-02-04 | 2027-02-08 | 2027-02-06 | 2027-02-09 | 0% | 0% | 2 | No
MS.CO.P2.HO.140 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-06 | 2027-02-24 | 2027-02-06 | 2027-02-24 | 0% | 0% | 16 | No
MS.CO.P2.FBC.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-06 | 2027-02-09 | 2027-02-06 | 2027-02-09 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-06 | 2027-02-09 | 2027-02-06 | 2027-02-09 | 0% | 0% | 0 | Yes
MS.CO.F4.B2.111 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-02 | 2027-02-02 | 2027-02-06 | 2027-02-06 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.121 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-02 | 2027-02-02 | 2027-02-06 | 2027-02-06 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.123 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-07 | 2027-02-06 | 2027-02-07 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.109 | B2 - Columns Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 0% | 0% | 2 | No
MS.CO.P3(2).B2.125 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 0% | 0% | 3 | No
MS.CO.P3(2).B2.209 | B2 - Walls Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 2027-02-06 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.164 | External Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-17 | 2027-02-06 | 2027-02-17 | 0% | 0% | 1 | No
MS.CO.P1.FAG.156 | Beams and Slab Steel Fix | 4 | Not Started | Con.Phase 01 | 2027-02-07 | 2027-02-10 | 2027-02-07 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 4 | No
MS.CO.P2.FBC.144 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-02-07 | 2027-02-10 | 2027-02-07 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.125 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-02-07 | 2027-02-10 | 2027-02-07 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.100 | B1 - Columns Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-02-03 | 2027-02-03 | 2027-02-07 | 2027-02-07 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.122 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 04 | 2027-02-03 | 2027-02-07 | 2027-02-07 | 2027-02-10 | 0% | 0% | 1 | No
MS.CO.F4.FCD.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-04 | 2027-02-04 | 2027-02-07 | 2027-02-07 | 0% | 0% | 1 | No
MS.CO.P5.FA.160 | External Block Work | 12 | Not Started | Con.Phase 05 | 2027-02-07 | 2027-02-23 | 2027-02-07 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.183 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-02-07 | 2027-02-08 | 2027-02-07 | 2027-02-08 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.113 | B2 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 2 | No
MS.CO.P3(2).B1.102 | B1 - Columns Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 10 | No
MS.CO.F4.B1.200 | B1 - Walls Steel Fix | 1 | Not Started | Con.Phase 04 | 2027-02-03 | 2027-02-03 | 2027-02-07 | 2027-02-07 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.213 | B2 - Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.202 | B1 - Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 2027-02-07 | 0% | 0% | 12 | No
MS.CO.P3(1).FAO.135 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-04 | 2027-02-05 | 2027-02-07 | 2027-02-08 | 0% | 0% | 6 | No
MS.CO.P3(1)MQ.108 | Top Of Roof- Slabs & Beams Formwork & Steel & Concreting work | 8 | Not Started | Con.Phase 03 | 2027-02-08 | 2027-02-17 | 2027-02-08 | 2027-02-17 | 0% | 0% | 2 | No
MS.CO.P1.FAE.159 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 01 | 2027-02-08 | 2027-02-09 | 2027-02-08 | 2027-02-09 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.150 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-02-08 | 2027-02-11 | 2027-02-08 | 2027-02-11 | 0% | 0% | 4 | No
MS.CO.P2.RB.138 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-08 | 2027-02-10 | 2027-02-08 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.131 | External Block Work | 12 | Not Started | Con.Phase 02 | 2027-02-08 | 2027-02-24 | 2027-02-08 | 2027-02-24 | 0% | 0% | 2 | No
MS.CO.P2.FBR.128 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-08 | 2027-02-11 | 2027-02-08 | 2027-02-11 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.101 | B1 - Columns Formwork | 1 | Not Started | Con.Phase 04 | 2027-02-04 | 2027-02-04 | 2027-02-08 | 2027-02-08 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.124 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 04 | 2027-02-04 | 2027-02-08 | 2027-02-08 | 2027-02-11 | 0% | 0% | 1 | No
MS.CO.F4.FCD.141 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-02-06 | 2027-02-08 | 2027-02-08 | 2027-02-10 | 0% | 0% | 1 | No
MS.CO.P5.FA.154 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2027-02-08 | 2027-02-24 | 2027-02-08 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.145 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-08 | 2027-02-08 | 2027-02-10 | 0% | 0% | 12 | No
MS.CO.P3(2).FAK.124 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.106 | B1 - Columns Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 0% | 0% | 10 | No
MS.CO.F4.B1.201 | B1 - Walls Formwork | 1 | Not Started | Con.Phase 04 | 2027-02-04 | 2027-02-04 | 2027-02-08 | 2027-02-08 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.206 | B1 - Walls Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 0% | 0% | 12 | No
MS.CO.P3(2).B1.211 | B1 - Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-08 | 0% | 0% | 12 | No
MS.CO.P2.B3.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-08 | 2027-02-09 | 2027-02-08 | 2027-02-09 | 0% | 0% | 50 | No
MS.CO.F4.FCD.156 | Special construction works planter, cross over ,water features ,canal | 19 | Not Started | Con.Phase 04 | 2027-02-07 | 2027-03-04 | 2027-02-09 | 2027-03-08 | 0% | 0% | 17 | No
MS.CO.P1.FAH.152 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-04 | 2027-02-23 | 2027-02-09 | 2027-03-01 | 0% | 0% | 8 | No
MS.CO.P1.FAH.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-08 | 2027-02-08 | 2027-02-09 | 2027-02-09 | 0% | 0% | 15 | No
MS.CO.P1.FAE.160 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 01 | 2027-02-09 | 2027-02-10 | 2027-02-09 | 2027-02-10 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.151 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-09 | 2027-02-14 | 2027-02-09 | 2027-02-14 | 0% | 0% | 4 | No
MS.CO.P2.FBC.125 | Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-09 | 2027-03-01 | 2027-02-09 | 2027-03-01 | 0% | 0% | 8 | No
MS.CO.P2.FBC.146 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-09 | 2027-02-14 | 2027-02-09 | 2027-02-14 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.102 | B1 - Columns Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-06 | 2027-02-06 | 2027-02-09 | 2027-02-09 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.117 | Internal Block Work | 20 | Not Started | Con.Phase 04 | 2027-02-08 | 2027-03-08 | 2027-02-09 | 2027-03-09 | 0% | 0% | 16 | No
MS.CO.F4.FCQ.125 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 04 | 2027-02-06 | 2027-02-09 | 2027-02-09 | 2027-02-14 | 0% | 0% | 1 | No
MS.CO.F4.FCD.142 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 04 | 2027-02-07 | 2027-02-09 | 2027-02-09 | 2027-02-11 | 0% | 0% | 1 | No
MS.CO.P5.FA.184 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAN.145 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-02-07 | 2027-02-09 | 2027-02-09 | 2027-02-11 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.144 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-06 | 2027-02-21 | 2027-02-09 | 2027-02-25 | 0% | 0% | 4 | No
MS.CO.P3(2).FAK.125 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-09 | 2027-02-11 | 2027-02-09 | 2027-02-11 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.111 | B1 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 0% | 0% | 10 | No
MS.CO.F4.B1.202 | B1 - Walls Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-06 | 2027-02-06 | 2027-02-09 | 2027-02-09 | 0% | 0% | 1 | No
MS.CO.P5.FA.171 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-02-09 | 2027-02-10 | 2027-02-09 | 2027-02-10 | 0% | 0% | 33 | No
MS.CO.P1.FAI.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-04 | 2027-02-04 | 2027-02-10 | 2027-02-10 | 0% | 0% | -2 | Yes
MS.CO.P1.FAF.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-09 | 2027-02-09 | 2027-02-10 | 2027-02-10 | 0% | 0% | 2 | No
MS.CO.P2.HO.153 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-02-10 | 2027-02-15 | 2027-02-10 | 2027-02-15 | 0% | 0% | 4 | No
MS.CO.F4.B1.107 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 04 | 2027-02-07 | 2027-02-10 | 2027-02-10 | 2027-02-15 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.128 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 04 | 2027-02-07 | 2027-02-10 | 2027-02-10 | 2027-02-15 | 0% | 0% | 1 | No
MS.CO.F4.FCD.131 | External Block Work | 12 | Not Started | Con.Phase 04 | 2027-02-10 | 2027-02-28 | 2027-02-10 | 2027-02-28 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.185 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 05 | 2027-02-10 | 2027-02-14 | 2027-02-10 | 2027-02-14 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.119 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-10 | 2027-02-14 | 2027-02-10 | 2027-02-14 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.117 | Beams and Slab Formwork | 2 | Not Started | Con.Phase 03 | 2027-02-10 | 2027-02-11 | 2027-02-10 | 2027-02-11 | 0% | 0% | 10 | No
MS.CO.P1.FAF.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-09 | 2027-02-10 | 2027-02-10 | 2027-02-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-10 | 2027-02-11 | 2027-02-10 | 2027-02-11 | 0% | 0% | 10 | No
MS.CO.P1.FAI.152 | Internal Block Work | 12 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-03-01 | 2027-02-11 | 2027-03-01 | 0% | 0% | 10 | No
MS.CO.P1.FAI.159 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-06 | 2027-02-08 | 2027-02-11 | 2027-02-15 | 0% | 0% | 1 | No
MS.CO.P1.FAG.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.159 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 01 | 2027-02-10 | 2027-02-11 | 2027-02-11 | 2027-02-14 | 0% | 0% | 4 | No
MS.CO.P1.FAE.152 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-03-03 | 2027-02-11 | 2027-03-03 | 0% | 0% | 6 | No
MS.CO.P1.FAE.161 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.125 | Internal Block Work | 20 | Not Started | Con.Phase 04 | 2027-02-11 | 2027-03-15 | 2027-02-11 | 2027-03-15 | 0% | 0% | 2 | No
MS.CO.F4.FCD.144 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 04 | 2027-02-09 | 2027-02-11 | 2027-02-11 | 2027-02-15 | 0% | 0% | 1 | No
MS.CO.P5.FA.186 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 05 | 2027-02-11 | 2027-02-15 | 2027-02-11 | 2027-02-15 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.146 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-09 | 2027-02-09 | 2027-02-11 | 2027-02-11 | 0% | 0% | 12 | No
MS.CO.P3(2).FAL.136 | Beams and Slab Steel Fix | 5 | Not Started | Con.Phase 03 | 2027-02-09 | 2027-02-15 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.127 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-02-11 | 2027-02-15 | 2027-02-11 | 2027-02-15 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.147 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-11 | 2027-02-12 | 2027-02-12 | 2027-02-13 | 0% | 0% | 4 | No
MS.CO.P1.FAI.160 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-07 | 2027-02-09 | 2027-02-14 | 2027-02-16 | 0% | 0% | 1 | No
MS.CO.P1.FAG.152 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-14 | 2027-03-04 | 2027-02-14 | 2027-03-04 | 0% | 0% | 7 | No
MS.CO.P1.FAG.159 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-14 | 2027-02-16 | 2027-02-14 | 2027-02-16 | 0% | 0% | 1 | No
MS.CO.P1.FAF.158 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-03-03 | 2027-02-14 | 2027-03-04 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.160 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 01 | 2027-02-11 | 2027-02-14 | 2027-02-14 | 2027-02-15 | 0% | 0% | 4 | No
MS.CO.P1.FAE.158 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-14 | 2027-03-04 | 2027-02-14 | 2027-03-04 | 0% | 0% | 6 | No
MS.CO.P1.FAE.163 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-14 | 2027-02-16 | 2027-02-14 | 2027-02-16 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.134 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-14 | 2027-03-04 | 2027-02-14 | 2027-03-04 | 0% | 0% | 5 | No
MS.CO.P2.HO.155 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-14 | 2027-02-17 | 2027-02-14 | 2027-02-17 | 0% | 0% | 4 | No
MS.CO.P2.RB.141 | Columns & Walls Steel Fix | 4 | Not Started | Con.Phase 02 | 2027-02-14 | 2027-02-17 | 2027-02-14 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.118 | Internal Block Work | 20 | Not Started | Con.Phase 02 | 2027-02-14 | 2027-03-16 | 2027-02-14 | 2027-03-16 | 0% | 0% | 1 | No
MS.CO.P2.FBR.129 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-14 | 2027-02-16 | 2027-02-14 | 2027-02-16 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.189 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 05 | 2027-02-14 | 2027-02-16 | 2027-02-14 | 2027-02-16 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.150 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-14 | 2027-03-02 | 2027-02-14 | 2027-03-02 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.146 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-10 | 2027-02-10 | 2027-02-14 | 2027-02-14 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.147 | Internal Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-09 | 2027-02-25 | 2027-02-14 | 2027-03-02 | 0% | 0% | 11 | No
MS.CO.P3(2).B1.123 | Beams and Slab Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-14 | 2027-02-14 | 2027-02-14 | 2027-02-14 | 0% | 0% | 10 | No
MS.CO.P1.FAI.162 | Columns & Walls Concreting work | 3 | Not Started | Con.Phase 01 | 2027-02-08 | 2027-02-10 | 2027-02-15 | 2027-02-17 | 0% | 0% | 1 | No
MS.CO.P1.FAG.160 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-15 | 2027-02-17 | 2027-02-15 | 2027-02-17 | 0% | 0% | 1 | No
MS.CO.P2.RB.142 | Columns & Walls Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-15 | 2027-02-18 | 2027-02-15 | 2027-02-18 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.147 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-15 | 2027-02-17 | 2027-02-15 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.146 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-02-11 | 2027-02-15 | 2027-02-15 | 2027-02-17 | 0% | 0% | 1 | No
MS.CO.P5.FA.191 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 05 | 2027-02-15 | 2027-02-17 | 2027-02-15 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.126 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-02-15 | 2027-02-16 | 2027-02-15 | 2027-02-16 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.125 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-15 | 2027-02-15 | 2027-02-15 | 2027-02-15 | 0% | 0% | 10 | No
MS.CO.P2.FBC.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-15 | 2027-02-16 | 2027-02-15 | 2027-02-16 | 0% | 0% | 12 | No
MS.CO.P2.FBR.117 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-15 | 2027-02-16 | 2027-02-15 | 2027-02-16 | 0% | 0% | 9 | No
MS.CO.F4.FCQ.118 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-02-10 | 2027-02-11 | 2027-02-15 | 2027-02-16 | 0% | 0% | 1 | No
MS.CO.P1.FAI.163 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 01 | 2027-02-09 | 2027-02-14 | 2027-02-16 | 2027-02-21 | 0% | 0% | 1 | No
MS.CO.P1.FAF.162 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-15 | 2027-02-15 | 2027-02-16 | 2027-02-16 | 0% | 0% | 4 | No
MS.CO.P2.RB.134 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-15 | 2027-03-07 | 2027-02-16 | 2027-03-08 | 0% | 0% | 3 | No
MS.CO.P2.RB.144 | Columns & Walls Concreting work | 4 | Not Started | Con.Phase 02 | 2027-02-16 | 2027-02-21 | 2027-02-16 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.109 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-02-11 | 2027-02-15 | 2027-02-16 | 2027-02-18 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.129 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-02-11 | 2027-02-15 | 2027-02-16 | 2027-02-18 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.129 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-16 | 2027-02-16 | 2027-02-16 | 2027-02-16 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.119 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-16 | 2027-02-17 | 2027-02-16 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.163 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-16 | 2027-02-18 | 2027-02-17 | 2027-02-21 | 0% | 0% | 4 | No
MS.CO.P2.RB.146 | Beams and Slab Formwork | 4 | Not Started | Con.Phase 02 | 2027-02-17 | 2027-02-23 | 2027-02-17 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-17 | 2027-02-17 | 2027-02-17 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.123 | External Block Work | 14 | Not Started | Con.Phase 04 | 2027-02-15 | 2027-03-07 | 2027-02-17 | 2027-03-09 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.130 | Columns & Walls Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-02-21 | 2027-02-17 | 2027-02-21 | 0% | 0% | 1 | No
MS.CO.P3(2).B2.127 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-02-17 | 2027-02-17 | 2027-02-17 | 0% | 0% | 0 | Yes
MS.CO.P1.FAI.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-10 | 2027-02-11 | 2027-02-17 | 2027-02-18 | 0% | 0% | 18 | No
MS.CO.P3(2).FAL.137 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 0% | 0% | 14 | No
MS.CO.P3(1)MQ.109 | Top Of Roof- Slabs & Beams DE shuttering work | 12 | Not Started | Con.Phase 03 | 2027-02-18 | 2027-03-08 | 2027-02-18 | 2027-03-08 | 0% | 0% | 2 | No
MS.CO.P2.ALL.144 | Special construction works planter, cross over ,water features ,canal | 19 | Not Started | Con.Phase 02 | 2027-02-18 | 2027-03-20 | 2027-02-18 | 2027-03-20 | 0% | 0% | 10 | No
MS.CO.P1.FAG.162 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0% | 0% | 1 | No
MS.CO.P1.FAE.165 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 01 | 2027-02-18 | 2027-02-21 | 2027-02-18 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.P2.HO.156 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-18 | 2027-02-23 | 2027-02-18 | 2027-02-23 | 0% | 0% | 4 | No
MS.CO.P2.FBC.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.131 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-02-18 | 2027-02-21 | 2027-02-18 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.147 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 04 | 2027-02-16 | 2027-02-18 | 2027-02-18 | 2027-02-23 | 0% | 0% | 1 | No
MS.CO.P5.FA.192 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-02-18 | 2027-02-21 | 2027-02-18 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.148 | Internal Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-03-07 | 2027-02-18 | 2027-03-08 | 0% | 0% | 5 | No
MS.CO.P3(2).FAL.138 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-16 | 2027-02-16 | 2027-02-18 | 2027-02-18 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.126 | External Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-18 | 2027-03-04 | 2027-02-18 | 2027-03-04 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.132 | Columns & Walls Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-18 | 2027-02-23 | 2027-02-18 | 2027-02-23 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.104 | B1 - Columns Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.204 | B1 - Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0% | 0% | 2 | No
MS.CO.P2.HO.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-18 | 2027-02-19 | 2027-02-18 | 2027-02-19 | 0% | 0% | 12 | No
MS.CO.F4.FCD.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 0% | 0% | 9 | No
MS.CO.P1.FAH.164 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-18 | 2027-02-19 | 2027-02-19 | 2027-02-20 | 0% | 0% | 4 | No
MS.CO.P1.FAG.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-19 | 2027-02-20 | 2027-02-19 | 2027-02-20 | 0% | 0% | 5 | No
MS.CO.P2.B2.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-19 | 2027-02-20 | 2027-02-19 | 2027-02-20 | 0% | 0% | 11 | No
MS.CO.F4.B3.124 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-02-16 | 2027-02-17 | 2027-02-19 | 2027-02-20 | 0% | 0% | 8 | No
MS.CO.F4.B3.135 | B3 - Block Works | 23 | Not Started | Con.Phase 04 | 2027-02-18 | 2027-03-24 | 2027-02-21 | 2027-03-25 | 0% | 0% | 5 | No
MS.CO.P1.FAI.158 | External Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-16 | 2027-03-08 | 2027-02-21 | 2027-03-15 | 0% | 0% | 11 | No
MS.CO.P1.FAG.158 | External Block Work | 12 | Not Started | Con.Phase 01 | 2027-02-21 | 2027-03-09 | 2027-02-21 | 2027-03-09 | 0% | 0% | 4 | No
MS.CO.P1.FAG.163 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 01 | 2027-02-21 | 2027-02-24 | 2027-02-21 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P2.B1.118 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-02-24 | 2027-02-21 | 2027-02-24 | 0% | 0% | 8 | No
MS.CO.P2.HO.149 | GF - External Block Work | 10 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-03-07 | 2027-02-21 | 2027-03-07 | 0% | 0% | 8 | No
MS.CO.P2.FBC.150 | Columns & Walls Steel Fix | 1 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 0% | 0% | 1 | No
MS.CO.P2.FBR.123 | External Block Work | 12 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-03-09 | 2027-02-21 | 2027-03-09 | 0% | 0% | 4 | No
MS.CO.P2.FBR.133 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-02-23 | 2027-02-21 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.110 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-16 | 2027-02-16 | 2027-02-21 | 2027-02-21 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.130 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-16 | 2027-02-16 | 2027-02-21 | 2027-02-21 | 0% | 0% | 1 | No
MS.CO.P3(1).FAN.148 | Internal Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-03-07 | 2027-02-21 | 2027-03-09 | 0% | 0% | 4 | No
MS.CO.P3(2).FAL.146 | External Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-03-03 | 2027-02-21 | 2027-03-07 | 0% | 0% | 9 | No
MS.CO.P3(2).FAL.139 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-02-18 | 2027-02-21 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.140 | Columns & Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-02-17 | 2027-02-17 | 2027-02-21 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.109 | B1 - Columns Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.209 | B1 - Walls Formwork | 1 | Not Started | Con.Phase 03 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 2027-02-21 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.174 | Internal Block Work | 8 | Not Started | Con.Phase 03 | 2027-02-21 | 2027-03-03 | 2027-02-21 | 2027-03-03 | 0% | 0% | 1 | No
MS.CO.P2.RB.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-02-19 | 2027-02-20 | 2027-02-22 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAM.149 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-19 | 2027-02-20 | 2027-02-22 | 2027-02-23 | 0% | 0% | 13 | No
MS.CO.P1.FAI.165 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-15 | 2027-02-17 | 2027-02-23 | 2027-02-25 | 0% | 0% | 1 | No
MS.CO.P1.FAF.165 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-21 | 2027-02-24 | 2027-02-23 | 2027-02-25 | 0% | 0% | 4 | No
MS.CO.P1.FAE.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.151 | Columns & Walls Formwork | 1 | Not Started | Con.Phase 02 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 0% | 0% | 1 | No
MS.CO.P2.FBR.134 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 02 | 2027-02-23 | 2027-02-24 | 2027-02-23 | 2027-02-24 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.131 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-02-17 | 2027-02-18 | 2027-02-23 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P5.FA.193 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.113 | B1 - Columns Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B1.213 | B1 - Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-23 | 0% | 0% | 2 | No
MS.CO.P1.FAH.167 | External Block Work | 19 | Not Started | Con.Phase 01 | 2027-02-21 | 2027-03-21 | 2027-02-24 | 2027-03-23 | 0% | 0% | 1 | No
MS.CO.P2.HO.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 0% | 0% | 4 | No
MS.CO.P2.RB.140 | GF - External Block Work | 14 | Not Started | Con.Phase 02 | 2027-02-21 | 2027-03-15 | 2027-02-24 | 2027-03-17 | 0% | 0% | 3 | No
MS.CO.P2.RB.147 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 02 | 2027-02-24 | 2027-02-28 | 2027-02-24 | 2027-02-28 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.153 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 02 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P2.FBR.135 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 02 | 2027-02-24 | 2027-02-28 | 2027-02-24 | 2027-02-28 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.133 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2027-02-18 | 2027-02-21 | 2027-02-24 | 2027-02-25 | 0% | 0% | 1 | No
MS.CO.F4.FCD.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-02-21 | 2027-02-21 | 2027-02-24 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P5.FA.169 | External Block Work | 12 | Not Started | Con.Phase 05 | 2027-02-24 | 2027-03-15 | 2027-02-24 | 2027-03-15 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.194 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-02-24 | 2027-02-25 | 2027-02-24 | 2027-02-25 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.142 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-21 | 2027-02-21 | 2027-02-24 | 2027-02-24 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.133 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 2027-02-24 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.119 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-24 | 2027-02-28 | 2027-02-24 | 2027-02-28 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.181 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-02-24 | 2027-02-25 | 2027-02-24 | 2027-02-25 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.147 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-19 | 2027-02-20 | 2027-02-24 | 2027-02-25 | 0% | 0% | 17 | No
MS.CO.P1.FAG.165 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 01 | 2027-02-25 | 2027-03-01 | 2027-02-25 | 2027-03-01 | 0% | 0% | 1 | No
MS.CO.P2.B1.123 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-02-25 | 2027-02-28 | 2027-02-25 | 2027-02-28 | 0% | 0% | 8 | No
MS.CO.P2.FBC.140 | External Block Work | 10 | Not Started | Con.Phase 02 | 2027-02-25 | 2027-03-14 | 2027-02-25 | 2027-03-14 | 0% | 0% | 2 | No
MS.CO.P2.FBC.154 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 02 | 2027-02-25 | 2027-03-01 | 2027-02-25 | 2027-03-01 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.134 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2027-02-21 | 2027-02-23 | 2027-02-25 | 2027-02-28 | 0% | 0% | 1 | No
MS.CO.F4.FCD.150 | Columns & Walls Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-28 | 0% | 0% | 1 | No
MS.CO.P5.FA.163 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2027-02-25 | 2027-03-16 | 2027-02-25 | 2027-03-16 | 0% | 0% | 1 | No
MS.CO.P5.FA.195 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 05 | 2027-02-25 | 2027-02-28 | 2027-02-25 | 2027-02-28 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.143 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-23 | 2027-02-25 | 2027-02-25 | 2027-03-01 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.134 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 03 | 2027-02-25 | 2027-03-01 | 2027-02-25 | 2027-03-01 | 0% | 0% | 1 | No
MS.CO.P3(1).FAO.148 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-22 | 2027-02-23 | 2027-02-25 | 2027-02-26 | 0% | 0% | 5 | No
MS.CO.P3(1)MQ.111 | FF - Block Work | 17 | Not Started | Con.Phase 03 | 2027-02-28 | 2027-03-23 | 2027-02-28 | 2027-03-23 | 0% | 0% | 7 | No
MS.CO.F4.B1.135 | B1 - Block Works | 23 | Not Started | Con.Phase 04 | 2027-02-21 | 2027-03-25 | 2027-02-28 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P1.FAI.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-18 | 2027-02-18 | 2027-02-28 | 2027-02-28 | 0% | 0% | 1 | No
MS.CO.P1.FAF.161 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-25 | 2027-03-18 | 2027-02-28 | 2027-03-20 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-02-25 | 2027-02-25 | 2027-02-28 | 2027-02-28 | 0% | 0% | 4 | No
MS.CO.F4.FCQ.135 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-02-23 | 2027-02-25 | 2027-02-28 | 2027-03-02 | 0% | 0% | 1 | No
MS.CO.F4.FCD.151 | Columns & Walls Formwork | 2 | Not Started | Con.Phase 04 | 2027-02-24 | 2027-02-25 | 2027-02-28 | 2027-03-01 | 0% | 0% | 3 | No
MS.CO.P5.FA.187 | External Block Work | 12 | Not Started | Con.Phase 05 | 2027-02-28 | 2027-03-17 | 2027-02-28 | 2027-03-17 | 0% | 0% | 2 | No
MS.CO.P5.FA.188 | Internal Block Work | 14 | Not Started | Con.Phase 05 | 2027-02-28 | 2027-03-20 | 2027-02-28 | 2027-03-20 | 0% | 0% | 10 | No
MS.CO.P3(1).FAN.150 | External Block Work | 12 | Not Started | Con.Phase 03 | 2027-02-21 | 2027-03-09 | 2027-02-28 | 2027-03-17 | 0% | 0% | 9 | No
MS.CO.P3(1).FAO.150 | External Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-24 | 2027-03-09 | 2027-02-28 | 2027-03-15 | 0% | 0% | 4 | No
MS.CO.P3(2).FAK.131 | Internal Block Work | 8 | Not Started | Con.Phase 03 | 2027-02-28 | 2027-03-09 | 2027-02-28 | 2027-03-09 | 0% | 0% | 16 | No
MS.CO.P2.B1.126 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 0% | 0% | 8 | No
MS.CO.P2.RB.148 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.138 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-03-01 | 2027-03-02 | 2027-03-01 | 2027-03-02 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.140 | External Block Work | 12 | Not Started | Con.Phase 04 | 2027-03-01 | 2027-03-18 | 2027-03-01 | 2027-03-18 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.152 | Columns & Walls Concreting work | 2 | Not Started | Con.Phase 04 | 2027-02-25 | 2027-02-28 | 2027-03-01 | 2027-03-02 | 0% | 0% | 3 | No
MS.CO.F4.FCD.154 | Beams and Slab Formwork | 3 | Not Started | Con.Phase 04 | 2027-02-25 | 2027-03-01 | 2027-03-01 | 2027-03-03 | 0% | 0% | 3 | No
MS.CO.P5.FA.196 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 05 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.137 | Beams and Slab Steel Fix | 3 | Not Started | Con.Phase 03 | 2027-03-01 | 2027-03-03 | 2027-03-01 | 2027-03-03 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.126 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-03-01 | 2027-03-02 | 2027-03-01 | 2027-03-02 | 0% | 0% | 0 | Yes
MS.CO.P1.FAH.168 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-02-26 | 2027-02-27 | 2027-03-01 | 2027-03-02 | 0% | 0% | 22 | No
MS.CO.P2.FBC.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-01 | 2027-03-02 | 2027-03-01 | 2027-03-02 | 0% | 0% | 14 | No
MS.CO.P3(1).FAO.149 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-02-25 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 0% | 0% | 18 | No
MS.CO.P1.FAI.161 | Internal Block Work | 12 | Not Started | Con.Phase 01 | 2027-03-02 | 2027-03-20 | 2027-03-02 | 2027-03-20 | 0% | 0% | 10 | No
MS.CO.P1.FAH.162 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-02-24 | 2027-03-17 | 2027-03-02 | 2027-03-22 | 0% | 0% | 8 | No
MS.CO.P1.FAG.166 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 01 | 2027-03-02 | 2027-03-02 | 2027-03-02 | 2027-03-02 | 0% | 0% | 1 | No
MS.CO.P2.HO.152 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-03-02 | 2027-03-22 | 2027-03-02 | 2027-03-22 | 0% | 0% | 8 | No
MS.CO.P2.FBC.134 | Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-03-02 | 2027-03-22 | 2027-03-02 | 2027-03-22 | 0% | 0% | 8 | No
MS.CO.P2.FBC.143 | Internal Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-02 | 2027-03-17 | 2027-03-02 | 2027-03-17 | 0% | 0% | 12 | No
MS.CO.P2.FBC.156 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 02 | 2027-03-02 | 2027-03-03 | 2027-03-02 | 2027-03-03 | 0% | 0% | 1 | No
MS.CO.P5.FA.199 | Beams and Slab Formwork | 2 | Not Started | Con.Phase 05 | 2027-03-02 | 2027-03-03 | 2027-03-02 | 2027-03-03 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.144 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-02-28 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 0% | 0% | 0 | Yes
MS.CO.F4.FCQ.127 | Internal Block Work | 20 | Not Started | Con.Phase 04 | 2027-03-01 | 2027-03-28 | 2027-03-03 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.138 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-02-28 | 2027-03-01 | 2027-03-03 | 2027-03-04 | 0% | 0% | 1 | No
MS.CO.P3(1).FAM.152 | External Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-03 | 2027-03-16 | 2027-03-03 | 2027-03-16 | 0% | 0% | 4 | No
MS.CO.P3(1).FAO.151 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-02-28 | 2027-03-15 | 2027-03-03 | 2027-03-18 | 0% | 0% | 11 | No
MS.CO.P3(2).B1.127 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.127 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-03 | 2027-03-04 | 2027-03-03 | 2027-03-04 | 0% | 0% | 13 | No
MS.CO.F4.FCD.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 0% | 0% | 4 | No
MS.CO.P3(2).FAK.128 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-03 | 2027-03-04 | 2027-03-03 | 2027-03-04 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.162 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-03-04 | 2027-03-24 | 2027-03-04 | 2027-03-24 | 0% | 0% | 6 | No
MS.CO.P2.FBC.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 02 | 2027-03-04 | 2027-03-04 | 2027-03-04 | 2027-03-04 | 0% | 0% | 1 | No
MS.CO.F4.FCD.155 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 04 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-07 | 0% | 0% | 3 | No
MS.CO.P5.FA.200 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 05 | 2027-03-04 | 2027-03-07 | 2027-03-04 | 2027-03-07 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.145 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-03-02 | 2027-03-02 | 2027-03-04 | 2027-03-04 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.138 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-03-04 | 2027-03-04 | 2027-03-04 | 2027-03-04 | 0% | 0% | 1 | No
MS.CO.F4.B2.124 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-02 | 2027-03-03 | 2027-03-05 | 2027-03-06 | 0% | 0% | 25 | No
MS.CO.F4.FCQ.126 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-02 | 2027-03-03 | 2027-03-05 | 2027-03-06 | 0% | 0% | 10 | No
MS.CO.P3(2).B2.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-05 | 2027-03-06 | 2027-03-05 | 2027-03-06 | 0% | 0% | 8 | No
MS.CO.P3(1).B2.135 | B2 - Block Works | 15 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-27 | 2027-03-07 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P1.FAG.161 | Internal Block Work | 12 | Not Started | Con.Phase 01 | 2027-03-07 | 2027-03-23 | 2027-03-07 | 2027-03-23 | 0% | 0% | 7 | No
MS.CO.P2.HO.143 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-03-07 | 2027-03-25 | 2027-03-07 | 2027-03-25 | 0% | 0% | 5 | No
MS.CO.F4.FCQ.139 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-03-02 | 2027-03-02 | 2027-03-07 | 2027-03-07 | 0% | 0% | 1 | No
MS.CO.F4.FCD.149 | External Block Work | 10 | Not Started | Con.Phase 04 | 2027-03-03 | 2027-03-18 | 2027-03-07 | 2027-03-21 | 0% | 0% | 2 | No
MS.CO.P3(1).B1.135 | B2 - Block Works | 8 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-18 | 2027-03-07 | 2027-03-20 | 0% | 0% | 11 | No
MS.CO.P3(2).FAL.148 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-03-03 | 2027-03-18 | 2027-03-07 | 2027-03-21 | 0% | 0% | 9 | No
MS.CO.P3(2).FAK.135 | External Block Work | 10 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-21 | 2027-03-07 | 2027-03-21 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.139 | Columns & Walls Formwork | 1 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.140 | Columns & Walls Steel Fix | 1 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.141 | Columns & Walls Concreting work | 1 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 2027-03-07 | 0% | 0% | 2 | No
MS.CO.P2.B1.135 | B1 - Block Works | 10 | Not Started | Con.Phase 02 | 2027-03-08 | 2027-03-22 | 2027-03-08 | 2027-03-22 | 0% | 0% | 8 | No
MS.CO.F4.FCD.157 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 04 | 2027-03-04 | 2027-03-04 | 2027-03-08 | 2027-03-08 | 0% | 0% | 3 | No
MS.CO.P5.FA.201 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 05 | 2027-03-08 | 2027-03-08 | 2027-03-08 | 2027-03-08 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.143 | Beams and Slab Formwork | 2 | Not Started | Con.Phase 03 | 2027-03-08 | 2027-03-09 | 2027-03-08 | 2027-03-09 | 0% | 0% | 2 | No
MS.CO.P1.FAE.164 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-08 | 2027-03-09 | 2027-03-08 | 2027-03-09 | 0% | 0% | 7 | No
MS.CO.P2.HO.154 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-08 | 2027-03-09 | 2027-03-08 | 2027-03-09 | 0% | 0% | 8 | No
MS.CO.P3(1)MQ.110 | Top Of Roof - External Block Work | 9 | Not Started | Con.Phase 03 | 2027-03-09 | 2027-03-22 | 2027-03-09 | 2027-03-22 | 0% | 0% | 2 | No
MS.CO.P3(1)MQ.112 | Special construction works planter, cross over ,water features ,canal | 10 | Not Started | Con.Phase 03 | 2027-03-09 | 2027-03-23 | 2027-03-09 | 2027-03-23 | 0% | 0% | 7 | No
MS.CO.P2.RB.143 | GF - Internal Block Work | 14 | Not Started | Con.Phase 02 | 2027-03-08 | 2027-03-27 | 2027-03-09 | 2027-03-28 | 0% | 0% | 3 | No
MS.CO.P3(1).FAM.151 | Internal Block Work | 12 | Not Started | Con.Phase 03 | 2027-03-08 | 2027-03-24 | 2027-03-09 | 2027-03-25 | 0% | 0% | 5 | No
MS.CO.P3(2).FAK.144 | Beams and Slab Steel Fix | 2 | Not Started | Con.Phase 03 | 2027-03-09 | 2027-03-14 | 2027-03-09 | 2027-03-14 | 0% | 0% | 2 | No
MS.CO.P3(1).FAN.149 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-05 | 2027-03-06 | 2027-03-09 | 2027-03-10 | 0% | 0% | 5 | No
MS.CO.P1.FAH.169 | Internal Block Work | 14 | Not Started | Con.Phase 01 | 2027-03-15 | 2027-03-31 | 2027-03-09 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P1.FAI.164 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-04 | 2027-03-05 | 2027-03-10 | 2027-03-11 | 0% | 0% | -2 | Yes
MS.CO.P1.FAF.164 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-10 | 2027-03-11 | 2027-03-10 | 2027-03-11 | 0% | 0% | 6 | No
MS.CO.P1.FAE.168 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-10 | 2027-03-11 | 2027-03-10 | 2027-03-11 | 0% | 0% | 4 | No
MS.CO.P5.FA.190 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-03-10 | 2027-03-11 | 2027-03-10 | 2027-03-11 | 0% | 0% | 9 | No
MS.CO.P3(2).FAK.136 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-10 | 2027-03-11 | 2027-03-10 | 2027-03-11 | 0% | 0% | 9 | No
MS.CO.P1.FAI.167 | External Block Work | 12 | Not Started | Con.Phase 01 | 2027-03-07 | 2027-03-23 | 2027-03-14 | 2027-03-27 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.167 | External Block Work | 12 | Not Started | Con.Phase 01 | 2027-03-14 | 2027-03-27 | 2027-03-14 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P1.FAE.167 | External Block Work | 10 | Not Started | Con.Phase 01 | 2027-03-14 | 2027-03-24 | 2027-03-14 | 2027-03-24 | 0% | 0% | 3 | No
MS.CO.P1.FAE.170 | External Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-14 | 2027-03-20 | 2027-03-14 | 2027-03-20 | 0% | 0% | 2 | No
MS.CO.P2.HO.158 | GF - External Block Work | 9 | Not Started | Con.Phase 02 | 2027-03-14 | 2027-03-23 | 2027-03-14 | 2027-03-23 | 0% | 0% | 4 | No
MS.CO.P2.FBR.132 | External Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-14 | 2027-03-24 | 2027-03-14 | 2027-03-24 | 0% | 0% | 4 | No
MS.CO.F4.FCQ.132 | External Block Work | 10 | Not Started | Con.Phase 04 | 2027-03-08 | 2027-03-22 | 2027-03-14 | 2027-03-24 | 0% | 0% | 3 | No
MS.CO.P3(1).FAN.151 | Internal Block Work | 12 | Not Started | Con.Phase 03 | 2027-03-08 | 2027-03-24 | 2027-03-14 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.152 | External Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-07 | 2027-03-18 | 2027-03-14 | 2027-03-22 | 0% | 0% | 2 | No
MS.CO.P2.FBC.149 | External Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-15 | 2027-03-25 | 2027-03-15 | 2027-03-25 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.145 | Beams and Slab Concreting work | 1 | Not Started | Con.Phase 03 | 2027-03-15 | 2027-03-15 | 2027-03-15 | 2027-03-15 | 0% | 0% | 2 | No
MS.CO.P2.FBR.136 | Internal Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-16 | 2027-03-27 | 2027-03-16 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.F4.FCD.134 | Internal Block Work | 12 | Not Started | Con.Phase 04 | 2027-03-16 | 2027-03-29 | 2027-03-16 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.F4.FCD.143 | Internal Block Work | 14 | Not Started | Con.Phase 04 | 2027-03-16 | 2027-03-31 | 2027-03-16 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.178 | External Block Work | 14 | Not Started | Con.Phase 05 | 2027-03-16 | 2027-03-31 | 2027-03-16 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.179 | Internal Block Work | 14 | Not Started | Con.Phase 05 | 2027-03-16 | 2027-03-31 | 2027-03-16 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P3(1).FAO.152 | External Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-14 | 2027-03-22 | 2027-03-16 | 2027-03-24 | 0% | 0% | 4 | No
MS.CO.P1.FAG.164 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-16 | 2027-03-17 | 2027-03-16 | 2027-03-17 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.145 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-16 | 2027-03-17 | 2027-03-16 | 2027-03-17 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.137 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-16 | 2027-03-17 | 2027-03-16 | 2027-03-17 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.147 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-10 | 2027-03-11 | 2027-03-16 | 2027-03-17 | 0% | 0% | 0 | Yes
MS.CO.P1.FAE.169 | Internal Block Work | 10 | Not Started | Con.Phase 01 | 2027-03-17 | 2027-03-28 | 2027-03-17 | 2027-03-28 | 0% | 0% | 3 | No
MS.CO.P2.HO.159 | GF - Internal Block Work | 9 | Not Started | Con.Phase 02 | 2027-03-17 | 2027-03-27 | 2027-03-17 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P2.FBR.126 | Internal Block Work | 12 | Not Started | Con.Phase 02 | 2027-03-17 | 2027-03-30 | 2027-03-17 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.136 | Internal Block Work | 10 | Not Started | Con.Phase 04 | 2027-03-15 | 2027-03-25 | 2027-03-17 | 2027-03-28 | 0% | 0% | 3 | No
MS.CO.P5.FA.172 | Internal Block Work | 12 | Not Started | Con.Phase 05 | 2027-03-17 | 2027-03-30 | 2027-03-17 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P2.HO.160 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-17 | 2027-03-18 | 2027-03-17 | 2027-03-18 | 0% | 0% | 5 | No
MS.CO.P1.FAI.169 | Internal Block Work | 12 | Not Started | Con.Phase 01 | 2027-03-17 | 2027-03-30 | 2027-03-18 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P1.FAG.167 | External Block Work | 10 | Not Started | Con.Phase 01 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.149 | GF - External Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.152 | Internal Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P2.FBR.140 | External Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.153 | Internal Block Work | 10 | Not Started | Con.Phase 04 | 2027-03-16 | 2027-03-27 | 2027-03-18 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P5.FA.197 | External Block Work | 10 | Not Started | Con.Phase 05 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P5.FA.198 | Internal Block Work | 10 | Not Started | Con.Phase 05 | 2027-03-18 | 2027-03-29 | 2027-03-18 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P3(1).FAM.153 | Internal Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-18 | 2027-03-27 | 2027-03-18 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P3(1).FAO.153 | Internal Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-16 | 2027-03-24 | 2027-03-18 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P3(2).FAL.150 | External Block Work | 6 | Not Started | Con.Phase 03 | 2027-03-14 | 2027-03-20 | 2027-03-18 | 2027-03-24 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.146 | External Block Work | 6 | Not Started | Con.Phase 03 | 2027-03-18 | 2027-03-24 | 2027-03-18 | 2027-03-24 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.148 | Internal Block Work | 6 | Not Started | Con.Phase 03 | 2027-03-18 | 2027-03-24 | 2027-03-18 | 2027-03-24 | 0% | 0% | 6 | No
MS.CO.F4.FCQ.137 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-15 | 2027-03-16 | 2027-03-18 | 2027-03-19 | 0% | 0% | 1 | No
MS.CO.P3(2).B1.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-18 | 2027-03-19 | 2027-03-18 | 2027-03-19 | 0% | 0% | 12 | No
MS.CO.P1.FAI.168 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-10 | 2027-03-11 | 2027-03-19 | 2027-03-20 | 0% | 0% | 2 | No
MS.CO.P1.FAF.168 | DE shuttering for Slab | 1 | Not Started | Con.Phase 01 | 2027-03-18 | 2027-03-18 | 2027-03-19 | 2027-03-19 | 0% | 0% | 5 | No
MS.CO.P2.FBC.155 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-19 | 2027-03-20 | 2027-03-19 | 2027-03-20 | 0% | 0% | 1 | No
MS.CO.F4.FCD.158 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 0% | 0% | 4 | No
MS.CO.P3(1)MQ.113 | Top Of Roof - Internal Block Work | 9 | Not Started | Con.Phase 03 | 2027-03-20 | 2027-03-29 | 2027-03-20 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P1.FAF.170 | External Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-20 | 2027-03-25 | 2027-03-20 | 2027-03-25 | 0% | 0% | 5 | No
MS.CO.P1.FAF.171 | Internal Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-20 | 2027-03-25 | 2027-03-20 | 2027-03-25 | 0% | 0% | 5 | No
MS.CO.P2.HO.161 | GF - External Block Work | 7 | Not Started | Con.Phase 02 | 2027-03-20 | 2027-03-27 | 2027-03-20 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P2.HO.162 | GF - Internal Block Work | 7 | Not Started | Con.Phase 02 | 2027-03-20 | 2027-03-27 | 2027-03-20 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.F4.FCQ.140 | External Block Work | 8 | Not Started | Con.Phase 04 | 2027-03-17 | 2027-03-25 | 2027-03-20 | 2027-03-28 | 0% | 0% | 1 | No
MS.CO.P1.FAI.170 | External Block Work | 8 | Not Started | Con.Phase 01 | 2027-03-14 | 2027-03-22 | 2027-03-21 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P1.FAI.171 | Internal Block Work | 8 | Not Started | Con.Phase 01 | 2027-03-14 | 2027-03-22 | 2027-03-21 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P1.FAG.169 | Internal Block Work | 10 | Not Started | Con.Phase 01 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P1.FAF.169 | Internal Block Work | 10 | Not Started | Con.Phase 01 | 2027-03-20 | 2027-03-30 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.150 | GF - Internal Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.158 | External Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-29 | 2027-03-21 | 2027-03-29 | 0% | 0% | 1 | No
MS.CO.P2.FBR.142 | Internal Block Work | 10 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.F4.FCD.160 | External Block Work | 6 | Not Started | Con.Phase 04 | 2027-03-20 | 2027-03-25 | 2027-03-21 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.F4.FCD.161 | Internal Block Work | 6 | Not Started | Con.Phase 04 | 2027-03-20 | 2027-03-25 | 2027-03-21 | 2027-03-27 | 0% | 0% | 4 | No
MS.CO.P3(1).FAN.153 | Internal Block Work | 8 | Not Started | Con.Phase 03 | 2027-03-17 | 2027-03-25 | 2027-03-21 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P3(2).FAK.142 | Internal Block Work | 10 | Not Started | Con.Phase 03 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.B1.132 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-22 | 2027-03-21 | 2027-03-22 | 0% | 0% | 9 | No
MS.CO.P2.RB.151 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-22 | 2027-03-21 | 2027-03-22 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.141 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-21 | 2027-03-22 | 2027-03-21 | 2027-03-22 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.203 | External Block Work | 10 | Not Started | Con.Phase 05 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.202 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-03-21 | 2027-03-22 | 2027-03-21 | 2027-03-22 | 0% | 0% | 0 | Yes
MS.CO.P3(2).B2.133 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-21 | 2027-03-22 | 2027-03-21 | 2027-03-22 | 0% | 0% | 9 | No
MS.CO.P5.FA.204 | Internal Block Work | 10 | Not Started | Con.Phase 05 | 2027-03-21 | 2027-03-31 | 2027-03-21 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.FBC.160 | Internal Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-22 | 2027-03-30 | 2027-03-22 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.142 | Internal Block Work | 8 | Not Started | Con.Phase 04 | 2027-03-20 | 2027-03-28 | 2027-03-22 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P1.FAG.168 | DE shuttering for Slab | 2 | Not Started | Con.Phase 01 | 2027-03-22 | 2027-03-23 | 2027-03-22 | 2027-03-23 | 0% | 0% | 1 | No
MS.CO.P2.FBC.159 | DE shuttering for Slab | 2 | Not Started | Con.Phase 02 | 2027-03-22 | 2027-03-23 | 2027-03-22 | 2027-03-23 | 0% | 0% | 1 | No
MS.CO.P5.FA.205 | DE shuttering for Slab | 2 | Not Started | Con.Phase 05 | 2027-03-22 | 2027-03-23 | 2027-03-22 | 2027-03-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.149 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-19 | 2027-03-20 | 2027-03-22 | 2027-03-23 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.147 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-22 | 2027-03-23 | 2027-03-22 | 2027-03-23 | 0% | 0% | 1 | No
MS.CO.P1.FAE.171 | Internal Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-23 | 2027-03-29 | 2027-03-23 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P2.RB.152 | GF - External Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-23 | 2027-03-31 | 2027-03-23 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.RB.153 | GF - Internal Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-23 | 2027-03-31 | 2027-03-23 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.143 | External Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-23 | 2027-03-31 | 2027-03-23 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P2.FBR.144 | Internal Block Work | 8 | Not Started | Con.Phase 02 | 2027-03-23 | 2027-03-31 | 2027-03-23 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.F4.B1.122 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-19 | 2027-03-20 | 2027-03-23 | 2027-03-24 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.141 | DE shuttering for Slab | 1 | Not Started | Con.Phase 04 | 2027-03-19 | 2027-03-19 | 2027-03-23 | 2027-03-23 | 0% | 0% | 1 | No
MS.CO.F4.FCD.159 | DE shuttering for Slab | 2 | Not Started | Con.Phase 04 | 2027-03-21 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 0% | 0% | 3 | No
MS.CO.P1.FAH.170 | External Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-21 | 2027-03-28 | 2027-03-23 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P1.FAH.171 | Internal Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-21 | 2027-03-28 | 2027-03-23 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P1.FAG.170 | External Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P1.FAG.171 | Internal Block Work | 6 | Not Started | Con.Phase 01 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P2.FBC.161 | External Block Work | 6 | Not Started | Con.Phase 02 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P2.FBC.162 | Internal Block Work | 6 | Not Started | Con.Phase 02 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.143 | External Block Work | 6 | Not Started | Con.Phase 04 | 2027-03-20 | 2027-03-25 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.F4.FCQ.144 | Internal Block Work | 6 | Not Started | Con.Phase 04 | 2027-03-20 | 2027-03-25 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P5.FA.207 | External Block Work | 6 | Not Started | Con.Phase 05 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 0 | Yes
MS.CO.P5.FA.208 | Internal Block Work | 6 | Not Started | Con.Phase 05 | 2027-03-24 | 2027-03-30 | 2027-03-24 | 2027-03-30 | 0% | 0% | 1 | No
MS.CO.P3(2).FAL.152 | External Block Work | 7 | Not Started | Con.Phase 03 | 2027-03-21 | 2027-03-28 | 2027-03-24 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAL.153 | Internal Block Work | 7 | Not Started | Con.Phase 03 | 2027-03-21 | 2027-03-28 | 2027-03-24 | 2027-03-31 | 0% | 0% | 0 | Yes
MS.CO.P3(2).FAK.151 | External Block Work | 4 | Not Started | Con.Phase 03 | 2027-03-24 | 2027-03-28 | 2027-03-24 | 2027-03-28 | 0% | 0% | 1 | No
MS.CO.P3(2).FAK.149 | DE shuttering for Slab | 2 | Not Started | Con.Phase 03 | 2027-03-24 | 2027-03-25 | 2027-03-24 | 2027-03-25 | 0% | 0% | 2 | No
MS.CO.F4.FCD.162 | External Block Work | 4 | Not Started | Con.Phase 04 | 2027-03-23 | 2027-03-27 | 2027-03-25 | 2027-03-29 | 0% | 0% | 2 | No
MS.CO.P5.FA.208 | Internal Block Work | 6 | Not Started | Con.Phase 05 | 2027-03-25 | 2027-03-31 | 2027-05-27 | 2027-06-02 | 0% | 0% | -50 | Yes

## Delays
Phase Delay/Ahead | BL Finish Date | Forecast Finish Date | Variance Finish Date | Delay Reason | Recovery Action | Responsible
Phase-1 | 2027-03-31 | 2027-03-31 | 0 |  |  | ACC OIC
Phase-2 | 2027-03-31 | 2027-03-31 | 0 |  |  | ACC
Phase-3 | 2027-03-31 | 2027-03-31 | 0 |  |  | ACC OIC
Phase-4 | 2027-03-31 | 2027-03-31 | 0 |  |  | ACC
Phase-5 | 2027-03-31 | 2027-03-31 | 0 | Risk for Delay In Remove Ramp | Increase Productivity | ACC
Overall | - | - | - | Delay in Reciving Loading Plan | Close follow-up with concerned authorities | OIC
Overall |  |  |  | Delay in Reciving MEP IFC | Close follow-up with concerned authorities | OIC
Overall | - | - | - | Obtaining required statutory approvals | Close follow-up with concerned authorities | OIC

## Issues_Risks
Risk ID | Risk Description | Impact Summary | Probability | Impact | Risk Level | Risk Owner | Mitigation | Target Date
R-01 | Delay in Soldier/Shoulder Pile Works | Overlapping with CMC works in valley area. Delay will remain within available float provided completion occurs prior to CMC completion; no impact anticipated unless float is consumed. | High (4/5) | High (4/5) | High | ACC | Close monitoring of progress, maintain resource allocation, ensure completion before CMC finish | 2026-06-13
R-02 | Submitting New Design for Slab As Post Tension | The IFC drawings for the Columns have been received.ACC to Submit the Design for Post Tension Slab. ACC Recivied IFC for first Basement ,ACC Waiting for Other IFC Elemnts to complete the Engineering works. | Medium (3/5) | Medium (3/5) | Medium | ACC/ OIC | ACC toFinish the Design for the Post Tension Slab and Submit it. OIC To send the Remaining IFC. | 2026-06-14
R-03 | Low progress in ramp removal works | Despite noticeable improvement in ramp removal activities, the daily achieved quantities remain consistently below planned targets . This continues to impact foundation works in Phase 5 due to delayed area handover and restricted access. | High (4/5) | High (4/5) | High | ACC | Increase resources and deploy additional equipment to accelerate ramp removal. Closely monitor daily productivity against planned targets to recover delays and enable timely access for Phase 5 foundation works. | 2026-06-20
R-04 | Pending statutory approvals for concrete works | Obtaining required statutory approvals . This may impact planned casting activities and subsequent sequencing if not resolved in a timely manner. | Medium (3/5) | High (4/5) | Medium | OIC | Close follow-up with concerned authorities and stakeholders to expedite permit issuance and avoid delays to scheduled concrete activities. | 2026-06-14
R-05 | Delay in Phase-2 Progress | Delay in Phase-2 Progress Impact on SPI | Low (2/5) | Medium (3/5) | Medium | ACC | ACC to Increase the Reseources Required | 2026-06-13

## Site_Photos
Date | Phase | Description | Photo URL
2026-06-17 | Phase-1 | Vertical Items Works | /progress-photos/Ph-1.jpeg
2026-06-17 | Phase-2 | Drops Excavation | /progress-photos/Ph-2.jpeg
2026-06-17 | Phase-3 | Concrete Pouring Works | /progress-photos/Ph-3.jpeg
2026-06-17 | Phase-4 | Soldier Piles works | /progress-photos/Ph-4.jpeg
2026-06-17 | Phase-5 | Steel Works | /progress-photos/Ph-5.jpeg

## SPI Trend
Month | 01-Feb-2026 | 01-Mar-2026 | 01-Apr-2026 | 01-May-2026 | 01-Jun-2026 | 01-Jul-2026 | 01-Aug-2026 | 01-Sep-2026 | 01-Oct-2026
SPI | 1.1161 | 1.0432 | 0.78253 | 0.55757 | 0.99253

## S-Curve
MONTH | 01-Oct-2025 | 01-Nov-2025 | 01-Dec-2025 | 01-Jan-2026 | 01-Feb-2026 | 01-Mar-2026 | 01-Apr-2026 | 01-May-2026 | 01-Jun-2026 | 01-Jul-2026 | 01-Aug-2026 | 01-Sep-2026 | 01-Oct-2026 | 01-Nov-2026 | 01-Dec-2026 | 01-Jan-2027 | 01-Feb-2027 | 01-Mar-2027
PLANNED % | 0.06066% | 0.09357% | 0.4855% | 0.7215% | 1.876% | 1.745% | 3.024% | 0.7675% | 2.735% | 7.266% | 10.28% | 12.46% | 10.62% | 11.25% | 11.36% | 11.73% | 9.652% | 3.883%
CUM PLANNED % | 0.06066% | 0.1542% | 0.6398% | 1.361% | 3.237% | 4.982% | 8.006% | 8.773% | 11.51% | 18.77% | 29.05% | 41.51% | 52.13% | 63.38% | 74.74% | 86.46% | 96.12% | 100%
Actual % | 0.06094% | 0.1002% | 0.523% | 0.7822% | 2.164% | 1.77% | 1.79% | 1.655% | 0.9916%
CUM Actual % | 0.06094% | 0.1612% | 0.6841% | 1.466% | 3.63% | 5.4% | 7.19% | 8.845% | 9.837%

## Lookahead_3Weeks
Activity ID | Activity Name | Original Duration | Activity Status | 02- Con.Phase | Start | Finish | Performance % Complete | Total Float | Critical
MS.EN.P5.ALL.104 | Ramp Removal | 82 | In Progress | Con.Phase 05 | 12-Feb-26 A | 2026-06-28 | 93% | 0 | Yes
MS.CO.P1.FO.200 | Blinding concrete for Upper Part | 55 | In Progress | Con.Phase 01 | 05-Apr-26 A | 2026-06-18 | 99.82% | 237 | No
MS.CO.P5.FO.101 | Blinding concrete for lower Part of Foundation | 62 | In Progress | Con.Phase 05 | 07-Apr-26 A | 2026-06-28 | 95% | 228 | No
MS.CO.P1.FO.210 | Surface preparation and Angle filet at RW Edge | 51 | In Progress | Con.Phase 01 | 09-Apr-26 A | 2026-06-18 | 99.9% | 237 | No
MS.CO.P1.FO.220 | Water Proofing Membrane under Raft Foundation | 52 | In Progress | Con.Phase 01 | 11-Apr-26 A | 2026-06-21 | 95% | 234 | No
MS.CO.P3(2).FO.118 | Rebars for 1st layer for Foundation | 49 | In Progress | Con.Phase 03 | 20-Apr-26 A | 2026-06-25 | 65% | 28 | No
MS.CO.P5.FO.103 | Blinding concrete for Upper Part | 50 | In Progress | Con.Phase 05 | 21-Apr-26 A | 2026-06-29 | 85% | 227 | No
MS.CO.P5.FO.104 | Water Proofing Membrane under Raft Foundation | 47 | In Progress | Con.Phase 05 | 28-Apr-26 A | 2026-07-01 | 90% | 225 | No
MS.EN.P4.ALL.157 | trimming for CMC (up to bottom level of drop panel) | 31 | In Progress | Con.Phase 04 | 10-May-26 A | 2026-06-29 | 95% | 8 | No
MS.CO.P5.FO.105 | Rebars for 1st layer for Foundation | 27 | In Progress | Con.Phase 05 | 18-May-26 A | 2026-07-05 | 80% | 25 | No
MS.CO.P1.FO.125 | Foundations Concrete Pouring | 18 | In Progress | Con.Phase 01 | 24-May-26 A | 2026-06-21 | 95% | 4 | No
MS.CO.P1.B2.100 | B2 - Columns Steel Fix | 10 | In Progress | Con.Phase 01 | 01-Jun-26 A | 2026-06-24 | 50% | 1 | No
MS.CO.P2.FO.320 | Excavation for drop Panels and Trenches | 13 | In Progress | Con.Phase 02 | 01-Jun-26 A | 2026-06-22 | 90% | 233 | No
MS.CO.P1.FO.126 | Rebars for 1st layer for Foundation | 8 | In Progress | Con.Phase 01 | 08-Jun-26 A | 2026-06-24 | 40% | 0 | No
MS.CO.P1.FO.127 | Installation for Mechanical and Electrical Embeds | 4 | In Progress | Con.Phase 01 | 10-Jun-26 A | 2026-06-28 | 40% | 0 | No
MS.CO.P1.B2.101 | B2 - Columns Formwork | 12 | In Progress | Con.Phase 01 | 11-Jun-26 A | 2026-06-29 | 10% | 2 | No
MS.CO.P2.FO.100 | Excavation for drop Panels and Trenches | 5 | In Progress | Con.Phase 02 | 11-Jun-26 A | 2026-06-23 | 60% | 0 | Yes
MS.CO.P1.B2.103 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 13-Jun-26 A | 2026-06-24 | 30% | 1 | No
MS.CO.P1.B2.106 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 14-Jun-26 A | 2026-07-01 | 25% | 0 | Yes
MS.CO.P1.B2.113 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 01 | 15-Jun-26 A | 2026-07-01 | 20% | 7 | No
MS.CO.P5.FO.118 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 9 | In Progress | Con.Phase 05 | 15-Jun-26 A | 2026-06-28 | 30% | 14 | No
MS.CO.P5.FO.109 | Installation for Mechanical and Electrical Embeds | 6 | In Progress | Con.Phase 05 | 15-Jun-26 A | 2026-06-24 | 50% | 14 | No
MS.CO.P3(1).B2.100 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 03 | 15-Jun-26 A | 2026-06-29 | 20% | 13 | No
MS.CO.P3(2).FO.124 | Installation for Mechanical and Electrical Embeds | 6 | In Progress | Con.Phase 03 | 15-Jun-26 A | 2026-06-29 | 30% | 28 | No
MS.CO.P3(1).B2.101 | B2 - Columns Steel Fix | 12 | In Progress | Con.Phase 03 | 16-Jun-26 A | 2026-06-30 | 10% | 14 | No
MS.CO.P1.B2.145 | B2 - Walls Steel Fix | 12 | In Progress | Con.Phase 01 | 16-Jun-26 A | 2026-06-30 | 10% | 2 | No
MS.CO.P2.FO.330 | Blinding concrete for lower Part of Foundation | 3 | In Progress | Con.Phase 02 | 16-Jun-26 A | 2026-06-21 | 30% | 2 | No
MS.CO.P1.FO.540 | Earthing and Lightning Protection System | 4 | In Progress | Con.Phase 02 | 16-Jun-26 A | 2026-06-21 | 40% | 3 | No
MS.CO.P1.B2.104 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 0% | 1 | No
MS.CO.P1.B2.175 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 0% | 3 | No
MS.CO.P1.B2.205 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-18 | 2026-07-01 | 0% | 4 | No
MS.CO.P3(1).B2.200 | B2 - Walls Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-06-18 | 2026-06-25 | 0% | 1 | No
MS.EN.P4.ALL.177 | Perform Geophysical Activity | 4 | Not Started |  | 2026-06-18 | 2026-06-22 | 0% | -1 | Yes
MS.CO.P5.FO.114 | Formwork for Foundations | 6 | Not Started | Con.Phase 05 | 2026-06-20 | 2026-06-25 | 0% | 16 | No
MS.CO.P1.B2.116 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-21 | 2026-07-04 | 0% | 7 | No
MS.CO.P3(1).B2.103 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-06-21 | 2026-07-04 | 0% | 13 | No
MS.CO.P1.B2.107 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-22 | 2026-07-05 | 0% | 0 | Yes
MS.CO.P3(1).B2.104 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-06-22 | 2026-07-05 | 0% | 14 | No
MS.CO.P1.B2.155 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-22 | 2026-07-05 | 0% | 2 | No
MS.CO.P2.FO.340 | Block work for Drop Panels | 1 | Not Started | Con.Phase 02 | 2026-06-22 | 2026-06-22 | 0% | 2 | No
MS.CO.P1.B2.185 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-23 | 2026-07-06 | 0% | 3 | No
MS.CO.P1.B2.215 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-23 | 2026-07-06 | 0% | 4 | No
MS.CO.P3(1).B2.203 | B2 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-06-23 | 2026-06-30 | 0% | 1 | No
MS.CO.P2.FO.350 | Blinding concrete for Upper Part | 1 | Not Started | Con.Phase 02 | 2026-06-23 | 2026-06-23 | 0% | 2 | No
MS.EN.P4.ALL.187 | Soil Improvement | 16 | Not Started |  | 2026-06-23 | 2026-07-11 | 0% | -1 | Yes
A1570 | Dewatering system | 18 | Not Started |  | 2026-06-23 | 2026-07-13 | 0% | 15 | No
MS.CO.P3(2).FO.126 | Formwork for Foundations | 6 | Not Started | Con.Phase 03 | 2026-06-24 | 2026-06-30 | 0% | 30 | No
MS.CO.P1.FO.250 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 02 | 2026-06-24 | 2026-06-27 | 0% | 0 | Yes
MS.CO.P2.FO.140 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 02 | 2026-06-24 | 2026-07-01 | 0% | 2 | No
MS.CO.P2.FO.360 | Surface preparation and Angle filet at RW Edge | 4 | Not Started | Con.Phase 02 | 2026-06-24 | 2026-06-28 | 0% | 2 | No
MS.CO.P3(1).B2.107 | B2 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-06-25 | 2026-07-08 | 0% | 13 | No
MS.CO.P1.B2.235 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 01 | 2026-06-25 | 2026-07-08 | 0% | 1 | No
MS.CO.P1.FO.128 | Formwork for Foundations | 5 | Not Started | Con.Phase 01 | 2026-06-27 | 2026-07-01 | 0% | 0 | No
MS.CO.P1.FO.129 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 5 | Not Started | Con.Phase 01 | 2026-06-27 | 2026-07-01 | 0% | 0 | No
MS.CO.P3(1).B2.108 | B2 - Columns Concreting work | 12 | Not Started | Con.Phase 03 | 2026-06-27 | 2026-07-09 | 0% | 14 | No
MS.CO.P3(2).FO.128 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6 | Not Started | Con.Phase 03 | 2026-06-27 | 2026-07-02 | 0% | 28 | No
MS.CO.P2.FO.101 | Blinding concrete for lower Part of Foundation | 3 | Not Started | Con.Phase 02 | 2026-06-28 | 2026-06-30 | 0% | 0 | Yes
MS.CO.P3(1).B2.207 | B2 - Walls Concreting work | 7 | Not Started | Con.Phase 03 | 2026-06-28 | 2026-07-05 | 0% | 1 | No
MS.CO.F4.FO.100 | Backfilling Including Drop Panels and Trenches | 9 | Not Started | Con.Phase 04 | 2026-06-29 | 2026-07-08 | 0% | -1 | Yes
MS.CO.P5.FO.124 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 05 | 2026-06-29 | 2026-06-30 | 0% | 14 | No
MS.EN.P5.ALL.106 | Perform Geophysical Activity | 0 | Not Started | Con.Phase 05 | 2026-06-29 | 2026-06-29 | 0% | 0 | Yes
MS.EN.P5.ALL.107 | Report preparation and Soil Improvement Proposal | 1 | Not Started | Con.Phase 05 | 2026-06-29 | 2026-06-29 | 0% | 0 | Yes
MS.CO.P2.FO.370 | Water Proofing Membrane under Raft Foundation | 6 | Not Started | Con.Phase 02 | 2026-06-29 | 2026-07-05 | 0% | 2 | No
MS.CO.P1.B2.102 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 01 | 2026-06-30 | 2026-07-06 | 0% | 2 | No
MS.CO.P3(1).B2.102 | B2 - Columns Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-06-30 | 2026-07-13 | 0% | 11 | No
MS.EN.P5.ALL.110 | Soil Improvement (By Other) | 6 | Not Started | Con.Phase 05 | 2026-06-30 | 2026-07-06 | 0% | 0 | Yes
MS.CO.P1.B2.245 | B2 - Walls Formwork | 12 | Not Started | Con.Phase 01 | 2026-06-30 | 2026-07-13 | 0% | 1 | No
MS.CO.P3(1).B2.201 | B2 - Walls Steel Fix | 7 | Not Started | Con.Phase 03 | 2026-06-30 | 2026-07-07 | 0% | 2 | No
MS.CO.P3(1).B2.202 | B2 - Walls Steel Fix | 12 | Not Started | Con.Phase 03 | 2026-06-30 | 2026-07-13 | 0% | 8 | No
MS.EN.P4.ALL.167 | Remaining CMC | 6 | Not Started |  | 2026-06-30 | 2026-07-06 | 0% | 6 | No
MS.CO.P2.FO.102 | Block work for Drop Panels | 2 | Not Started | Con.Phase 02 | 2026-07-01 | 2026-07-02 | 0% | 0 | Yes
MS.CO.P1.FO.130 | Foundations Concrete Pouring | 2 | Not Started | Con.Phase 01 | 2026-07-02 | 2026-07-04 | 0% | 0 | No
MS.CO.P1.B2.105 | B2 - Columns Concreting work | 6 | Not Started | Con.Phase 01 | 2026-07-02 | 2026-07-08 | 0% | 1 | No
MS.CO.P1.FO.480 | Earthing and Lightning Protection System | 3 | Not Started | Con.Phase 02 | 2026-07-02 | 2026-07-05 | 0% | 2 | No
MS.CO.P2.FO.200 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 02 | 2026-07-02 | 2026-07-09 | 0% | 2 | No
MS.CO.P2.FO.103 | Blinding concrete for Upper Part | 2 | Not Started | Con.Phase 02 | 2026-07-04 | 2026-07-05 | 0% | 0 | Yes
MS.CO.P3(2).FO.129 | Foundations Concrete Pouring | 1 | Not Started | Con.Phase 03 | 2026-07-04 | 2026-07-04 | 0% | 28 | No
MS.CO.P1.B2.118 | B2 - Columns Concreting work | 5 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-09 | 0% | 7 | No
MS.CO.P1.B2.119 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-11 | 0% | 0 | No
MS.CO.P3(1).B2.105 | B2 - Columns Formwork | 12 | Not Started | Con.Phase 03 | 2026-07-05 | 2026-07-18 | 0% | 11 | No
MS.CO.P1.B2.265 | B2 - Walls Steel Fix | 6 | Not Started | Con.Phase 01 | 2026-07-05 | 2026-07-11 | 0% | 7 | No
MS.CO.P1.B2.109 | B2 - Columns Concreting work | 5 | Not Started | Con.Phase 01 | 2026-07-06 | 2026-07-11 | 0% | 0 | Yes
MS.CO.P2.FO.104 | Surface preparation and Angle filet at RW Edge | 4 | Not Started | Con.Phase 02 | 2026-07-06 | 2026-07-09 | 0% | 0 | Yes
MS.CO.P5.B2.100 | B2 - Columns Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-07-06 | 2026-07-12 | 0% | 10 | No
MS.CO.P1.B2.165 | B2 - Walls Concreting work | 3 | Not Started | Con.Phase 01 | 2026-07-06 | 2026-07-08 | 0% | 2 | No
MS.CO.P2.FO.150 | Blinding concrete for lower Part of Foundation | 3 | Not Started | Con.Phase 02 | 2026-07-06 | 2026-07-08 | 0% | 2 | No
MS.CO.P5.FO.165 | Excavation for drop Panels and Trenches | 7 | Not Started | Con.Phase 05 | 2026-07-06 | 2026-07-13 | 0% | 0 | Yes
MS.CO.P5.B2.200 | Walls Steel Fix | 6 | Not Started | Con.Phase 05 | 2026-07-06 | 2026-07-12 | 0% | 10 | No
MS.CO.P3(1).B2.204 | B2 - Walls Formwork | 7 | Not Started | Con.Phase 03 | 2026-07-06 | 2026-07-13 | 0% | 1 | No
A1060 | Post-Grouting Verification Test | 3 | Not Started | Con.Phase 05 | 2026-07-07 | 2026-07-09 | 0% | 0 | Yes
MS.CO.P1.B2.195 | B2 - Walls Concreting work | 8 | Not Started | Con.Phase 01 | 2026-07-07 | 2026-07-15 | 0% | 3 | No
MS.CO.P1.B2.225 | B2 - Walls Concreting work | 8 | Not Started | Con.Phase 01 | 2026-07-07 | 2026-07-15 | 0% | 4 | No
MS.CO.P1.B2.122 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 01 | 2026-07-08 | 2026-07-14 | 0% | 0 | No
MS.CO.P2.FO.118 | Rebars for 1st layer for Foundation | 8 | Not Started | Con.Phase 02 | 2026-07-08 | 2026-07-16 | 0% | 0 | Yes
MS.CO.P5.B2.105 | B2 - Columns Formwork | 6 | Not Started | Con.Phase 05 | 2026-07-08 | 2026-07-14 | 0% | 10 | No
MS.CO.P5.B2.205 | Walls Formwork | 6 | Not Started | Con.Phase 05 | 2026-07-08 | 2026-07-14 | 0% | 10 | No

## Website_API_Map
Purpose | Sheet Name | Excel Table Name | Recommended Website Endpoint | Notes
Project header information | Project_Info | ProjectInfoTable | /api/project-info | One row only. Used for website title/header.
Overall KPI cards | Overall_Progress | OverallProgressTable | /api/overall-progress | Report Date, Planned, Actual, SPI and forecast dates.
Phase progress cards/chart | Phase_Progress | PhaseProgressTable | /api/phase-progress | One row per project phase.
Activity register / Gantt source | Activities | ActivitiesTable | /api/activities | Main detailed activity list. Keep Activity ID unique.
Delay summary | Delays | DelaysTable | /api/delays | Used for delay page and recovery actions.
Issues & risks | Issues_Risks | IssuesRisksTable | /api/issues-risks | Used for risk/issue page.
Site photo gallery | Site_Photos | SitePhotosTable | /api/site-photos | Photo URL must be a shareable direct/public link.
SPI trend chart | SPI Trend | SPITrendTable | /api/spi-trend | Months in row 1, SPI in row 2.
S-Curve chart | S-Curve | SCurveTable | /api/s-curve | Monthly planned/actual rows for S-Curve.

## Website_Setup
Website Dynamic Excel Setup - Ready Checklist
1 | Upload this workbook to OneDrive/SharePoint and keep the same file as the live data source.
2 | The website should read the Excel Tables listed in Website_API_Map, not random cell ranges.
3 | When adding new rows, type inside the existing Excel Table so the table expands automatically.
4 | Do not rename sheets or Excel Table names after the website is connected.
5 | Photo URLs must be accessible to website viewers or stored in the website storage.
6 | Recommended first website pages: Login, Dashboard, Progress, Activities, Delays, Risks, Photos, Reports.
7 | Use a scheduled refresh / API re-fetch so website values update after Excel changes.